## Shivalaya
Project ID | CODE1 | CODE2 | Project Title | Project Name | SCHEMENAME_ENG | SCHEMENAME_BEN | PACKAGEID | Package No. | COMPONENTSUBHEADID | COMPONENTSUBHEADNAME | Upazila ID | Road ID | Length of Road (Km) | DISTRICTID | Date of Completion | Name of Contractor | Date of Contract | FINANCIALYEAR | SCHEMECODE | Physical Progress (%) | STATUS
1 |  |  | Construction of Upazilla Muktijoddha Complex(1st Revised) | CUMCP | UMC/MAN/SHI/ 15/C-237 |  | 1 | UMC/MAN/SHI/ 15/C-237 |  |  | 36606 |  | 0 | 366 | 4/26/2016 | M/S.Debesh Traders | 4/26/2016 | 2018 | UMC/MAN/SHI/ 15/C-237 | 0 | 0
2 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-37 |  | 2 | IRIDP-2/ Mnk/DW-37 |  |  | 36606 | 356784001 | 1.08 | 366 | 4/26/2017 | M/S. Al-Mamun Traders | 4/26/2017 | 2018 | IRIDP-2/ Mnk/DW-37 | 35 | 0
3 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-50 |  | 3 | IRIDP-2/ Mnk/DW-50 |  |  | 36606 | 356782010 | 1.24 | 366 | 4/26/2018 | M/S MM Bricks | 4/26/2018 | 2018 | IRIDP-2/ Mnk/DW-50 | 20 | 0
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-51 |  | 4 | IRIDP-2/ Mnk/DW-51 |  |  | 36606 | 356783007 | 1 | 366 | 4/26/2019 | M/S Raka Enterprise, Manikganj | 4/26/2019 | 2018 | IRIDP-2/ Mnk/DW-51 | 50 | 0
5 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-57 |  | 5 | IRIDP-2/ Mnk/DW-57 |  |  | 36606 | 356784009 | 1.2 | 366 | 4/26/2020 | M/S Reba Construction Manikganj | 4/26/2020 | 2018 | IRIDP-2/ Mnk/DW-57 | 30 | 0
6 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-58 |  | 6 | IRIDP-2/ Mnk/DW-58 |  |  | 36606 | 356783005 | 0.9 | 366 | 4/26/2021 | M/S. Israfil Traders | 4/26/2021 | 2018 | IRIDP-2/ Mnk/DW-58 | 0 | 0
7 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-59 |  | 7 | IRIDP-2/ Mnk/DW-59 |  |  | 36606 | 356784019 | 0.63 | 366 | 4/26/2022 | M/S Hemal Traders, Garpara, Manikganj. | 4/26/2022 | 2018 | IRIDP-2/ Mnk/DW-59 | 0 | 0
8 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-60 |  | 8 | IRIDP-2/ Mnk/DW-60 |  |  | 36606 | 356784024 | 0.75 | 366 | 4/26/2023 | M/S Hemal Traders, Garpara, Manikganj. | 4/26/2023 | 2018 | IRIDP-2/ Mnk/DW-60 | 0 | 0
9 |  |  | Important Rural Infrastructure Development Project On Priority Basis(IRIDP-II) | IRIDP-2 | IRIDP-2/ Mnk/DW-72 |  | 9 | IRIDP-2/ Mnk/DW-72 |  |  | 36606 | 356785094 | 0.97 | 366 | 4/26/2024 | M/S. Twin Trade | 4/26/2024 | 2018 | IRIDP-2/ Mnk/DW-72 | 0 | 0
10 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-3 |  | 10 | IRIDP/ Mnk/W-3 |  |  | 36606 | 356785039 | 1 | 366 | 4/26/2025 | M/S. Mona Traders | 4/26/2025 | 2018 | IRIDP/ Mnk/W-3 | 100 | 0
11 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-28 |  | 11 | IRIDP/ Mnk/W-28 |  |  | 36606 |  | 1 | 366 | 4/26/2026 | M/S. Sarnamoni fish & Co. | 4/26/2026 | 2018 | IRIDP/ Mnk/W-28 | 100 | 0
12 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-30 |  | 12 | IRIDP/ Mnk/W-30 |  |  | 36606 |  | 0.79 | 366 | 4/26/2027 | M/S. Pervez Enterprise | 4/26/2027 | 2018 | IRIDP/ Mnk/W-30 | 100 | 0
13 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-27 |  | 13 | IRIDP/ Mnk/W-27 |  |  | 36606 |  | 1.5 | 366 | 4/26/2028 | M/S. Rana Enterprise | 4/26/2028 | 2018 | IRIDP/ Mnk/W-27 | 100 | 0
14 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-47 |  | 14 | IRIDP/ Mnk/W-47 |  |  | 36606 |  | 1 | 366 | 4/26/2029 | M/S. Debsh Traders | 4/26/2029 | 2018 | IRIDP/ Mnk/W-47 | 100 | 0
15 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-32 |  | 15 | IRIDP/ Mnk/W-32 |  |  | 36606 |  | 0.88 | 366 | 4/26/2030 | M/S. Hera Corporation | 4/26/2030 | 2018 | IRIDP/ Mnk/W-32 | 100 | 0
16 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-46 |  | 16 | IRIDP/ Mnk/W-46 |  |  | 36606 |  | 0.88 | 366 | 4/26/2031 | M/S. M.A Quddus | 4/26/2031 | 2018 | IRIDP/ Mnk/W-46 | 100 | 0
17 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/W-33 |  | 17 | IRIDP/ Mnk/W-33 |  |  | 36606 |  | 1.25 | 366 | 4/26/2032 | M/S. Al-Amin Enterprise | 4/26/2032 | 2018 | IRIDP/ Mnk/W-33 | 75 | 0
18 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP | IRIDP/ Mnk/TP-57 |  | 18 | IRIDP/ Mnk/TP-57 |  |  | 36606 |  | 2.5 | 366 | 4/26/2033 | L.C.S | 4/26/2033 | 2018 | IRIDP/ Mnk/TP-57 | 0 | 0
19 |  |  | Rural Infrastructure Development Project: Greater Dhaka, Tangail & Kishoreganj Districts | GDP-2 | GDP-II/MAN/ Ghi/W(B)-58 |  | 19 | GDP-II/MAN/ Ghi/W(B)-58 |  |  | 36606 | 356784030 | 0 | 366 | 4/26/2034 | M/s. Debesh Traders | 4/26/2034 | 2018 | GDP-II/MAN/ Ghi/W(B)-58 | 80 | 0
20 |  |  | Rural Infrastructure Development Project: Greater Dhaka, Tangail & Kishoreganj Districts | GDP-2 | GDP-II/MAN/ Ghi/W(R)-74 |  | 20 | GDP-II/MAN/ Ghi/W(R)-74 |  |  | 36606 | 356784012 | 0.35 | 366 | 4/26/2035 | M/s.Al-Mamun Traders | 4/26/2035 | 2018 | GDP-II/MAN/ Ghi/W(R)-74 | 75 | 0
21 |  |  | Rural Infrastructure Development Project: Greater Dhaka, Tangail & Kishoreganj Districts | GDP-2 | GDP-II/MAN/ Ghi/W(R)-79 |  | 21 | GDP-II/MAN/ Ghi/W(R)-79 |  |  | 36606 | 356784035 | 0.87 | 366 | 4/26/2036 | M/s.Al-Mamun Traders | 4/26/2036 | 2018 | GDP-II/MAN/ Ghi/W(R)-79 | 20 | 0
22 |  |  | Third Primary Education Development Program(PEDP-III) | PEDP-3 | PEDP-III/MNK/SHI/2011-12/W2.0551 |  | 22 | PEDP-III/MNK/SHI/2011-12/W2.0551 |  |  | 36606 |  | 0 | 366 | 4/26/2037 | M/S Rana Enterprise | 4/26/2037 | 2018 | PEDP-III/MNK/SHI/2011-12/W2.0551 | 100 | 0
23 |  |  | Third Primary Education Development Program(PEDP-III) | PEDP-3 | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 |  | 23 | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 |  |  | 36606 |  | 0 | 366 | 4/26/2038 | M/S Sthapati Construction | 4/26/2038 | 2018 | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | 0 | 0
24 |  |  | Third Primary Education Development Program(PEDP-III) | PEDP-3 | PEDP-III/MNK/SHI/2011-12/W3.0333 |  | 24 | PEDP-III/MNK/SHI/2011-12/W3.0333 |  |  | 36606 |  | 0 | 366 | 4/26/2039 | M/S Rana Enterprise | 4/26/2039 | 2018 | PEDP-III/MNK/SHI/2011-12/W3.0333 | 100 | 0

## Savar
Project ID | CODE1 | CODE2 | Project Title | Project Name | SCHEMENAME_ENG | SCHEMENAME_BEN | PACKAGEID | Package No. | COMPONENTSUBHEADID | COMPONENTSUBHEADNAME | Upazila ID | Road ID | Length of Road (Km) | DISTRICTID | Date of Completion | Name of Contractor | Date of Contract | FINANCIALYEAR | SCHEMECODE | Physical Progress (%) | STATUS
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka - Aricha Highway Ashulia GC Road (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/ W-01 |  |  | 36105 |  | 10.67 | 361 | 15/07/2014 | Mir Akhtar Hossain Ltd | 15/07/2014 | 2018 | CRDP/LGED/Savar/ ICB/2013/ W-01 |  | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka - Aricha Highway Ashulia GC Road side Drain and Cross Culverts (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/ W-02 |  |  | 36105 |  | 10.67 | 361 | 15/07/2014 | Mir Akhtar Hossain Ltd | 15/07/2015 | 2018 | CRDP/LGED/Savar/ ICB/2013/ W-02 | 10 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road (Ch. 0.00 - 5770m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/ W-03 |  |  | 36105 |  | 10.67 | 361 | 15/07/2014 | Mir Akhtar Hossain Ltd | 15/07/2016 | 2018 | CRDP/LGED/Savar/ ICB/2013/ W-03 | 10 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road side Drain & Cross Culverts (Ch. 0.00 - 5770m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/ W-04 |  |  | 36105 |  | 10.67 | 361 | 15/07/2014 | Mir Akhtar Hossain Ltd | 15/07/2017 | 2018 | CRDP/LGED/Savar/ ICB/2013/ W-04 |  | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Re-construction of Road (Nabinagar - Kaliakoir RHD at Sreepur - Kashimpur GC Road (Ch. 0- 1500m) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-02 |  |  | 36105 |  | 18.53 | 361 | 15/07/2015 | Mir Akhtar Hossain Ltd | 15/07/2018 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-02 | 5 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Kuturia - Bogabari Bazar Road (Ch.0- 4570m) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-03 |  |  | 36105 |  | 18.53 | 361 | 15/07/2015 | Mir Akhtar Hossain Ltd | 15/07/2019 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-03 |  | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Jamgora Bazzar - Chitrachali -Kandail-Katgora Bazzar Road (Ch.0 --3615) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-04 |  |  | 36105 |  | 18.53 | 361 | 15/07/2015 | Mir Akhtar Hossain Ltd | 15/07/2020 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-04 | 35 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Jamgora Chowrasha Bhadail via Bhadail Primary School Road (Ch.0+000 - 2420, link 0+000 - 0+067) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-05 |  |  | 36105 |  | 18.53 | 361 | 15/07/2015 | Mir Akhtar Hossain Ltd | 15/07/2021 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-05 |  | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Bhadail Chowrasta Madar Textile via Anobic Shakti Commission road. (Ch.0+00-1+280m) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-06 |  |  | 36105 |  | 18.53 | 361 | 15/07/2016 | Mir Akhtar Hossain Ltd | 15/07/2022 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-06 | 44 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Nabinagor-Kaliakoir RHD road-Tongi EPZ road via Birds Garments & Gajirchat Aliya Madrasha. (ch.0+350-1+620m) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-07 |  |  | 36105 |  | 18.53 | 361 | 15/07/2016 | Mir Akhtar Hossain Ltd | 15/07/2023 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-07 | 50 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Kumkumary-Sadhupara road. (ch.0+00-2+300m) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-08 |  |  | 36105 |  | 18.53 | 361 | 15/07/2016 | Mir Akhtar Hossain Ltd | 15/07/2024 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-08 | 50 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhalpur-Katgora road. (ch.0+00-1+525m) |  | 26 | CRDP/LGED/ DHK/ NCB/2013/ W-09 |  |  | 36105 |  | 18.53 | 361 | 15/07/2016 | Mir Akhtar Hossain Ltd | 15/07/2025 | 2018 | CRDP/LGED/ DHK/ NCB/2013/ W-09 | 78 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka - Aricha Highway Ashulia GC Road (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/W-01 |  |  | 36105 |  | 17.53 | 361 | 15/07/2017 | Mir Akhtar Hossain Ltd | 15/07/2026 | 2018 | CRDP/LGED/Savar/ ICB/2013/W-01 | 0 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka - Aricha Highway Ashulia GC Road side Drain and Cross Culverts (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/W-02 |  |  | 36105 |  | 17.48 | 361 | 15/07/2017 | Mir Akhtar Hossain Ltd | 15/07/2027 | 2018 | CRDP/LGED/Savar/ ICB/2013/W-02 |  | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road (Ch. 0.00 - 5770m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/W-03 |  |  | 36105 |  | 17.53 | 361 | 15/07/2017 | Mir Akhtar Hossain Ltd | 15/07/2028 | 2018 | CRDP/LGED/Savar/ ICB/2013/W-03 | 100 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road side Drain & Cross Culverts (Ch. 0.00 - 5770m) |  | 26 | CRDP/LGED/Savar/ ICB/2013/W-04 |  |  | 36105 |  | 17.53 | 361 | 15/07/2017 | Mir Akhtar Hossain Ltd | 15/07/2029 | 2018 | CRDP/LGED/Savar/ ICB/2013/W-04 | 100 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Re-construction of Road (Nabinagar - Kaliakoir RHD at Sreepur - Kashimpur GC Road (Ch. 0- 1500m) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-02 |  |  | 36105 |  | 18.53 | 361 | 15/07/2018 | Project Builders Ltd. (PBL) | 15/07/2030 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-02 | 20 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Kuturia - Bogabari Bazar Road (Ch.0- 4570m) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-03 |  |  | 36105 |  | 18.53 | 361 | 15/07/2018 | Project Builders Ltd. (PBL) | 15/07/2031 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-03 | 5 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Jamgora Bazzar - Chitrachali -Kandail-Katgora Bazzar Road (Ch.0 --3615) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-04 |  |  | 36105 |  | 18.53 | 361 | 15/07/2018 | Project Builders Ltd. (PBL) | 15/07/2032 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-04 |  | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Jamgora Chowrasha Bhadail via Bhadail Primary School Road (Ch.0+000 - 2420, link 0+000 - 0+067) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-05 |  |  | 36105 |  | 18.53 | 361 | 15/07/2018 | Project Builders Ltd. (PBL) | 15/07/2033 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-05 | 40 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Bhadail Chowrasta Madar Textile via Anobic Shakti Commission road. (Ch.0+00-1+280m) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-06 |  |  | 36105 |  | 18.53 | 361 | 15/07/2019 | Project Builders Ltd. (PBL) | 15/07/2034 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-06 |  | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Nabinagor-Kaliakoir RHD road-Tongi EPZ road via Birds Garments & Gajirchat Aliya Madrasha. (ch.0+350-1+620m) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-07 |  |  | 36105 |  | 18.53 | 361 | 15/07/2019 | Project Builders Ltd. (PBL) | 15/07/2035 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-07 | 100 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Kumkumary-Sadhupara road. (ch.0+00-2+300m) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-08 |  |  | 36105 |  | 18.53 | 361 | 15/07/2019 | Project Builders Ltd. (PBL) | 15/07/2036 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-08 | 74 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Dhalpur-Katgora road. (ch.0+00-1+525m) |  | 26 | CRDP/LGED/Savar/ NCB/2013/W-09 |  |  | 36105 |  | 18.53 | 361 | 15/07/2019 | Project Builders Ltd. (PBL) | 15/07/2037 | 2018 | CRDP/LGED/Savar/ NCB/2013/W-09 | 45 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Improvement of Road and Drain in Ashulia, Savar |  | 26 | CRDP/LGED/DHK/ ICB/2013/W-01 |  |  | 36105 |  | 17.73 | 361 | 15/07/2020 | Mir Akhtar Hossain Ltd | 26/09/2013 | 2018 | CRDP/LGED/DHK/ ICB/2013/W-01 | 12 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Improvement of Road and Drain in Ashulia, Savar |  | 26 | CRDP/LGED/DHK/ NCB/2013/W-02 |  |  | 36105 |  | 17.26 | 361 | 15/07/2020 | Project Builders Ltd. (PBL) | 26/02/2015 | 2018 | CRDP/LGED/DHK/ NCB/2013/W-02 | 48 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Impprovement of Road and Drain in Savar Pourashava |  | 26 | CRDP/LGED/ Savar/NCB/2014/ W-01 |  |  | 36105 |  | 10.74 | 361 | 15/07/2020 | M/S. Md. Jamil Iqbal | 22/03/2015 | 2018 | CRDP/LGED/ Savar/NCB/2014/ W-01 | 85 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Impprovement of Road and Drain in Savar Pourashava |  | 26 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-01 |  |  | 36105 |  | 6.73 | 361 | 15/07/2020 | TI-SB (Jv) | 29/03/2015 | 2018 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-01 | 30 | 0
26 |  |  | City Region Development Project (1st revised) | CRDP | Impprovement of Road and Drain in Savar Pourashava |  | 26 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-2 |  |  | 36105 |  | 6.69 | 361 | 15/07/2021 | M/S Jemin Corporation | 20/09/2011 | 2018 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-2 | 15 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Fulbaria Bazar to Harannagar Bridge road (Ch. 00-1210m) Tetuljhora UP under Savar Upazila, District-Dhaka. (Estimate No. 209/10-11) ID No. 326723019 |  | 27 | IRIDP/Dhk/W-90 |  |  | 36105 |  | 1.21 | 361 | 15/07/2021 | M/S. Polas Construction | 20/09/2012 | 2018 | IRIDP/Dhk/W-90 | 2 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Hemayetpur Bus Stand-Joynabare Beparepara Bazar (Ch. 00-1440m) under Savar Upazila, District-Dhaka. ID No. 326724101 |  | 27 | IRIDP-DHK/W-151 |  |  | 36105 |  | 1.44 | 361 | 15/07/2021 | M/S. Sumon Enterprise | 21/07/2013 | 2018 | IRIDP-DHK/W-151 | 98 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Alipur Bridge-Firingikanda road by BC Ch. 00-1200m under Savar, District-Dhaka. (Estimate No. 51/11-12) |  | 27 | IRIDP/Dhk/SW-116 |  |  | 36105 |  | 1.2 | 361 | 15/07/2021 | M/S. Jams Engineer's | 21/07/2014 | 2018 | IRIDP/Dhk/SW-116 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road & pipe drain on Swiss Tex Tile-Motin Bricks road (Ch. 00-700m) under Savar Upazila, District-Dhaka. (Estimate No. 86/11-12), ID No. 326724224 |  | 27 | IRIDP/Dhk/W-134 |  |  | 36105 |  | 0.7 | 361 | 15/07/2022 | M/S.Redowan Builders | 21/07/2015 | 2018 | IRIDP/Dhk/W-134 | 95 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Shampur Bazar-Horindhora Tenary more road (Ch. 00-475m) under Savar Upazila, District-Dhaka. ID No. 326724345 |  | 27 | IRIDP-DHK/W-221 |  |  | 36105 |  | 0.48 | 361 | 15/07/2022 | M/S. Chonchal Builder's | 21/07/2016 | 2018 | IRIDP-DHK/W-221 | 87 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Chapra to Chapra Kheyaghat road at Vakorta UP Ch. 00-355m road under Savar Upazila, District-Dhaka. (Estimate No. 21/10-11),IRIDP/Dhk/W-25 |  | 27 | IRIDP/Dhk/W-25 |  |  | 36105 |  | 0.36 | 361 | 15/07/2022 | Boxer Enterprise | 21/07/2017 | 2018 | IRIDP/Dhk/W-25 | 58 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvment of Kalmarchar-Shamlapur Hight School road Ch. 00-1200m under Vakurta UP, Savar, Dist-Dhaka. (Estimate No. 212/10-11), ID No. 326725232 |  | 27 | IRIDP/Dhk/W-94 |  |  | 36105 |  | 1.2 | 361 | 15/07/2022 | M/S. KhanTraders | 25/06/2012 | 2018 | IRIDP/Dhk/W-94 |  | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Anower Jong road (Narsari) to Helal Master's house road at ch. 00-870m) under Savar Upazila, District-Dhaka. (Estimate No.149/09-10), ID No. 326724264 |  | 27 | IRIDP/Dhk/W-1 |  |  | 36105 |  | 0.87 | 361 | 15/07/2023 | M/S. G. C Enterprise | 25/06/2013 | 2018 | IRIDP/Dhk/W-1 |  | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | ConstrucConstruction of Kondolbag Pukurpar to Sarker Market via Manikgonjpara & Gosbag (GPS) road at Ch. 1250-2550m under Savar Upazila, District-Dhaka. (Estimate No.152/09-10), ID No. 326724202 |  | 27 | IRIDP/Dhk/W-1 |  |  | 36105 |  | 1.35 | 361 | 15/07/2023 | M/S. Urmi Enterprise | 25/06/2014 | 2018 | IRIDP/Dhk/W-1 | 85 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of DEPZ-Vadial Chowrasta-Pobnarteck road (Ch.1000-1851m) under Savar Upazila, District-Dhaka. (Estimate No.153/09-10), ID No. 326724060 |  | 27 | IRIDP/Dhk/W-5 |  |  | 36105 |  | 0.85 | 361 | 15/07/2023 | M/S. Builders Aid | 25/06/2015 | 2018 | IRIDP/Dhk/W-5 |  | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Baron-Chitrashail-Manikgonj Para-Goshbag road (Ch.00-920m) under Savar Upazila, District-Dhaka. (Estimate No.154/09-10), ID No. 326724119 |  | 27 | IRIDP/Dhk/W-6 |  |  | 36105 |  | 0.92 | 361 | 15/07/2023 | M/S. Tahmina Traders | 25/06/2016 | 2018 | IRIDP/Dhk/W-6 | 79 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of Ali Azam Sarkar house-Nohingertek-Manikgaonjpara road (Norshinghapur-Nischintapur-Tayebpur road) road (Ch.750-1750m) under Savar Upazila, District-Dhaka. (Estimate No.157/09-10), ID No. 326724077 |  | 27 | IRIDP/Dhk/W-9 |  |  | 36105 |  | 1 | 361 | 15/07/2024 | M/S. Alam Traders | 25/06/2017 | 2018 | IRIDP/Dhk/W-9 | 86 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ashulia School & College to Tongi EPZ road via Bangobondu road at road under Savar Upazila, District-Dhaka. (Ch. 00-2060m) (Estimate No. 29/10-11) |  | 27 | IRIDP/Dhk/W-33 |  |  | 36105 |  | 2.06 | 361 | 15/07/2024 | M/S. Eva Enterprise | 25/06/2018 | 2018 | IRIDP/Dhk/W-33 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road under Savar Upazila, District-Dhaka. (Ch. 1234-1817m) (Estimate No. 30/10-11) |  | 27 | IRIDP/Dhk/W-34 |  |  | 36105 |  | 0.58 | 361 | 15/07/2024 | M/S. Hemany Enterprise | 25/06/2019 | 2018 | IRIDP/Dhk/W-34 | 5 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Yearpur-Yearpur High School road Ch. 00-300m under Savar Upazila, District-Dhaka. (Estimate No. 60/11-12), ID No. 326725234 |  | 27 | IRIDP/Dhk/W-124 |  |  | 36105 |  | 0.3 | 361 | 15/07/2024 | Alpona Construction | 25/06/2020 | 2018 | IRIDP/Dhk/W-124 |  | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ashulia UP Office-Ashulia Hazera Khatun Madrasha road (Ch. 410-560m) under Savar Upazila, District-Dhaka. ID No. 326725111 |  | 27 | IRIDP-DHK/W-172 |  |  | 36105 |  | 0.15 | 361 | 15/07/2025 | M/S. Zia Enterprise | 25/06/2021 | 2018 | IRIDP-DHK/W-172 | 0 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Polashbari Bazar-Bashbari via Gocharartek road (Ch. 650-1200m) under Savar Upazila,, District-Dhaka. (Estimate No. 75/11-12), ID No. 326724333 |  | 27 | IRIDP/Dhk/W-130 |  |  | 36105 |  | 0.55 | 361 | 15/07/2025 | M/S.Rima Tarders | 28/12/2011 | 2018 | IRIDP/Dhk/W-130 | 0 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Zamgora Chowrastha-Gazirchor High School road (Ch. 00-1010m) ID No. 326724153 |  | 27 | IRIDP-DHK/W-170 |  |  | 36105 |  | 1.63 | 361 | 15/07/2025 | M/S. Nazma Enterprise | 20/09/2010 | 2018 | IRIDP-DHK/W-170 | 1 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) |  | Maintenance of Gazirchot-Kandail road (Ch. 0-620m) under Savar Upazila, District-Dhaka. ID No. 326724235 |  | 27 | IRIDP-DHK/W-171 |  |  | 36105 |  | 1.63 | 361 | 15/07/2025 |  | 14/09/2010 | 2018 | IRIDP-DHK/W-171 | 5 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Dendabor (RHD) Madrasha-Polash Bari-Gocharateck road (Ch. 412-1785m) under Savar Upazila, District-Dhaka. ID No. 326724289 |  | 27 | IRIDP-DHK/W-177 |  |  | 36105 |  |  | 361 | 15/07/2026 |  | 16/07/2013 | 2018 | IRIDP-DHK/W-177 | 12 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement road from Gonokbari (Pacca road)-DEPZ road (ch. 00-498m) & Construction of 1x4.00x4.00m RCC Box Culvert (Ch. 455m) under Savar Upazila, District-Dhaka. (Estimate No. 04/11-12), ID No. 326724235 |  | 27 | IRIDP/Dhk/SW-108 |  |  | 36105 |  | 1.37 | 361 | 15/07/2026 | M/S. Dewan Enterprise | 16/07/2014 | 2018 | IRIDP/Dhk/SW-108 | 55 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Ashulia Polli Biddut to Office-Ashulia High School road (Ch. 00-400m) under Savar Upazila, District-Dhaka. ID No. 326725253 |  | 27 | IRIDP-DHK/W-167 |  |  | 36105 |  | 0.5 | 361 | 15/07/2026 | M/S. Dewan Enterprise | 16/07/2015 | 2018 | IRIDP-DHK/W-167 | 96 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of C&B Ashulia road's Mozid Market-Roton Member;s house-Hikmot Alis house Dinestry Soweater's Ltd. (Akupara-Bongabandu road via Belma) under Savar Upazila, District-Dhaka. (Ch. 00-1500m) ID No. 326724175 (Estimate No. 205/10-11) |  | 27 | IRIDP/Dhk/SW-85 |  |  | 36105 |  | 0.4 | 361 | 15/07/2026 | M/S. Dewan Enterprise | 16/07/2016 | 2018 | IRIDP/Dhk/SW-85 | 65 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from H/O Salek Mohajon at Konda-H/O Javed Ali (Ch. 00-1200m) under Bongaon UP under Savar Upazila, District-Dhaka. (Estimate No. 119/2010-11) |  | 27 | IRIDP/Dhk/W-59 |  |  | 36105 |  | 1.5 | 361 | 15/07/2027 | M/S. Dewan Enterprise | 16/07/2017 | 2018 | IRIDP/Dhk/W-59 | 36 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of Ashulia UP-Dolpur via Baro Rangamatia-Katgora road (Ch. 6260-7260m under Savar Upazila, District-Dhaka. (Estimate No.155/09-10), ID No. 3267223010 |  | 27 | IRIDP/Dhk/W-7 |  |  | 36105 |  | 1.2 | 361 | 15/07/2027 | M/S. Dewan Enterprise | 16/07/2018 | 2018 | IRIDP/Dhk/W-7 |  | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Sreepur-Kashimpur road Hasan Member house-Hazi Rashid Shaheb house road (Ch. 00-575m) under Savar Upazila, District-Dhaka. (Estimate No.156/09-10), ID No. 326725112 |  | 27 | IRIDP/Dhk/W-8 |  |  | 36105 |  | 1 | 361 | 15/07/2027 | M/S. Dewan Enterprise | 16/07/2019 | 2018 | IRIDP/Dhk/W-8 | 70 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Yearpur H/O Jamat Ali-Lalpahar Buripara road Ch. 00-900m under Savar Upazila, District-Dhaka. (Estimate No. 59/11-12), ID No. 326724334 |  | 27 | IRIDP/Dhk/W-123 |  |  | 36105 |  | 0.58 | 361 | 15/07/2027 | M/S. Dewan Enterprise | 16/07/2020 | 2018 | IRIDP/Dhk/W-123 | 45 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Kandail Eidgah-Etakhola via Ghoshbag Rotary Girl's School road (Ghoshbag Rotary Girls School-Dewan filling Station) (Ch. 00-1240m) under Savar Upazila, District-Dhaka. ID No. 326724072 |  | 27 | IRIDP-DHK/W-164 |  |  | 36105 |  | 0.9 | 361 | 15/07/2028 | M/S. Dewan Enterprise | 16/07/2021 | 2018 | IRIDP-DHK/W-164 | 48 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Kohinor Mill to Pathalia-Rohimpur road (Ch. 400-1650m) under Savar Upazila, District-Dhaka. ID No. 326724115 |  | 27 | IRIDP-DHK/W-174 |  |  | 36105 |  | 1.24 | 361 | 15/07/2028 | M/S. Dewan Enterprise | 16/07/2022 | 2018 | IRIDP-DHK/W-174 | 23 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Savar GC-CRP-Lalteck-Savar UP road (Ch.400-1650m) under Savar Upazila, District-Dhaka. ID No. 326723027 |  | 27 | IRIDP-DHK/W-175 |  |  | 36105 |  | 1.25 | 361 | 15/07/2028 | M/S. Dewan Enterprise | 16/07/2023 | 2018 | IRIDP-DHK/W-175 | 97 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of Polashbari-Kaichabari-Bashbari road (Ch. 1.500-2.500Km) under Savar Upazila, District-Dhaka. ID No. 326724096 (Estimate No. 202/10-11) |  | 27 | IRIDP/Dhk/W-86 |  |  | 36105 |  | 1.25 | 361 | 15/07/2028 | M/S. Dewan Enterprise | 16/07/2024 | 2018 | IRIDP/Dhk/W-86 | 98 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Kaliakoir Kamlapur road Krishibid West Vew main Gate-Bagne Bare road (Ch. 00-750m) under Savar Upazila, District-Dhaka. (Estimate No. 84/11-12), ID No. 326725251 |  | 27 | IRIDP/DHK/W-132 |  |  | 36105 |  | 1 | 361 | 15/07/2029 | M/S. Dewan Enterprise | 16/07/2025 | 2018 | IRIDP/DHK/W-132 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Choto Kaliakoir Pucca road-Komlapur road (Ch. 00-520m) under Savar Upazila, District-Dhaka. ID No. 326724350 |  | 27 | IRIDP-DHK/W-168 |  |  | 36105 |  | 0.75 | 361 | 15/07/2029 | M/S. Dewan Enterprise | 16/07/2026 | 2018 | IRIDP-DHK/W-168 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Polashbari- Kaichabari-Bashbari road (Ch. 2500-3500m) & Link road & Ch.00-300m) |  | 27 | IRIDP-DHK/W-165 |  |  | 36105 |  | 0.52 | 361 | 15/07/2029 | M/S. Dewan Enterprise | 16/07/2027 | 2018 | IRIDP-DHK/W-165 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) |  | Same road 2715m, 2757m, 2788m & 3253m Ch. 0.600x0.600m 4 Drain Culvert under Savar Upazila, District-Dhaka. ID No. 326724096 |  | 27 | IRIDP-DHK/W-166 |  |  | 36105 |  | 1 | 361 | 15/07/2029 | M/S. Dewan Enterprise | 16/07/2028 | 2018 | IRIDP-DHK/W-166 | 48 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Gerua Bazar-Jamshing Bazar a road (Ch. 00-672m) under Savar Upazila, District-Dhaka. ID No. 326724190 |  |  | IRIDP-DHK/W-173 |  |  | 36105 |  | 0.67 | 361 | 15/07/2030 | M/S. Dewan Enterprise | 16/07/2029 | 2018 | IRIDP-DHK/W-173 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) |  | Construction of 4.50x3.50m RCC Box culvert road on Dhakhin Gazirchot Sher Ali Market-Bottola (Ch. 630m) road under Savar Upazila, District-Dhaka. (Estimate No.151/ |  | 27 | IRIDP/Dhk/W-3 |  |  | 36105 |  | 0.75 | 361 | 15/07/2030 | M/S. Dewan Enterprise | 16/07/2030 | 2018 | IRIDP/Dhk/W-3 | 98 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Construction of 90.00m RCC Girder Bridge over Kasoir Khal on Nutun Bondor Shimulia UP Office-Kasoir-Bagabari road at Ch. 0+610m under Savar Upazila, District-Dhaka.(Estimate No. 188/10-11) ID No. 326724204 |  | 27 | IRIDP/Dhk/W-82 |  |  | 36105 |  |  | 361 | 15/07/2030 | M/S. Dewan Enterprise | 16/07/2031 | 2018 | IRIDP/Dhk/W-82 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ambagan-Islamnagar-Bottola-Gerua Bazar road (Ch. 00-972m) under Savar Upazila, District-Dhaka. (Estimate No. 85/11-12), ID No. 326724192 |  | 27 | IRIDP/DHK/W-133 |  |  | 36105 |  | 0.97 | 361 | 15/07/2030 | M/S. Dewan Enterprise | 16/07/2032 | 2018 | IRIDP/DHK/W-133 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Nickrail-Chandpur-Vobanipur road (Ch. 00-1500m) |  | 27 | IRIDP-DHK/W-171 |  |  | 36105 |  | 1.5 | 361 | 15/07/2031 | M/S. Dewan Enterprise | 16/07/2033 | 2018 | IRIDP-DHK/W-171 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) |  | Same road 1100m Ch. 0.600x0.600m 1 Drain Culvert under Savar Upazila, District-Dhaka. ID No. 326724153 |  | 27 | IRIDP-DHK/W-172 |  |  | 36105 |  | 1.5 | 361 | 15/07/2031 | M/S. Dewan Enterprise | 16/07/2034 | 2018 | IRIDP-DHK/W-172 | 70 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ashulia UP Office to Hajerakhatun Madrasha road at Ch. 00-410m under Savar Upazila, District-Dhaka. (Estimate No.150/09-10), ID No. 326725111 |  | 27 | IRIDP/Dhk/W-2 |  |  | 36105 |  | 0.45 | 361 | 15/07/2031 | M/S. Dewan Enterprise | 16/07/2035 | 2018 | IRIDP/Dhk/W-2 | 75 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Chakulia Pucca road (Gosh Bag) to Chakulia Deep Tubewell road (Ch. 00-500m) under Savar Upazila, District-Dhaka. ID No. 326724349 |  | 27 | IRIDP-DHK/W-169 |  |  | 36105 |  | 0.5 | 361 | 15/07/2031 | M/S. Dewan Enterprise | 16/07/2036 | 2018 | IRIDP-DHK/W-169 | 65 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Jamgora Simultoli-Sayed Masterbari-Jamgora Primary School road (Ch. 00-1000m) under Savar Upazila, District-Dhaka. ID No. 326725025 |  | 27 | IRIDP-DHK/W-166 |  |  | 36105 |  | 1 | 361 | 15/07/2032 | M/S. Dewan Enterprise | 16/07/2037 | 2018 | IRIDP-DHK/W-166 | 55 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Toyebpur (Zirabo) Dewan Idrish College-Safina Poultry Firm Culvert Approach-Tayebpur Jame Mosque road) (Ch. 00-455m) under Savar Upazila, District-Dhaka. ID No. 326724247 |  | 27 | IRIDP-DHK/W-176 |  |  | 36105 |  | 0.46 | 361 | 15/07/2032 | M/S. Dewan Enterprise | 16/07/2038 | 2018 | IRIDP-DHK/W-176 | 90 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Shampur Bazar-Horindhora Tenary more road (Ch. 00-475m) under Savar Upazila, District-Dhaka. ID No. 326724345 |  | 27 | IRIDP-DHK/SW-221 |  |  | 36105 |  | 0.48 | 361 | 15/07/2032 | M/S. Dewan Enterprise | 16/07/2039 | 2018 | IRIDP-DHK/SW-221 | 85065 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Alipur Bridge-Firingikanda road by BC Ch. 450-700m under Savar, District-Dhaka. (Estimate No. 51/11-12) ID No.326724272 |  | 27 | IRIDP/Dhk/W-116 |  |  | 36105 |  | 1.2 | 361 | 15/07/2032 | M/S. Dewan Enterprise | 16/07/2040 | 2018 | IRIDP/Dhk/W-116 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road & pipe drain on Swiss Tex Tile-Motin Bricks road (Ch. 450-700m) under Savar Upazila, District-Dhaka. (Estimate No. 86/11-12), ID No. 326724224 |  | 27 | IRIDP/Dhk/SW-134 |  |  | 36105 |  | 0.25 | 361 | 15/07/2033 | M/S. Dewan Enterprise | 16/07/2041 | 2018 | IRIDP/Dhk/SW-134 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvment of Kalmarchar-Shamlapur Hight School road Ch. 00-1200m under Vakurta UP, Savar, Dist-Dhaka. (Estimate No. 212/10-11), ID No. 326725232 |  | 27 | IRIDP/Dhk/SW-94 |  |  | 36105 |  | 1.2 | 361 | 15/07/2033 | M/S. Dewan Enterprise | 16/07/2042 | 2018 | IRIDP/Dhk/SW-94 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Road from Hemayetpur Suwitch Textile to Motin Brick Field (Ch:00-445m) Road Code:326724224. |  | 27 | IRIDP/DHK/DW-241 |  |  | 36105 |  | 1.2 | 361 | 15/07/2033 | M/S. Dewan Enterprise | 16/07/2043 | 2018 | IRIDP/DHK/DW-241 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) |  | Improvement of Road from Apurupa Textile Miles to Bagbari Via Kuddus Ali House. (CH:00-253.00m) Road Code:326725265 |  | 27 | IRIDP/DHK/DW-242 |  |  | 36105 |  | 0.25 | 361 | 15/07/2033 | M/S. Dewan Enterprise | 16/07/2044 | 2018 | IRIDP/DHK/DW-242 | 100 | 0
27 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Bangabandhu Road to Katgora Bazar via Aragaon Road (Ch. 00-1110 m) under Savar Upazila, District-Dhaka. (Road ID No: 326724037) |  | 27 | IRIDP/DHK/DW-23 |  |  | 36105 |  | 1.11 | 361 | 15/07/2034 | M/S. Dewan Enterprise | 16/07/2045 | 2018 | IRIDP/DHK/DW-23 | 100 | 0
28 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IARP | Approach road at Beraid HZ. Abul Khalek house to School (Ch. 00-345m) |  | 28 | IARP/DHK-08 |  |  | 36105 |  |  | 361 | 15/07/2034 | M/S. Dewan Enterprise | 16/07/2046 | 2018 | IARP/DHK-08 | 0 | 0
28 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) |  | Toibpur Dewan Iddrish College to Shafina Poultry Firm Culvert approach (Ch. 0-455m) under Savar Upazila, District-Dhaka. (Estimate No. 46/11-12) |  | 28 | IARP/DHK-09 |  |  |  |  | 0.69 |  | 15/07/2034 | M/S. Dewan Enterprise | 16/07/2047 |  | IARP/DHK-09 | 0 | 0
29 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | improvement of Zirani-Shimulia Analbari-Nallapolla road Ch. 00-690m under Savar Upazila, District-Dhaka. (Estimate No. 22/11-12), ID No. 32672114 |  | 29 | GDP-II/Dha/Sav/W(R)-05 |  |  | 36105 |  | 0.65 | 361 | 15/07/2034 | M/S. Dewan Enterprise | 16/07/2048 | 2018 | GDP-II/Dha/Sav/W(R)-05 | 0 | 0
29 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of Rajfulbaria Bus Stand-Rishipara via Fulbaria Bazar Road Ch. 00m- 650 m (ID No. 3267623005) under Saver Upazila Dist: Dhaka. |  | 29 | GDP-II/Dha/sav/W(R)-11 |  |  | 36105 |  | 1.14 | 361 | 15/07/2035 | M/S. Dewan Enterprise | 16/07/2049 | 2018 | GDP-II/Dha/sav/W(R)-11 | 0 | 0
29 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of Aragaon Primary School-Doshaid School road Ch. 1400-2535m (ID No. -326724037) under Savar Upazila, District-Dhaka. (Estimate No. 53/11-12) |  | 29 | GDP-II/DHA/Sav/W(R)-13 |  |  | 36105 |  | 1.14 | 361 | 15/07/2035 | M/S. Dewan Enterprise | 16/07/2050 | 2018 | GDP-II/DHA/Sav/W(R)-13 | 0 | 0
29 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of road from Gerua Bazar to Physics Department via Moulana Bhasani Hall & Bangabandhu Sheikh Mujibur Rahman Hall of Jahangir Nagar University Ch. 00-1020m (ID No. 326724003) |  | 29 | GDP-II/DHA/Sav/W(R)-15 |  |  | 36105 |  |  | 361 | 15/07/2035 | M/S. Dewan Enterprise | 16/07/2051 | 2018 | GDP-II/DHA/Sav/W(R)-15 | 45 | 0
|  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts |  | Improvement of Baroipara (Pacca road)-Olosara road Ch. 00-65m |  | 29 | GDP-II/DHA/Sav/W(R)-16 |  |  | 36105 |  |  | 361 | 15/07/2035 | M/S. Dewan Enterprise | 16/07/2052 | 2018 | GDP-II/DHA/Sav/W(R)-16 | 74 | 0
30 |  |  | RIIP-2 | RIIP-2 | Improvement of Aricha Boliapur Bongaon UP (Konda Bazar)-Chakulia Bazar road, (Ch. 0+000Km to 4+881 Km), Upazila: Savar. |  | 30 | W-DHAK-Savar-UNR-08-05 |  |  | 36105 |  | 4.88 | 361 | 15/07/2036 | M/S. Dewan Enterprise | 16/07/2053 | 2018 | W-DHAK-Savar-UNR-08-05 | 15 | 0
30 |  |  | RIIP-2 | RIIP-2 | Improvement of Dhaka Aricha RHD at 22 Mile-Shimulia Road via nalam (ch. 2915-6000m) upazila Savar, Dist.- Dhaka |  | 30 | W-DHAK-Savar-UZR-09-77(a) |  |  | 36105 |  | 3.09 | 361 | 15/07/2036 | M/S. Dewan Enterprise | 16/07/2054 | 2018 | W-DHAK-Savar-UZR-09-77(a) | 20 | 0
30 |  |  | RIIP-2 | RIIP-2 | Improvement of Dhaka Aricha RHD at 22 Mile-Shimulia Road via nalam (ch. 6000-7658m)connect vararia UPC(ch.00-1003m) upazila Savar, Dist.- Dhaka |  | 30 | W-DHAK-Savar-UZR-09-77(b) |  |  | 36105 |  | 2.69 | 361 | 15/07/2036 | M/S. Dewan Enterprise | 16/07/2055 | 2018 | W-DHAK-Savar-UZR-09-77(b) | 45 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | sandip com. primary school School Reconstruction |  | 31 | PEDP-III/DHK/SAV/2011-12/W1.0072 |  |  | 36105 |  |  | 361 | 15/07/2036 | M/S. Dewan Enterprise | 16/07/2056 | 2018 | PEDP-III/DHK/SAV/2011-12/W1.0072 | 50 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | GAZIR CHAT School Additional Room |  | 31 | PEDP-III/DHK/SAV/2012-13/W2.2128 |  |  | 36105 |  |  | 361 | 15/07/2037 | M/S. Dewan Enterprise | 16/07/2057 | 2018 | PEDP-III/DHK/SAV/2012-13/W2.2128 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | PARAGRAM School Additional Room |  | 31 | PEDP-III/DHK/SAV/2011-12/W2.0062 |  |  | 36105 |  |  | 361 | 15/07/2037 | M/S. Dewan Enterprise | 16/07/2058 | 2018 | PEDP-III/DHK/SAV/2011-12/W2.0062 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | NUTAN BANDAR School Additional Room |  | 31 | PEDP-III/DHK/SAV/2011-12/W2.0538 |  |  | 36105 |  |  | 361 | 15/07/2037 | M/S. Dewan Enterprise | 16/07/2059 | 2018 | PEDP-III/DHK/SAV/2011-12/W2.0538 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | TETUL JHORA School Additional Room |  | 31 | PEDP-III/DHK/SAV/2011-12/W2.0538 |  |  | 36105 |  |  | 361 | 15/07/2037 | M/S. Dewan Enterprise | 16/07/2060 | 2018 | PEDP-III/DHK/SAV/2011-12/W2.0538 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | SAIPARA School Additional Room |  | 31 | PEDP-III/DHK/SAV/2011-12/W2.1398 |  |  | 36105 |  |  | 361 | 15/07/2038 | M/S. Dewan Enterprise | 16/07/2061 | 2018 | PEDP-III/DHK/SAV/2011-12/W2.1398 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | GOMAIL School Additional Room |  | 31 | PEDP-III/DHK/SAV/2011-12/W2.0540 |  |  | 36105 |  |  | 361 | 15/07/2038 | M/S. Dewan Enterprise | 16/07/2062 | 2018 | PEDP-III/DHK/SAV/2011-12/W2.0540 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | BARADESHI School Additional Room |  | 31 | PEDP-III/DHK/2012-13/W2.1842 |  |  | 36105 |  |  | 361 | 15/07/2038 | M/S. Dewan Enterprise | 16/07/2063 | 2018 | PEDP-III/DHK/2012-13/W2.1842 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | CHAKAL GRAM School Additional Room |  | 31 | PEDP-III/DHK/SAV/2012-13/W2.1921 |  |  | 36105 |  |  | 361 | 15/07/2038 | M/S. Nazma Enterprise | 16/07/2064 | 2018 | PEDP-III/DHK/SAV/2012-13/W2.1921 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | kabirpur reg. primary school School Additional Room |  | 31 | PEDP-III/DHK/SAV/2013-14/W2.2839 |  |  | 36105 |  |  | 361 | 15/07/2039 | M/S. Nazma Enterprise | 16/07/2065 | 2018 | PEDP-III/DHK/SAV/2013-14/W2.2839 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | kabirpur reg. primary school School Additional Room |  | 31 | PEDP-III/DHK/SAV/2013-14/W3.0400 |  |  | 36105 |  |  | 361 | 15/07/2039 | M/S. Nazma Enterprise | 16/07/2066 | 2018 | PEDP-III/DHK/SAV/2013-14/W3.0400 | 100 | 0
31 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | KRINSHAPUR HASSIN School Major Maintenance |  | 31 | PEDP-III/DHK/SAV/2011-12/W3.0325 |  |  | 36105 |  |  | 361 | 15/07/2039 | M/S. Nazma Enterprise | 16/07/2067 | 2018 | PEDP-III/DHK/SAV/2011-12/W3.0325 | 100 | 0
31 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Savar UP (Dhaka-Aricha RHDD) Genda-Sadapur Bangoan road (Ch. 7315-7830m) under Savar Upazila, District-Dhaka. (Estimate No. 149/08-09), Package No. UNR-GDP-W-07/08-10 |  | 31 | GDP-D-18 |  |  | 36105 |  | 0.52 | 361 | 15/07/2039 | M/S. Nazma Enterprise | 16/07/2068 | 2018 | GDP-D-18 | 100 | 0
31 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Sreepur-Gohailbari via Shobondi & Dhamsona UP road (Ch. 5224-6570m) under Savar Upazial, District-Dhaka. (Estimate No. 150/08-09), Package No. UNR-GDP-W-08/08-0 |  | 31 | GDP-D-19 |  |  | 36105 |  | 1.35 | 361 | 15/07/2040 | M/S. Nazma Enterprise | 16/07/2069 | 2018 | GDP-D-19 | 100 | 0
31 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Baipail BKSP Training Academy link road (Ch. 00-344m).under Savar Upazila, District-Dhaka.Package No.UNR-GDP-W-20/08-09 |  | 31 | GDP-D-19 |  |  | 36105 |  | 0.34 | 361 | 15/07/2040 | M/S. Nazma Enterprise | 16/07/2070 | 2018 | GDP-D-19 | 100 | 0
31 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Hatubhanga road to Pathalia Housing Society road (Ch. 500-750m).under Savar Upazila, District-Dhaka. Package No. UNR-GDP-W-08/08-09 |  | 31 | GDP-D-28 |  |  | 36105 |  | 0.25 | 361 | 15/07/2040 | M/S. Nazma Enterprise | 16/07/2071 | 2018 | GDP-D-28 | 100 | 0
31 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Boroipara RHD-Polly Biddut road (Ch. 981-1620m).under Savar Upazila, District-Dhaka.(Estimate No. 19/09-10) Package No. UNR-GDP-W-05/09-10 |  | 31 | GDP-D-33 |  |  | 36105 |  | 0.64 | 361 | 15/07/2040 | M/S. Nazma Enterprise | 16/07/2072 | 2018 | GDP-D-33 | 100 | 0
31 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch. 00-826m).under Savar Upazila, District-Dhaka.(Estimate No. 21/09-10), Package No. UNR-GDP-W-07/09-10 |  | 31 | GDP-D-37 |  |  | 36105 |  | 0.83 | 361 | 15/07/2041 | M/S. Nazma Enterprise | 16/07/2073 | 2018 | GDP-D-37 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch. 825-1565m).under Savar Upazila, District-Dhaka.(Estimate No. 22/09-10), Package No. UNR-GDP-W-09/09-10 |  | 32 | GDP-D-38 |  |  | 36105 |  | 0.74 | 361 | 15/07/2041 | M/S. Nazma Enterprise | 16/07/2074 | 2018 | GDP-D-38 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch.1565-2219m).under Savar Upazila, District-Dhaka.(Estimate No. 23/09-10), Package No. UNR-GDP-W-10/09-10 |  | 32 | GDP-D-39 |  |  | 36105 |  | 0.65 | 361 | 15/07/2041 | M/S. Nazma Enterprise | 16/07/2075 | 2018 | GDP-D-39 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Durgapur-Porbochala ch. 00-570m, 00-175m |  | 32 | GDP-D-59 |  |  | 36105 |  | 0.75 | 361 | 15/07/2041 | M/S. Nazma Enterprise | 16/07/2076 | 2018 | GDP-D-59 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Dhaka-Aricha RHD to Genda Shadapur-Bongaon ch. 2100-3500m road. |  | 32 | GDP-D-05 |  |  | 36105 |  | 1.14 | 361 | 15/07/2042 | M/S. Suchana Enterprise | 16/07/2077 | 2018 | GDP-D-05 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Mugrakanda Vakurta road Baily Bridge to Turag Super Market (Dewan house connecting road) road under Savar Upazila, (Ch. 00-210m) District-Dhaka. |  | 32 | GDP-D-35 |  |  | 36105 |  | 0.21 | 361 | 15/07/2042 | M/S. Suchana Enterprise | 16/07/2078 | 2018 | GDP-D-35 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Tengori main road Shop of Rafiq-Tengori Mujibur & Ershad House road (Ch. 0-360m & 0-215m) |  | 32 | GDP-D-58 |  |  | 36105 |  | 1.17 | 361 | 15/07/2042 | M/S. Suchana Enterprise | 16/07/2079 | 2018 | GDP-D-58 | 100 | 0
|  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District |  | Madhaya Konapara main road (Ch. 0-490m & 107m) under Savar Upazila, District-Dhaka. (Estimate No.94/09-10) |  | 32 | GDP-D-59 |  |  | 36105 |  | 1.17 | 361 | 15/07/2042 | M/S. Suchana Enterprise | 16/07/2080 | 2018 | GDP-D-59 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Zirani-Shimulia road Samon Ali Colony Konapara Jame Mosque road (Ch. 522-1044m) under Savar Upazila, District-Dhaka. |  | 32 | GDP-D-62 |  |  | 36105 |  | 0.52 | 361 | 15/07/2043 | M/S. Suchana Enterprise | 16/07/2081 | 2018 | GDP-D-62 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kalasuti Sultan house-Madrasha via H/O Haji Based road ch. 00-802m |  | 32 | GDP-D-74 |  |  | 36105 |  | 0.8 | 361 | 15/07/2043 | M/S. Suchana Enterprise | 16/07/2082 | 2018 | GDP-D-74 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kaltasuti Edrish Chowkider house-Noapara house of Jamal road at Shimulia UP (Ch. 00-587m) |  | 32 | GDP-D-63 |  |  | 36105 |  | 0.59 | 361 | 15/07/2043 |  | 16/07/2083 | 2018 | GDP-D-63 | 100 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Tenguri Harun Factory to Kaltasuti Morichkata Shadhubari road (Ch. 00-545m) |  | 32 | GDP-D-64 |  |  | 36105 |  | 0.55 | 361 | 15/07/2043 | M/S. Sajal Enterprise | 16/07/2084 | 2018 | GDP-D-64 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Sreepur Busstand Subondi Trimohoni road (Ch. 1150-2712m). |  | 32 | GDP-D-91 |  |  | 36105 |  | 0.55 | 361 | 15/07/2044 | M/S. Sajal Enterprise | 16/07/2085 | 2018 | GDP-D-91 | 70 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Gonakpara Govt. Primary School Joynal Dealar House road (Ch. 00-322m). |  | 32 | GDP-D-83 |  |  | 36105 |  | 1.56 | 361 | 15/07/2044 | M/S. Sajal Enterprise | 16/07/2086 | 2018 | GDP-D-83 | 80 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Hemayetpur Oporupa Textiles Mill to Bugbari Connecting road (Ch. 00-253m). |  | 32 | GDP-D-85 |  |  | 36105 |  | 0.32 | 361 | 15/07/2044 | M/S. Sajal Enterprise | 16/07/2087 | 2018 | GDP-D-85 | 90 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Kaliakoir Nabinagaor road at Tengori Shop of Gias Uddin-Tengori Modina Colony road (Ch. 00-357m) |  | 32 | GDP-D-86 |  |  | 36105 |  | 0.25 | 361 | 15/07/2044 | M/S. Sajal Enterprise | 16/07/2088 | 2018 | GDP-D-86 | 75 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Purbo Katlasuti house of Zahirul Islam-House of Nazir Hossain road Ch. 00-250m |  | 32 | GDP-D-87 |  |  | 36105 |  | 0.25 | 361 | 15/07/2045 | M/S. Sajal Enterprise | 16/07/2089 | 2018 | GDP-D-87 | 68 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | House of Khaleque-House of Azgar Ali at Tengori Ch. 00-210m |  | 32 | GDP-D-87 |  |  | 36105 |  | 0.61 | 361 | 15/07/2045 | M/S. Sajal Enterprise | 16/07/2090 | 2018 | GDP-D-87 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | House of Belayet Hossain-house of Abu Taher at Tan Konapara road Ch. 00-150m |  | 32 | GDP-D-88 |  |  | 36105 |  | 0.61 | 361 | 15/07/2045 | M/S. Sajal Enterprise | 16/07/2091 | 2018 | GDP-D-88 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Paragram Rustompur road Deun-Moinuddin Shop to Hazirat Ali House Ch. 00-568m |  | 32 | GDP-D-76 |  |  | 36105 |  | 0.36 | 361 | 15/07/2045 | M/S. Sajal Enterprise | 16/07/2092 | 2018 | GDP-D-76 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Circular road of Savar Cantonment Savar, Dhaka. Ch. 00-10100m Dhaka.(Estimate No. 51/10-11) GDP-D-111 |  | 32 | GDP-D-111 |  |  | 36105 |  | 0.36 | 361 | 15/07/2046 | M/S. Sajal Enterprise | 16/07/2093 | 2018 | GDP-D-111 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road Ch. 1817-2328m under Savar Upazila, District-Dhaka. (Estimate No. 48/10-11 |  | 32 | GDP-D-100 |  |  | 36105 |  | 0.57 | 361 | 15/07/2046 | M/S. Sajal Enterprise | 16/07/2094 | 2018 | GDP-D-100 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Koltasuti Sabida Chala-Barol Kabarastan road Ch. 00-576m |  | 32 | GDP-D-104 |  |  | 36105 |  | 10.1 | 361 | 15/07/2046 | 40762 | 16/07/2095 | 2018 | GDP-D-104 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District |  | Improvement of Koltasuti Sabida Chala-Dhalivari road Ch. 00-342m |  | 32 | GDP-D-105 |  |  | 36105 |  | 10.1 | 361 | 15/07/2046 | M/S. Sajal Enterprise | 16/07/2096 | 2018 | GDP-D-105 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District |  | Improvement of Tengori-Konapara Baidgaon road Ch. 00-837m under Savar Upazila, District-Dhaka. (Estimate N |  | 32 | GDP-D-106 |  |  | 36105 |  | 10.1 | 361 | 15/07/2047 | M/S. Sajal Enterprise | 16/07/2097 | 2018 | GDP-D-106 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement road from Miar Rahman House-House of Sahufu at Kaltasuti (Road from House of Badsha-House of Halim at Kaltasuti (Ch. 00-145m & Ch. 00-145m) |  | 32 | GDP-D-105 |  |  | 36105 |  | 0.51 | 361 | 15/07/2047 | M/S. Sajal Enterprise | 16/07/2098 | 2018 | GDP-D-105 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District |  | Tengori Akali House-Tengori Mujibur House road (Ch. 00-340m) under Savar Upazila, District-Dhaka |  | 32 | GDP-D-106 |  |  | 36105 |  | 0.51 | 361 | 15/07/2047 |  | 16/07/2099 | 2018 | GDP-D-106 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kuturia-Bogabari Bazar road Ashulia UP road (Ch.00-1700m) under Savar Upazila, Dist-Dhaka. (Estimate No.66/10-11) |  | 32 | GDP-D-106 |  |  | 36105 |  | 1.18 | 361 | 15/07/2047 | M/S. M.R Construction | 16/07/2100 | 2018 | GDP-D-106 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Sreepur-Subondi road near shop of Kojon Miah to house of Azim Uddin Member at Subondi (Ch. 00-1064m) |  | 32 | GDP-D-116 |  |  | 36105 |  | 1.18 | 361 | 15/07/2048 | M/S. M.R Construction | 16/07/2101 | 2018 | GDP-D-116 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District |  | Construction of 0.60m Span U-Drain at (Ch. 52m & 160m) on same road under Savar Upazila, District-Dhaka. (Estim |  | 32 | GDP-D-117 |  |  | 36105 |  | 1.18 | 361 | 15/07/2048 | M/S. M.R Construction | 16/07/2102 | 2018 | GDP-D-117 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Purbo Kaltasuti Muslimteck (House of Surot Ali)-Mollarbag Mosque road (Ch. 00-1270m) |  | 32 | GDP-D-138 |  |  | 36105 |  | 1.27 | 361 | 15/07/2048 | M/S. M.R Construction | 16/07/2103 | 2018 | GDP-D-138 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Construction of 2.00m Span Box at (Ch. 692m) on the same road under Savar Upazila, District-Dhaka. (Estimate No. 122/10-11,Package No. UN |  | 32 | GDP-D-139 |  |  | 36105 |  |  | 361 | 15/07/2048 | M/S. M.R Construction | 16/07/2104 | 2019 | GDP-D-139 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Rostumpur Shadhupara Chowrastha-Kagan Paragram Connecting via Paragram Koborstan road (Ch. 00-976m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 124/10-11 |  | 32 | GDP-D-125 |  |  | 36105 |  | 1.27 | 361 | 15/07/2049 | M/S. M.R Construction | 16/07/2105 | 2020 | GDP-D-125 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Ronosthal-Myjhail-Pychail road (Ch. 00-1150m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 125/10-11 |  | 32 | GDP-D-126 |  |  |  |  | 0.98 |  | 15/07/2049 | M/S. M.R Construction | 16/07/2106 | 2021 | GDP-D-126 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kuturia Dewan Bari Mosque-Khatghora High School road (Ch. 00-1038m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 126/10-11 |  | 32 | GDP-D-127 |  |  |  |  | 1.15 |  | 15/07/2049 | M/S. M.R Construction | 16/07/2107 | 2022 | GDP-D-127 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Purbo Baidgaon (Pagla Bazar)-Purbo Baidgaon Govt. Primary School road (Ch.250-1000m) under Savar Upazila, Dist-Dhaka. (Estimate No.70/10-11) Package No. UNR-GDP-D-112 |  | 32 | GDP-D-112 |  |  |  |  | 1.04 |  | 15/07/2049 | M/S. M.R Construction | 16/07/2108 | 2023 | GDP-D-112 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Bariopara (RHD)-Polly Biddut road (Ch. 00-1134m) under Savar Upazila, Dist-Dhaka. (Estimate No.71/10-11) Package No. UNR-GDP-D-113 |  | 32 | GDP-D-113 |  |  |  |  | 0.75 |  | 15/07/2050 | M/S. M.R Construction | 16/07/2109 | 2024 | GDP-D-113 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Goalbari Machinepar Momin Bari-House of Ali (Ch.00-662m) under Savar Upazila, Dist-Dhaka. (Estimate No.72/10-11) Package No. UNR-GDP-D-114 |  | 32 | GDP-D-114 |  |  |  |  | 1.13 |  | 15/07/2050 | M/S. M.R Construction | 16/07/2110 | 2025 | GDP-D-114 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Kondalbag Pukur Par to Sarkar Market via Bhuiyan Bari Jame Mosque road (Ch. 2550-3050m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 127/10-11) ,Package No. UNR-GDP-D-141 |  | 32 | GDP-D-141 |  |  |  |  | 0.66 |  | 15/07/2050 | M/S. M.R Construction | 16/07/2111 | 2026 | GDP-D-141 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Nabinagar-Kaliakoair RHD (Savar Metal)-Sreepur Kaborsthan road (Ch. 00-962m) |  | 32 | GDP-D-142 |  |  |  |  | 0.5 |  | 15/07/2050 | M/S. M.R Construction | 16/07/2112 | 2027 | GDP-D-142 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District |  | Construction of 500mm Span U-Drain at Ch. 650m same road under Savar Upazila, District-Dhaka. (Estimate No. 147/10-11), Package No. UNR-GDP-D-142 |  | 32 | GDP-D-143 |  |  |  |  | 0.5 |  | 15/07/2051 | M/S. M.R Construction | 16/07/2113 | 2028 | GDP-D-143 | 60 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Nama Konapara Jalus House- Jolhash House Road . (Ch. 00-665m) |  | 32 | GDP-D-159 |  |  |  |  | 0.96 |  | 15/07/2051 | M/S. Miah Trader | 16/07/2114 | 2029 | GDP-D-159 | 50 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Road form of Satter Hazi (Pucca road) to House of Fazal at Purbo Kaltasuti Road (Ch. 00-350m), |  | 32 | GDP-D-161 |  |  |  |  | 0.67 |  | 15/07/2051 | M/S. Miah Trader | 16/07/2115 | 2030 | GDP-D-161 | 20 | 0
32 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Purbo Kaltasuti Anwar House (BKSP Wall) to House of Kohinoor Road (Ch. 00-180m) |  | 32 | GDP-D-162 |  |  |  |  | 0.35 |  | 15/07/2051 | M/S. Miah Trader | 16/07/2116 | 2031 | GDP-D-162 | 20 | 0