## Savar_Jalal
Project ID | Code Part 1 | Code Part 2 | Project Title | Project Name | SCHEMENAME_ENG | SCHEMENAME_BEN | PACKAGEID | Package No. | Schema_Type_id | Schema_Type_name | Upazila ID | Road ID | Length of Road (Km) | DISTRICTID | Date of Completion | Name of Contractor | Date of Contract | FINANCIALYEAR | SCHEMECODE | Physical Progress (%) | STATUS | Date of Commencement | Remarks | Lat-long
1 |  |  | City Region Development Project (1st revised) | CRDP | (a) Dhaka - Aricha Highway Ashulia GC Road (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) ; (b) Dhaka - Aricha Highway Ashulia GC Road side Drain and Cross Culverts (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m); (c) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road (Ch. 0.00 - 5770m); (d) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road side Drain & Cross Culverts (Ch. 0.00 - 5770m) |  | 3000 | CRDP/LGED/Savar/ ICB/2013/ W-01 | 1 | road | 36105 |  | 10.67 | 361 |  |  |  |  | CRDP/LGED/Savar/ ICB/2013/ W-01 | 0 | 0
1 |  |  | City Region Development Project (1st revised) | CRDP | (a) Re-construction of Road (Nabinagar - Kaliakoir RHD at Sreepur - Kashimpur GC Road (Ch. 0- 1500m); (b) Kuturia - Bogabari Bazar Road (Ch.0- 4570m); (c) Jamgora Bazzar - Chitrachali -Kandail-Katgora Bazzar Road (Ch.0 --3615); (d) Jamgora Chowrasha Bhadail via Bhadail Primary School Road (Ch.0+000 - 2420, link 0+000 - 0+067); (e) Bhadail Chowrasta Madar Textile via Anobic Shakti Commission road. (Ch.0+00-1+280m); (f) Nabinagor-Kaliakoir RHD road-Tongi EPZ road via Birds Garments & Gajirchat Aliya Madrasha. (ch.0+350-1+620m); (g) Kumkumary-Sadhupara road. (ch.0+00-2+300m); and (h) Dhalpur-Katgora road. (ch.0+00-1+525m) |  | 3001 | CRDP/LGED/ DHK/ NCB/2013/ W-02 | 1 | road | 36105 |  | 18.53 | 361 |  |  |  |  | CRDP/LGED/ DHK/ NCB/2013/ W-02 | 0 | 0
1 |  |  | City Region Development Project (1st revised) | CRDP | (a) Dhaka - Aricha Highway Ashulia GC Road (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) ; (b) Dhaka - Aricha Highway Ashulia GC Road side Drain and Cross Culverts (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m); (c) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road (Ch. 0.00 - 5770m); (d) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road side Drain & Cross Culverts (Ch. 0.00 - 5770m) |  | 3002 | CRDP/LGED/Savar/ ICB/2013/W-01 | 1 | road | 36105 |  |  | 361 | 2014-07-15 | Mir Akhtar Hossain Ltd. |  |  | CRDP/LGED/Savar/ ICB/2013/W-01 | 40 | 0
1 |  |  | City Region Development Project (1st revised) | CRDP | (a) Re-construction of Road (Nabinagar - Kaliakoir RHD at Sreepur - Kashimpur GC Road (Ch. 0- 1500m); (b) Kuturia - Bogabari Bazar Road (Ch.0- 4570m); (c) Jamgora Bazzar - Chitrachali -Kandail-Katgora Bazzar Road (Ch.0 --3615); (d) Jamgora Chowrasha Bhadail via Bhadail Primary School Road (Ch.0+000 - 2420, link 0+000 - 0+067); (e) Bhadail Chowrasta Madar Textile via Anobic Shakti Commission road. (Ch.0+00-1+280m); (f) Nabinagor-Kaliakoir RHD road-Tongi EPZ road via Birds Garments & Gajirchat Aliya Madrasha. (ch.0+350-1+620m); (g) Kumkumary-Sadhupara road. (ch.0+00-2+300m); and (h) Dhalpur-Katgora road. (ch.0+00-1+525m) |  | 3003 | CRDP/LGED/Savar/ NCB/2013/W-02 | 1 | road | 36105 |  | 18.53 | 361 | 2014-09-25 | Project Builders Ltd. (PBL) |  |  | CRDP/LGED/Savar/ NCB/2013/W-02 | 20 | 0
1 |  |  | City Region Development Project (1st revised) | CRDP | Improvement of Road and Drain in Ashulia, Savar |  | 3004 | CRDP/LGED/DHK/ ICB/2013/W-01 | 1 | road | 36105 |  | 17.73 | 361 | 2014-08-24 | Mir Akhtar Hossain Ltd. | 2013-07-16 |  | CRDP/LGED/DHK/ ICB/2013/W-01 | 100 | 1 | 2013-07-16
1 |  |  | City Region Development Project (1st revised) | CRDP | Improvement of Road and Drain in Ashulia, Savar |  | 3005 | CRDP/LGED/DHK/ NCB/2013/W-02 | 1 | road | 36105 |  | 17.26 | 361 | 2014-10-04 | Project Builders Ltd. (PBL) | 2013-09-26 |  | CRDP/LGED/DHK/ NCB/2013/W-02 | 100 | 1 | 2013-09-26
1 |  |  | City Region Development Project (1st revised) | CRDP | Impprovement of Road and Drain in Savar Pourashava |  | 3006 | CRDP/LGED/ Savar/NCB/2014/ W-01 | 1 | road | 36105 |  | 10.74 | 361 | 2016-03-09 | M/S. Md. Jamil Iqbal | 2015-02-26 |  | CRDP/LGED/ Savar/NCB/2014/ W-01 | 100 | 1 | 2015-02-26
1 |  |  | City Region Development Project (1st revised) | CRDP | Impprovement of Road and Drain in Savar Pourashava |  | 3007 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-01 | 1 | road | 36105 |  | 6.73 | 361 | 2016-03-21 | TI-SB (Jv) | 2015-03-22 |  | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-01 | 100 | 1 | 2015-03-22
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Fulbaria Bazar to Harannagar Bridge road (Ch. 00-1210m) Tetuljhora UP under Savar Upazila, District-Dhaka. (Estimate No. 209/10-11) ID No. 326723019 |  | 3010 | IRIDP/Dhk/W-90 | 1 | road | 36105 | 326723019 | 1.21 | 361 | 2011-04-26 | M/S. Polas Construction | 2011-09-20 |  | IRIDP/Dhk/W-90 | 100 | 1 | 2011-09-20 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Hemayetpur Bus Stand-Joynabare Beparepara Bazar (Ch. 00-1440m) under Savar Upazila, District-Dhaka. ID No. 326724101 |  | 3011 | IRIDP-DHK/W-151 | 1 | road | 36105 | 326724101 | 1.44 | 361 | 2013-11-01 | M/S. Sumon Enterprise | 2013-07-07 |  | IRIDP-DHK/W-151 | 100 | 1 | 2013-07-07
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Alipur Bridge-Firingikanda road by BC Ch. 00-1200m under Savar, District-Dhaka. (Estimate No. 51/11-12) |  | 3012 | IRIDP/Dhk/SW-116 | 1 | road | 36105 |  | 1.2 | 361 | 2012-09-20 | M/S. Jams Engineer's | 2012-05-14 |  | IRIDP/Dhk/SW-116 | 100 | 1 | 2012-05-14
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road & pipe drain on Swiss Tex Tile-Motin Bricks road (Ch. 00-700m) under Savar Upazila, District-Dhaka. (Estimate No. 86/11-12), ID No. 326724224 |  | 3013 | IRIDP/Dhk/W-134 | 1 | road | 36105 | 326724224 | 0.7 | 361 | 2012-10-01 | M/S.Redowan Builders | 2012-06-25 |  | IRIDP/Dhk/W-134 | 95 | 0 | 2012-06-25
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Shampur Bazar-Horindhora Tenary more road (Ch. 00-475m) under Savar Upazila, District-Dhaka. ID No. 326724345 |  | 3014 | IRIDP-DHK/W-221 | 1 | road | 36105 | 326724345 | 0.48 | 361 | 2013-10-27 | M/S. Chonchal Builder's | 2013-07-21 |  | IRIDP-DHK/W-221 | 70 | 0 | 2013-07-21
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Chapra to Chapra Kheyaghat road at Vakorta UP Ch. 00-355m road under Savar Upazila, District-Dhaka. (Estimate No. 21/10-11),IRIDP/Dhk/W-25 |  | 3015 | IRIDP/Dhk/W-25 | 1 | road | 36105 |  | 0.36 | 361 | 2011-02-14 | Boxer Enterprise | 2010-11-08 |  | IRIDP/Dhk/W-25 | 100 | 1 | 2010-11-08 | Work Order Cancel and bill paid with penalti
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvment of Kalmarchar-Shamlapur Hight School road Ch. 00-1200m under Vakurta UP, Savar, Dist-Dhaka. (Estimate No. 212/10-11), ID No. 326725232 |  | 3016 | IRIDP/Dhk/W-94 | 1 | road | 36105 | 326725232 | 1.2 | 361 | 2011-05-03 | M/S. KhanTraders | 2011-12-28 |  | IRIDP/Dhk/W-94 | 0 | 0 | 2011-12-28
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Anower Jong road (Narsari) to Helal Master's house road at ch. 00-870m) under Savar Upazila, District-Dhaka. (Estimate No.149/09-10), ID No. 326724264 |  | 3017 | IRIDP/Dhk/W-1 | 1 | road | 36105 | 326724264 | 0.87 | 361 | 2011-01-26 | M/S. G. C Enterprise | 2010-09-20 |  | IRIDP/Dhk/W-1 | 100 | 1 | 2010-09-20 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Construction of Kondolbag Pukurpar to Sarker Market via Manikgonjpara & Gosbag (GPS) road at Ch. 1250-2550m under Savar Upazila, District-Dhaka. (Estimate No.152/09-10), ID No. 326724202 |  | 3018 | IRIDP/Dhk/W-4 | 1 | road | 36105 | 326724202 | 1.35 | 361 | 2011-04-20 | M/S. Urmi Enterprise | 2010-09-14 |  | IRIDP/Dhk/W-4 | 100 | 1 | 2010-09-14 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of DEPZ-Vadial Chowrasta-Pobnarteck road (Ch.1000-1851m) under Savar Upazila, District-Dhaka. (Estimate No.153/09-10), ID No. 326724060 |  | 3019 | IRIDP/Dhk/W-5 | 1 | road | 36105 | 326724060 | 0.85 | 361 | 2011-03-25 | M/S. Builders Aid | 2010-09-20 |  | IRIDP/Dhk/W-5 | 100 | 1 | 2010-09-20 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Baron-Chitrashail-Manikgonj Para-Goshbag road (Ch.00-920m) under Savar Upazila, District-Dhaka. (Estimate No.154/09-10), ID No. 326724119 |  | 3020 | IRIDP/Dhk/W-6 | 1 | road | 36105 | 326724119 | 0.92 | 361 | 2011-03-30 | M/S. Tahmina Traders | 2010-09-19 |  | IRIDP/Dhk/W-6 | 100 | 1 | 2010-09-19 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of Ali Azam Sarkar house-Nohingertek-Manikgaonjpara road (Norshinghapur-Nischintapur-Tayebpur road) road (Ch.750-1750m) under Savar Upazila, District-Dhaka. (Estimate No.157/09-10), ID No. 326724077 |  | 3021 | IRIDP/Dhk/W-9 | 1 | road | 36105 | 326724077 | 1 | 361 | 2011-03-30 | M/S. Alam Traders | 2010-09-16 |  | IRIDP/Dhk/W-9 | 100 | 1 | 2010-09-16 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ashulia School & College to Tongi EPZ road via Bangobondu road at road under Savar Upazila, District-Dhaka. (Ch. 00-2060m) (Estimate No. 29/10-11) |  | 3022 | IRIDP/Dhk/W-33 | 1 | road | 36105 |  | 2.06 | 361 | 2011-04-07 | M/S. Eva Enterprise | 2010-12-09 |  | IRIDP/Dhk/W-33 | 100 | 1 | 2010-12-09 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road under Savar Upazila, District-Dhaka. (Ch. 1234-1817m) (Estimate No. 30/10-11) |  | 3023 | IRIDP/Dhk/W-34 | 1 | road | 36105 |  | 0.58 | 361 | 2011-03-03 | M/S. Hemany Enterprise | 2010-10-25 |  | IRIDP/Dhk/W-34 | 100 | 1 | 2010-10-25 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Yearpur-Yearpur High School road Ch. 00-300m under Savar Upazila, District-Dhaka. (Estimate No. 60/11-12), ID No. 326725234 |  | 3024 | IRIDP/Dhk/W-124 | 1 | road | 36105 | 326725234 | 0.3 | 361 | 2012-06-18 | Alpona Construction | 2012-04-12 |  | IRIDP/Dhk/W-124 | 100 | 1 | 2012-04-12 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ashulia UP Office-Ashulia Hazera Khatun Madrasha road (Ch. 410-560m) under Savar Upazila, District-Dhaka. ID No. 326725111 |  | 3025 | IRIDP-DHK/W-172 | 1 | road | 36105 | 326725111 | 0.15 | 361 | 2013-05-29 | M/S. Zia Enterprise | 2013-04-23 |  | IRIDP-DHK/W-172 | 100 | 1 | 2013-04-23 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Polashbari Bazar-Bashbari via Gocharartek road (Ch. 650-1200m) under Savar Upazila,, District-Dhaka. (Estimate No. 75/11-12), ID No. 326724333 |  | 3026 | IRIDP/Dhk/W-130 | 1 | road | 36105 | 326724333 | 0.55 | 361 | 2013-01-25 | M/S.Rima Tarders |  |  | IRIDP/Dhk/W-130 | 100 | 1
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Part-A) Improvement of road from Zamgora Chowrastha-Gazirchor High School road (Ch. 00-1010m) ID No. 326724153 & Part-(B) Maintenance of Gazirchot-Kandail road (Ch. 0-620m) under Savar Upazila, District-Dhaka. ID No. 326724235 |  | 3027 | IRIDP-DHK/W-170 | 1 | road | 36105 | 326724235 | 1.63 | 361 | 2013-07-16 | M/S. Nazma Enterprise | 2013-04-10 |  | IRIDP-DHK/W-170 | 100 | 1 | 2013-04-10
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Dendabor (RHD) Madrasha-Polash Bari-Gocharateck road (Ch. 412-1785m) under Savar Upazila, District-Dhaka. ID No. 326724289 |  | 3028 | IRIDP-DHK/W-177 | 1 | road | 36105 | 326724289 | 1.37 | 361 | 2013-10-19 | M/S. Dewan Enterprise | 2013-04-21 |  | IRIDP-DHK/W-177 | 100 | 1 | 2013-04-21
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement road from Gonokbari (Pacca road)-DEPZ road (ch. 00-498m) & Construction of 1x4.00x4.00m RCC Box Culvert (Ch. 455m) under Savar Upazila, District-Dhaka. (Estimate No. 04/11-12), ID No. 326724235 |  | 3029 | IRIDP/Dhk/SW-108 | 1 | road | 36105 | 326724235 | 0.5 | 361 | 2013-06-28 | M/S.Abdus Salam | 2012-06-26 |  | IRIDP/Dhk/SW-108 | 100 | 1 | 2012-06-26
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Ashulia Polli Biddut to Office-Ashulia High School road (Ch. 00-400m) under Savar Upazila, District-Dhaka. ID No. 326725253 |  | 3030 | IRIDP-DHK/W-167 | 1 | road | 36105 | 326725253 | 0.4 | 361 | 2013-07-25 | Maz Bussiness Syn | 2013-05-19 |  | IRIDP-DHK/W-167 | 100 | 1 | 2013-05-19 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of C&B Ashulia road's Mozid Market-Roton Member;s house-Hikmot Alis house Dinestry Soweater's Ltd. (Akupara-Bongabandu road via Belma) under Savar Upazila, District-Dhaka. (Ch. 00-1500m) ID No. 326724175 (Estimate No. 205/10-11) |  | 3031 | IRIDP/Dhk/SW-85 | 1 | road | 36105 | 326724175 | 1.5 | 361 | 2011-07-13 | M/S. Unique Engineering | 2011-07-06 |  | IRIDP/Dhk/SW-85 | 70 | 0 | 2011-07-06
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from H/O Salek Mohajon at Konda-H/O Javed Ali (Ch. 00-1200m) under Bongaon UP under Savar Upazila, District-Dhaka. (Estimate No. 119/2010-11) |  | 3032 | IRIDP/Dhk/W-59 | 1 | road | 36105 |  | 1.2 | 361 | 2011-06-07 | M/S. Suchana Enterprise | 2011-02-02 |  | IRIDP/Dhk/W-59 | 60 | 0 | 2011-02-02 | W/O Canceled
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of Ashulia UP-Dolpur via Baro Rangamatia-Katgora road (Ch. 6260-7260m under Savar Upazila, District-Dhaka. (Estimate No.155/09-10), ID No. 3267223010 |  | 3033 | IRIDP/Dhk/W-7 | 1 | road | 36105 | 3267223010 | 1 | 361 | 2011-03-25 | M/S. Sony Enterprise | 2010-09-19 |  | IRIDP/Dhk/W-7 | 60 | 0 | 2010-09-19
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Sreepur-Kashimpur road Hasan Member house-Hazi Rashid Shaheb house road (Ch. 00-575m) under Savar Upazila, District-Dhaka. (Estimate No.156/09-10), ID No. 326725112 |  | 3034 | IRIDP/Dhk/W-8 | 1 | road | 36105 | 326725112 | 0.58 | 361 | 2010-12-27 | M/S. Bari Construction | 2010-09-21 |  | IRIDP/Dhk/W-8 | 60 | 0 | 2010-09-21
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Yearpur H/O Jamat Ali-Lalpahar Buripara road Ch. 00-900m under Savar Upazila, District-Dhaka. (Estimate No. 59/11-12), ID No. 326724334 |  | 3035 | IRIDP/Dhk/W-123 | 1 | road | 36105 | 326724334 | 0.9 | 361 | 2012-07-18 | M/S. Sajal Enterprise | 2012-04-12 |  | IRIDP/Dhk/W-123 | 60 | 0 | 2012-04-12
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Kandail Eidgah-Etakhola via Ghoshbag Rotary Girl's School road (Ghoshbag Rotary Girls School-Dewan filling Station) (Ch. 00-1240m) under Savar Upazila, District-Dhaka. ID No. 326724072 |  | 3036 | IRIDP-DHK/W-164 | 1 | road | 36105 | 326724072 | 1.24 | 361 | 2013-08-25 | M/S. Talukder Traders | 2013-05-19 |  | IRIDP-DHK/W-164 | 60 | 0 | 2013-05-19
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Kohinor Mill to Pathalia-Rohimpur road (Ch. 400-1650m) under Savar Upazila, District-Dhaka. ID No. 326724115 |  | 3037 | IRIDP-DHK/W-174 | 1 | road | 36105 | 326724115 | 1.25 | 361 | 2013-05-28 | M/S. M.R Construction | 2013-05-21 |  | IRIDP-DHK/W-174 | 60 | 0 | 2013-05-21
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Savar GC-CRP-Lalteck-Savar UP road (Ch.400-1650m) under Savar Upazila, District-Dhaka. ID No. 326723027 |  | 3038 | IRIDP-DHK/W-175 | 1 | road | 36105 | 326723027 | 1.25 | 361 | 2013-05-06 | Amanat Shah Electrict & Engr. | 2013-04-29 |  | IRIDP-DHK/W-175 | 60 | 0 | 2013-04-29
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Development of Polashbari-Kaichabari-Bashbari road (Ch. 1.500-2.500Km) under Savar Upazila, District-Dhaka. ID No. 326724096 (Estimate No. 202/10-11) |  | 3039 | IRIDP/Dhk/W-86 | 1 | road | 36105 |  | 1 | 361 | 2013-12-04 | M/S. Dewan Enterprise | 2011-08-08 |  | IRIDP/Dhk/W-86 | 100 | 1 | 2011-08-08 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Kaliakoir Kamlapur road Krishibid West Vew main Gate-Bagne Bare road (Ch. 00-750m) under Savar Upazila, District-Dhaka. (Estimate No. 84/11-12), ID No. 326725251 |  | 3040 | IRIDP/DHK/W-132 | 1 | road | 36105 | 326725251 | 0.75 | 361 | 2013-08-29 | Fina Superlub Co. | 2012-07-10 |  | IRIDP/DHK/W-132 | 100 | 1 | 2012-07-10 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Choto Kaliakoir Pucca road-Komlapur road (Ch. 00-520m) under Savar Upazila, District-Dhaka. ID No. 326724350 |  | 3041 | IRIDP-DHK/W-168 | 1 | road | 36105 | 326724350 | 0.52 | 361 | 2013-06-16 | M/S. Nazma Enterprise | 2013-04-10 |  | IRIDP-DHK/W-168 | 100 | 1 | 2013-04-10
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | (A) Improvement of Polashbari- Kaichabari-Bashbari road (Ch. 2500-3500m) & Link road & Ch.00-300m) (B) Same road 2715m, 2757m, 2788m & 3253m Ch. 0.600x0.600m 4 Drain Culvert under Savar Upazila, District-Dhaka. ID No. 326724096 |  | 3042 | IRIDP-DHK/W-165 | 1 | road | 36105 | 326724096 | 1 | 361 | 2014-01-15 | M/S. Talukder Traders | 2013-06-02 |  | IRIDP-DHK/W-165 | 100 | 1 | 2013-06-02 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Gerua Bazar-Jamshing Bazar a road (Ch. 00-672m) under Savar Upazila, District-Dhaka. ID No. 326724190 |  | 3043 | IRIDP-DHK/W-173 | 1 | road | 36105 | 326724190 | 0.67 | 361 | 2013-07-27 | M/S. Hasib Enterprise | 2013-04-21 |  | IRIDP-DHK/W-173 | 60 | 0 | 2013-04-21
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Part-A: Improvement of Dhakhin Gazirchot Sher Ali Market-Bottola road (Ch. 0-750m), Part-B: Construction of 4.50x3.50m RCC Box culvert road on Dhakhin Gazirchot Sher Ali Market-Bottola (Ch. 630m) road under Savar Upazila, District-Dhaka. (Estimate No.151/ |  | 3044 | IRIDP/Dhk/W-3 | 1 | road | 36105 |  | 0.75 | 361 | 2011-01-27 | M/S. Deep Laid Enterprise | 2010-09-21 |  | IRIDP/Dhk/W-3 | 50 | 0 | 2010-09-21
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Construction of 90.00m RCC Girder Bridge over Kasoir Khal on Nutun Bondor Shimulia UP Office-Kasoir-Bagabari road at Ch. 0+610m under Savar Upazila, District-Dhaka.(Estimate No. 188/10-11) ID No. 326724204 |  | 3045 | IRIDP/Dhk/W-82 | 1 | road | 36105 | 326724204 |  | 361 | 2012-06-26 | M/S. Humaira Enterprise | 2011-06-20 |  | IRIDP/Dhk/W-82 | 45 | 0 | 2011-06-20
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ambagan-Islamnagar-Bottola-Gerua Bazar road (Ch. 00-972m) under Savar Upazila, District-Dhaka. (Estimate No. 85/11-12), ID No. 326724192 |  | 3046 | IRIDP/DHK/W-133 | 1 | road | 36105 | 326724192 | 0.97 | 361 | 2014-04-23 | M/S. Alam Traders | 2012-07-01 |  | IRIDP/DHK/W-133 | 60 | 0 | 2012-07-01 | W/O Canceled and 242990/- pending paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | (A) Improvement of Nickrail-Chandpur-Vobanipur road (Ch. 00-1500m) (B) Same road 1100m Ch. 0.600x0.600m 1 Drain Culvert under Savar Upazila, District-Dhaka. ID No. 326724153 |  | 3047 | IRIDP-DHK/W-171 | 1 | road | 36105 | 326724153 | 1.5 | 361 | 2013-09-15 | M/S. S.S Construction | 2013-05-09 |  | IRIDP-DHK/W-171 | 60 | 0 | 2013-05-09
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Ashulia UP Office to Hajerakhatun Madrasha road at Ch. 00-410m under Savar Upazila, District-Dhaka. (Estimate No.150/09-10), ID No. 326725111 |  | 3048 | IRIDP/Dhk/W-2 | 1 | road | 36105 | 326725111 | 0.41 | 361 | 2011-01-04 | M/S. Nabil International | 2010-09-29 |  | IRIDP/Dhk/W-2 | 20 | 0 | 2010-09-29
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Chakulia Pucca road (Gosh Bag) to Chakulia Deep Tubewell road (Ch. 00-500m) under Savar Upazila, District-Dhaka. ID No. 326724349 |  | 3049 | IRIDP-DHK/W-169 | 1 | road | 36105 | 326724349 | 0.5 | 361 | 2013-12-09 | M/S. Hasib Enterprise | 2013-04-21 |  | IRIDP-DHK/W-169 | 100 | 1 | 2013-04-21
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Jamgora Simultoli-Sayed Masterbari-Jamgora Primary School road (Ch. 00-1000m) under Savar Upazila, District-Dhaka. ID No. 326725025 |  | 3050 | IRIDP-DHK/W-166 | 1 | road | 36105 | 326725025 | 1 | 361 | 2014-03-13 | M/S. Jakir Hossain | 2013-07-29 |  | IRIDP-DHK/W-166 | 100 | 1 | 2013-07-29
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Toyebpur (Zirabo) Dewan Idrish College-Safina Poultry Firm Culvert Approach-Tayebpur Jame Mosque road) (Ch. 00-455m) under Savar Upazila, District-Dhaka. ID No. 326724247 |  | 3051 | IRIDP-DHK/W-176 | 1 | road | 36105 | 326724247 | 0.46 | 361 | 2013-06-28 | M/S. Biplop Enterprise | 2013-04-23 |  | IRIDP-DHK/W-176 | 0 | 0 | 2013-04-23
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road from Shampur Bazar-Horindhora Tenary more road (Ch. 00-475m) under Savar Upazila, District-Dhaka. ID No. 326724345 |  | 3052 | IRIDP-DHK/SW-221 | 1 | road | 36105 | 326724345 | 0.48 | 361 | 2013-10-27 | M/S. Chonchal Builder's | 2013-07-21 |  | IRIDP-DHK/SW-221 | 100 | 1 | 2013-07-21 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Alipur Bridge-Firingikanda road by BC Ch. 450-700m under Savar, District-Dhaka. (Estimate No. 51/11-12) ID No.326724272 |  | 3053 | IRIDP/Dhk/W-116 | 1 | road | 36105 | 326724272 | 1.2 | 361 | 2013-03-10 | M/S. Jams Engineer's | 2012-05-14 |  | IRIDP/Dhk/W-116 | 100 | 1 | 2012-05-14 | Final bill paid
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of road & pipe drain on Swiss Tex Tile-Motin Bricks road (Ch. 450-700m) under Savar Upazila, District-Dhaka. (Estimate No. 86/11-12), ID No. 326724224 |  | 3054 | IRIDP/Dhk/SW-134 | 1 | road | 36105 | 326724224 | 0.25 | 361 | 2012-10-01 | M/S.Redowan Builders | 2012-06-25 |  | IRIDP/Dhk/SW-134 | 95 | 0 | 2012-06-25
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvment of Kalmarchar-Shamlapur Hight School road Ch. 00-1200m under Vakurta UP, Savar, Dist-Dhaka. (Estimate No. 212/10-11), ID No. 326725232 |  | 3055 | IRIDP/Dhk/SW-94 | 1 | road | 36105 | 326725232 | 1.2 | 361 | 2011-05-03 | M/S. KhanTraders | 2011-12-28 |  | IRIDP/Dhk/SW-94 | 0 | 0 | 2011-12-28 | W/O Canceled
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | a)Improvement of Road from Hemayetpur Suwitch Textile to Motin Brick Field (Ch:00-445m) Road Code:326724224. b) Improvement of Road from Apurupa Textile Miles to Bagbari Via Kuddus Ali House. (CH:00-253.00m) Road Code:326725265 |  | 3056 | IRIDP/DHK/DW-241 | 1 | road | 36105 | 326725265 | 0.25 | 361 |  | M/S. Shafique & Brothers |  |  | IRIDP/DHK/DW-241 | 0 | 0
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Bangabandhu Road to Katgora Bazar via Aragaon Road (Ch. 00-1110 m) under Savar Upazila, District-Dhaka. (Road ID No: 326724037) |  | 3057 | IRIDP/DHK/DW-238 | 1 | road | 36105 | 326724037 | 1.11 | 361 | 2014-10-01 | M/S Shafiqual & Brothers | 2014-03-03 |  | IRIDP/DHK/DW-238 | 60 | 0 | 2014-03-03
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | Improvement of Dendabor (PBS)-Corapir Mazar road from Ch. 00-2013m. |  | 3067 | IRIDP-2/DHK/DW-13 | 1 | road | 36105 |  | 2.01 | 361 | 2017-01-31 | M/S. M.B Traders, Prop: Md.Masudur Rahman Khan | 2016-03-23 |  | IRIDP-2/DHK/DW-13 | 100 | 1 | 2016-03-23
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | a) Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road from Ch. 3179-4044m.b) Construction of 01 no 0.900mx1.000m culvert at ch.3537m on the same road. |  | 3068 | IRIDP-2/DHK/DW-14 | 1 | road | 36105 |  | 0.87 | 361 | 2016-09-26 | M/S. M.B Traders, Prop: Md.Masudur Rahman Khan | 2016-03-23 |  | IRIDP-2/DHK/DW-14 | 100 | 1 | 2016-03-23
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | Improvement of Jahangir Nagar Bhashani Hall-Dakshin Shindhuria Road from Ch. 500-1500m. |  | 3069 | IRIDP-2/DHK/DW-15 | 1 | road | 36105 |  | 1 | 361 | 2016-11-12 | M/S. Shahjahan Traders Prop: Mr. Shawkat Hossain | 2016-03-16 |  | IRIDP-2/DHK/DW-15 | 100 | 1 | 2016-03-16
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | c) Dhaka-Aricha RHD 20 Mile Army check post-Pathalaia UP (Ghugudia) Road |  | 3078 | RTIP-II/DHA/UNR-12 | 1 | road | 36105 |  | 3.55 | 361 | 2017-02-20 |  | 2014-08-13 |  | RTIP-II/DHA/UNR-12 | 100 | 1 | 2014-08-13
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | Ashulia UP Office-Rustumpur bazar road |  | 3079 | RTIP-II/DHA/RPM-106 | 1 | road | 36105 |  | 3.33 | 361 | 2015-11-08 | M/S. Aunica International | 2014-03-19 |  | RTIP-II/DHA/RPM-106 | 100 | 1 | 2014-03-19 | Final
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | d) Construction of 2x4.00x5.50m RCC Box Culvert at Ch. 2+150km on Dhaka-Aricha RHD 20 Mile Army check post-Pathalaia UP (Ghugudia) Road |  | 3080 | RTIP-II/DHA/UNR-12-STR-2 | 1 | road | 36105 |  | 8 | 361 | 2017-05-16 |  | 2015-07-23 |  | RTIP-II/DHA/UNR-12-STR-2 | 100 | 1 | 2015-07-23
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | Zirani Bazar-Shimulia Bazar Road |  | 3081 | RTIP-II/DHA/RPM-199 | 1 | road | 36105 |  | 8.25 | 361 | 2019-02-28 | AL_AMIN-KINGDOM-JVA | 2016-08-07 |  | RTIP-II/DHA/RPM-199 | 80 | 0 | 2016-08-07
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | Bhakurta UP-Mugrakanda-Mohammad Pur. City protection embankment Rd. |  | 3082 | RTIP-II/DHA/RPM-346 | 22 | embankment | 36105 |  | 1.3 | 361 | 2017-12-19 | Western Engineering (Pvt.) Ltd | 2017-03-20 |  | RTIP-II/DHA/RPM-346 | 100 | 1 | 2017-03-20 | Final. Force Majeure
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | Savar Bazar Bus Stand-Birulia UP-Birulia bazar Rd |  | 3083 | RTIP-II/DHA/RPM-392 | 1 | road | 36105 |  | 2.68 | 361 | 2018-06-30 | Topline | 2017-04-25 |  | RTIP-II/DHA/RPM-392 | 100 | 1 | 2017-04-25
6 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of Zirani-Shimulia Analbari-Nallapolla road Ch. 00-690m under Savar Upazila, District-Dhaka. (Estimate No. 22/11-12), ID No. 32672114, |  | 3087 | GDP-II/Dha/Sav/W(R)-05 | 1 | road | 36105 | 32672114 | 0.69 | 361 | 2012-04-21 | M/S Aunika International | 2012-01-22 |  | GDP-II/Dha/Sav/W(R)-05 | 0 | 0 | 2012-01-22
6 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of Rajfulbaria Bus Stand-Rishipara via Fulbaria Bazar Road Ch. 00m- 650 m (ID No. 3267623005) under Saver Upazila Dist: Dhaka. |  | 3088 | GDP-II/Dha/sav/W(R)-11 | 1 | road | 36105 | 3267623005 | 0.65 | 361 | 2012-06-30 | M/S Emran Builders | 2012-03-01 |  | GDP-II/Dha/sav/W(R)-11 | 10 | 0 | 2012-03-01
6 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of Aragaon Primary School-Doshaid School road Ch. 1400-2535m (ID No. -326724037) under Savar Upazila, District-Dhaka. (Estimate No. 53/11-12) |  | 3089 | GDP-II/DHA/Sav/W(R)-13 | 1 | road | 36105 | 326724037 | 1.14 | 361 | 2012-08-02 | M/S Futme Castle Constriction | 2012-04-03 |  | GDP-II/DHA/Sav/W(R)-13 | 0 | 0 | 2012-04-03
6 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | A) Improvement of road from Gerua Bazar to Physics Department via Moulana Bhasani Hall & Bangabandhu Sheikh Mujibur Rahman Hall of Jahangir Nagar University Ch. 00-1020m (ID No. 326724003) & B) Improvement of Baroipara (Pacca road)-Olosara road Ch. 00-65m |  | 3090 | GDP-II/DHA/Sav/W(R)-15 | 1 | road | 36105 | 326724003 |  | 361 |  |  |  |  | GDP-II/DHA/Sav/W(R)-15 | 0 | 0 |  | Tender sent to H/Q for approval
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | sandip com. primary school School Reconstruction |  | 3094 | PEDP-III/DHK/SAV/2011-12/W1.0072 | 3 | school building | 36105 |  |  | 361 | 2014-01-04 | M/s Emran Builders | 2012-09-07 |  | PEDP-III/DHK/SAV/2011-12/W1.0072 | 100 | 1 | 2012-09-07
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | GAZIR CHAT School Additional Room |  | 3095 | PEDP-III/DHK/SAV/2012-13/W2.2128 | 3 | school building | 36105 |  |  | 361 | 2014-08-05 | M/s Emran Builders | 2013-07-30 |  | PEDP-III/DHK/SAV/2012-13/W2.2128 | 100 | 1 | 2013-07-30
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | PARAGRAM School Additional Room |  | 3096 | PEDP-III/DHK/SAV/2011-12/W2.0062 | 3 | school building | 36105 |  |  | 361 | 2013-06-25 | M/S Udy Enterprise | 2012-06-09 |  | PEDP-III/DHK/SAV/2011-12/W2.0062 | 100 | 1 | 2012-06-09
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | NUTAN BANDAR School Additional Room |  | 3097 | PEDP-III/DHK/SAV/2011-12/W2.0538 | 3 | school building | 36105 |  |  | 361 | 2013-07-04 | M/s Boyanna Enterprise | 2012-07-05 |  | PEDP-III/DHK/SAV/2011-12/W2.0538 | 100 | 1 | 2012-07-05
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | TETUL JHORA School Additional Room |  | 3098 | PEDP-III/DHK/SAV/2011-12/W2.0539 | 3 | school building | 36105 |  |  | 361 | 2013-07-04 | M/s Nazma Enterprise | 2012-07-05 |  | PEDP-III/DHK/SAV/2011-12/W2.0539 | 100 | 1 | 2012-07-05
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | SAIPARA School Additional Room |  | 3099 | PEDP-III/DHK/SAV/2011-12/W2.1398 | 3 | school building | 36105 |  |  | 361 | 2013-10-06 | M/s Aziz Construction | 2012-09-30 |  | PEDP-III/DHK/SAV/2011-12/W2.1398 | 100 | 1 | 2012-09-30
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | GOMAIL School Additional Room |  | 3100 | PEDP-III/DHK/SAV/2011-12/W2.0540 | 3 | school building | 36105 |  |  | 361 | 2013-07-04 | M/s M.R Construction | 2012-07-05 |  | PEDP-III/DHK/SAV/2011-12/W2.0540 | 100 | 1 | 2012-07-05
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | BARADESHI School Additional Room |  | 3101 | PEDP-III/DHK/2012-13/W2.1842 | 3 | school building | 36105 |  |  | 361 | 2014-06-11 | M/s Kazi Traders | 2013-09-05 |  | PEDP-III/DHK/2012-13/W2.1842 | 100 | 1 | 2013-09-05
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | CHAKAL GRAM School Additional Room |  | 3102 | PEDP-III/DHK/SAV/2012-13/W2.1921 | 3 | school building | 36105 |  |  | 361 | 2013-10-15 | M/s Shahid & Co. | 2013-01-09 |  | PEDP-III/DHK/SAV/2012-13/W2.1921 | 25 | 0 | 2013-01-09
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | kabirpur reg. primary school School Additional Room |  | 3103 | PEDP-III/DHK/SAV/2013-14/W2.2839 | 3 | school building | 36105 |  |  | 361 | 2014-07-10 | M/s Alam traders | 2013-11-05 |  | PEDP-III/DHK/SAV/2013-14/W2.2839 | 85 | 0 | 2013-11-05
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | kabirpur reg. primary school School Major Maintenance |  | 3104 | PEDP-III/DHK/SAV/2013-14/W3.0400 | 3 | school building | 36105 |  |  | 361 | 2014-11-09 | M/S Udoy Enterprise | 2014-04-23 |  | PEDP-III/DHK/SAV/2013-14/W3.0400 | 100 | 1 | 2014-04-23
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | KRINSHAPUR HASSIN School Major Maintenance |  | 3105 | PEDP-III/DHK/SAV/2011-12/W3.0325 | 3 | school building | 36105 |  |  | 361 | 2013-04-06 | M/s Mow Construction | 2012-09-30 |  | PEDP-III/DHK/SAV/2011-12/W3.0325 | 100 | 1 | 2012-09-30
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Savar UP (Dhaka-Aricha RHDD) Genda-Sadapur Bangoan road (Ch. 7315-7830m) under Savar Upazila, District-Dhaka. (Estimate No. 149/08-09), Package No. UNR-GDP-W-07/08-10 |  | 3109 | GDP-D-18 | 1 | road | 36105 |  | 0.52 | 361 | 2009-07-21 | The Bhuyan Engineers Ltd. | 2009-04-27 |  | GDP-D-18 | 100 | 1 | 2009-04-27
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Part-A) Improvement of Sreepur-Gohailbari via Shobondi & Dhamsona UP road (Ch. 5224-6570m) under Savar Upazial, District-Dhaka. (Estimate No. 150/08-09), Package No. UNR-GDP-W-08/08-09 |  | 3110 | GDP-D-19 | 1 | road | 36105 |  | 1.35 | 361 | 2009-07-05 | M/S. M.M Construction | 2009-03-12 |  | GDP-D-19 | 100 | 1 | 2009-03-12
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Baipail BKSP Training Academy link road (Ch. 00-344m).under Savar Upazila, District-Dhaka.Package No.UNR-GDP-W-20/08-09 |  | 3111 | GDP-D-26 | 1 | road | 36105 |  | 0.34 | 361 | 2009-09-04 | M/S. M.R Enterprise | 2009-06-02 |  | GDP-D-26 | 100 | 1 | 2009-06-02
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Hatubhanga road to Pathalia Housing Society road (Ch. 500-750m).under Savar Upazila, District-Dhaka. Package No. UNR-GDP-W-08/08-09 |  | 3112 | GDP-D-28 | 1 | road | 36105 |  | 0.25 | 361 | 2009-10-14 | M/S. Kazoli Enterprise | 2009-07-20 |  | GDP-D-28 | 100 | 1 | 2009-07-20
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Boroipara RHD-Polly Biddut road (Ch. 981-1620m).under Savar Upazila, District-Dhaka.(Estimate No. 19/09-10) Package No. UNR-GDP-W-05/09-10 |  | 3113 | GDP-D-33 | 1 | road | 36105 |  | 0.64 | 361 | 2010-05-20 | M/S. Talukder Enterprise | 2010-01-20 |  | GDP-D-33 | 100 | 1 | 2010-01-20
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch. 00-826m).under Savar Upazila, District-Dhaka.(Estimate No. 21/09-10), Package No. UNR-GDP-W-07/09-10 |  | 3114 | GDP-D-37 | 1 | road | 36105 |  | 0.83 | 361 | 2010-05-24 | M/S. Khondoker Enterprise | 2010-01-24 |  | GDP-D-37 | 100 | 1 | 2010-01-24
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch. 825-1565m).under Savar Upazila, District-Dhaka.(Estimate No. 22/09-10), Package No. UNR-GDP-W-09/09-10 |  | 3115 | GDP-D-38 | 1 | road | 36105 |  | 0.74 | 361 | 2011-05-02 | M/S. T\Khondakar Enterprise | 2011-01-24 |  | GDP-D-38 | 65 | 0 | 2011-01-24
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch.1565-2219m).under Savar Upazila, District-Dhaka.(Estimate No. 23/09-10), Package No. UNR-GDP-W-10/09-10 |  | 3116 | GDP-D-39 | 1 | road | 36105 |  | 0.65 | 361 | 2010-05-24 | M/S. Khondoker Enterprise | 2010-01-24 |  | GDP-D-39 | 100 | 1 | 2010-01-24
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Durgapur-Porbochala ch. 00-570m, 00-175m |  | 3117 | GDP-D-59 | 1 | road | 36105 |  | 0.75 | 361 | 2012-04-22 | M/S. Anando Construction | 2010-03-08 |  | GDP-D-59 | 100 | 1 | 2010-03-08
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Dhaka-Aricha RHD to Genda Shadapur-Bongaon ch. 2100-3500m road. |  | 3118 | GDP-D-05 | 1 | road | 36105 |  | 1.4 | 361 | 2010-07-13 | M/S. Khan Enterprise | 2010-03-13 |  | GDP-D-05 | 100 | 1 | 2010-03-13
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Mugrakanda Vakurta road Baily Bridge to Turag Super Market (Dewan house connecting road) road under Savar Upazila, (Ch. 00-210m) District-Dhaka. |  | 3119 | GDP-D-35 | 1 | road | 36105 |  | 0.21 | 361 | 2010-09-12 | M/S. Integrated Solution Ltd. | 2010-05-12 |  | GDP-D-35 | 70 | 0 | 2010-05-12
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | a) Improvement of Tengori main road Shop of Rafiq-Tengori Mujibur & Ershad House road (Ch. 0-360m & 0-215m), b) Madhaya Konapara main road (Ch. 0-490m & 107m) under Savar Upazila, District-Dhaka. (Estimate No.94/09-10) |  | 3120 | GDP-D-58 | 1 | road | 36105 |  | 1.17 | 361 | 2010-09-04 | M/S. S.A Engineering | 2010-05-04 |  | GDP-D-58 | 100 | 1 | 2010-05-04
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Zirani-Shimulia road Samon Ali Colony Konapara Jame Mosque road (Ch. 522-1044m) under Savar Upazila, District-Dhaka. |  | 3121 | GDP-D-62 | 1 | road | 36105 |  | 0.52 | 361 | 2010-07-02 | M/S. Siam Corporaton | 2010-05-02 |  | GDP-D-62 | 60 | 0 | 2010-05-02
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kalasuti Sultan house-Madrasha via H/O Haji Based road ch. 00-802m |  | 3122 | GDP-D-74 | 1 | road | 36105 |  | 0.8 | 361 | 2010-09-22 | M/S. M.S.A. Construction & Engineering | 2010-06-22 |  | GDP-D-74 | 100 | 1 | 2010-06-22
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kaltasuti Edrish Chowkider house-Noapara house of Jamal road at Shimulia UP (Ch. 00-587m) |  | 3123 | GDP-D-73 | 1 | road | 36105 |  | 0.59 | 361 | 2010-09-05 | Pial Construction | 2010-06-05 |  | GDP-D-73 | 100 | 1 | 2010-06-05
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Tenguri Harun Factory to Kaltasuti Morichkata Shadhubari road (Ch. 00-545m) |  | 3124 | GDP-D-63 | 1 | road | 36105 |  | 0.55 | 361 | 2010-09-04 | M/S. Joy Construction | 2010-07-04 |  | GDP-D-63 | 50 | 0 | 2010-07-04
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Sreepur Busstand Subondi Trimohoni road (Ch. 1150-2712m). |  | 3125 | GDP-D-91 | 1 | road | 36105 |  | 1.56 | 361 | 2011-01-24 | M/S. Hasan Traders | 2010-10-24 |  | GDP-D-91 | 60 | 0 | 2010-10-24
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Gonakpara Govt. Primary School Joynal Dealar House road (Ch. 00-322m). |  | 3126 | GDP-D-83 | 1 | road | 36105 |  | 0.32 | 361 | 2011-01-09 | M/S. J&J Corporation | 2010-10-09 |  | GDP-D-83 | 60 | 0 | 2010-10-09
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Hemayetpur Oporupa Textiles Mill to Bugbari Connecting road (Ch. 00-253m). |  | 3127 | GDP-D-85 | 1 | road | 36105 |  | 0.25 | 361 | 2010-10-07 | M/S. Santa Enterprise | 2010-08-07 |  | GDP-D-85 | 60 | 0 | 2010-08-07
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of a) Kaliakoir Nabinagaor road at Tengori Shop of Gias Uddin-Tengori Modina Colony road (Ch. 00-357m), b) Purbo Katlasuti house of Zahirul Islam-House of Nazir Hossain road Ch. 00-250m |  | 3128 | GDP-D-86 | 1 | road | 36105 |  | 0.61 | 361 | 2010-10-09 | Deep-Laid Enterprise | 2010-08-03 |  | GDP-D-86 | 70 | 0 | 2010-08-03
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from a) House of Khaleque-House of Azgar Ali at Tengori Ch. 00-210m b) House of Belayet Hossain-house of Abu Taher at Tan Konapara road Ch. 00-150m |  | 3129 | GDP-D-87 | 1 | road | 36105 |  | 0.36 | 361 | 2010-10-08 | M/S. Rekha Enterprise | 2010-08-08 |  | GDP-D-87 | 60 | 0 | 2010-08-08
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Paragram Rustompur road Deun-Moinuddin Shop to Hazirat Ali House Ch. 00-568m |  | 3130 | GDP-D-76 | 1 | road | 36105 |  | 0.57 | 361 | 2010-10-19 | M/S. Momtaz Builder | 2010-07-19 |  | GDP-D-76 | 25 | 0 | 2010-07-19
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Circular road of Savar Cantonment Savar, Dhaka. Ch. 00-10100m Dhaka.(Estimate No. 51/10-11) GDP-D-111 |  | 3131 | GDP-D-111 | 1 | road | 36105 |  | 10.1 | 361 | 2011-12-12 | Islam Trading Construction | 2010-12-12 |  | GDP-D-111 | 30 | 0 | 2010-12-12
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road Ch. 1817-2328m under Savar Upazila, District-Dhaka. (Estimate No. 48/10-11 |  | 3132 | GDP-D-100 | 1 | road | 36105 |  | 0.51 | 361 | 2011-04-01 | M/S Haji Enterprize | 2011-01-01 |  | GDP-D-100 | 40 | 0 | 2011-01-01
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | A) Improvement of Koltasuti Sabida Chala-Barol Kabarastan road Ch. 00-576m, B) Improvement of Koltasuti Sabida Chala-Dhalivari road Ch. 00-342m & c) Improvement of Tengori-Konapara Baidgaon road Ch. 00-837m under Savar Upazila, District-Dhaka. (Estimate N |  | 3133 | GDP-D-104 | 1 | road | 36105 |  | 1.18 | 361 | 2011-04-21 | M/S Bishal Enterprise | 2001-12-21 |  | GDP-D-104 | 60 | 0 | 2001-12-21
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | A) Improvement road from Miar Rahman House-House of Sahufu at Kaltasuti (Road from House of Badsha-House of Halim at Kaltasuti (Ch. 00-145m & Ch. 00-145m) B) Tengori Akali House-Tengori Mujibur House road (Ch. 00-340m) under Savar Upazila, District-Dhaka |  | 3134 | GDP-D-105 | 1 | road | 36105 |  | 0.63 | 361 | 2011-06-09 | M/S. Zia Construction | 2011-02-02 |  | GDP-D-105 | 60 | 0 | 2011-02-02
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kuturia-Bogabari Bazar road Ashulia UP road (Ch.00-1700m) under Savar Upazila, Dist-Dhaka. (Estimate No.66/10-11) |  | 3135 | GDP-D-106 | 1 | road | 36105 |  | 1.7 | 361 | 2011-05-04 | M/S. Mollah Traders | 2011-02-05 |  | GDP-D-106 | 50 | 0 | 2011-02-05
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Part-A: Improvement of road from Sreepur-Subondi road near shop of Kojon Miah to house of Azim Uddin Member at Subondi (Ch. 00-1064m) & Part-B: Construction of 0.60m Span U-Drain at (Ch. 52m & 160m) on same road under Savar Upazila, District-Dhaka. (Estim |  | 3136 | GDP-D-116 | 1 | road | 36105 |  | 1.06 | 361 | 2011-07-19 | M/S Khazababa Center Point | 2011-03-20 |  | GDP-D-116 | 10 | 0 | 2011-03-20
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Part-A: Improvement of Purbo Kaltasuti Muslimteck (House of Surot Ali)-Mollarbag Mosque road (Ch. 00-1270m) & Part-B: Construction of 2.00m Span Box at (Ch. 692m) on the same road under Savar Upazila, District-Dhaka. (Estimate No. 122/10-11,Package No. UN |  | 3137 | GDP-D-138 | 1 | road | 36105 |  | 1.27 | 361 | 2011-07-12 | M/S. Hasan Traders | 2011-03-13 |  | GDP-D-138 | 65 | 0 | 2011-03-13
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Rostumpur Shadhupara Chowrastha-Kagan Paragram Connecting via Paragram Koborstan road (Ch. 00-976m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 124/10-11 |  | 3138 | GDP-D-125 | 1 | road | 36105 |  | 0.98 | 361 | 2011-05-16 | M/S. Kashem Traders | 2011-02-17 |  | GDP-D-125 | 65 | 0 | 2011-02-17
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Ronosthal-Myjhail-Pychail road (Ch. 00-1150m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 125/10-11 |  | 3139 | GDP-D-126 | 1 | road | 36105 |  | 1.15 | 361 | 2011-07-02 | M/S. Sadia Enterprise | 2011-03-28 |  | GDP-D-126 | 60 | 0 | 2011-03-28
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Kuturia Dewan Bari Mosque-Khatghora High School road (Ch. 00-1038m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 126/10-11 |  | 3140 | GDP-D-127 | 1 | road | 36105 |  | 1.04 | 361 | 2011-06-06 | M/S. Palash Construction | 2011-03-01 |  | GDP-D-127 | 0 | 0 | 2011-03-01
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Purbo Baidgaon (Pagla Bazar)-Purbo Baidgaon Govt. Primary School road (Ch.250-1000m) under Savar Upazila, Dist-Dhaka. (Estimate No.70/10-11) Package No. UNR-GDP-D-112 |  | 3141 | GDP-D-112 | 1 | road | 36105 |  | 0.75 | 361 | 2011-05-04 | M/S. Mollah Traders | 2011-02-05 |  | GDP-D-112 | 0 | 0 | 2011-02-05
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Bariopara (RHD)-Polly Biddut road (Ch. 00-1134m) under Savar Upazila, Dist-Dhaka. (Estimate No.71/10-11) Package No. UNR-GDP-D-113 |  | 3142 | GDP-D-113 | 1 | road | 36105 |  | 1.13 | 361 | 2011-06-30 | M/S. Bishal Enterprise | 2011-02-23 |  | GDP-D-113 | 65 | 0 | 2011-02-23
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Goalbari Machinepar Momin Bari-House of Ali (Ch.00-662m) under Savar Upazila, Dist-Dhaka. (Estimate No.72/10-11) Package No. UNR-GDP-D-114 |  | 3143 | GDP-D-114 | 1 | road | 36105 |  | 0.66 | 361 |  | M/S Udhya Enterprize |  |  | GDP-D-114 | 60 | 0
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of road from Kondalbag Pukur Par to Sarkar Market via Bhuiyan Bari Jame Mosque road (Ch. 2550-3050m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 127/10-11) ,Package No. UNR-GDP-D-141 |  | 3144 | GDP-D-141 | 1 | road | 36105 |  | 0.5 | 361 | 2011-07-08 | M/S. Urmi Enterprise | 2011-03-09 |  | GDP-D-141 | 85 | 0 | 2011-03-09
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Part-A: Improvement of Nabinagar-Kaliakoair RHD (Savar Metal)-Sreepur Kaborsthan road (Ch. 00-962m) & Part-B: Construction of 500mm Span U-Drain at Ch. 650m same road under Savar Upazila, District-Dhaka. (Estimate No. 147/10-11), Package No. UNR-GDP-D-142 |  | 3145 | GDP-D-142 | 1 | road | 36105 |  | 0.96 | 361 | 2011-07-23 | M/S. Erfan Cons: | 2011-03-20 |  | GDP-D-142 | 65 | 0 | 2011-03-20
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Improvement of Nama Konapara Jalus House- Jolhash House Road . (Ch. 00-665m) |  | 3146 | GDP-D-159 | 1 | road | 36105 |  | 0.67 | 361 | 2011-07-16 | M/S. Miah Trader | 2011-04-11 |  | GDP-D-159 | 50 | 0 | 2011-04-11
8 |  |  | Union Road & Other Infrastructure Development Project: Dhaka, Narayanganj, Munshiganj, Gazipur, Narshingdi & Manikganj District | UNR-GDP | Part: A: Improvement of Road form of Satter Hazi (Pucca road) to House of Fazal at Purbo Kaltasuti Road (Ch. 00-350m), Part: B: Improvement of Purbo Kaltasuti Anwar House (BKSP Wall) to House of Kohinoor Road (Ch. 00-180m) |  | 3147 | GDP-D-161 | 1 | road | 36105 |  | 0.35 | 361 | 2011-07-16 | M/S. Miah Trader | 2011-04-17 |  | GDP-D-161 | 20 | 0 | 2011-04-17
9 |  |  | GDP-3, Greater Dhaka Rural Infrastructure Improvement Project-3 | GDP-3 | Improvement of Kobirpur BazarShimulia UP via Baidgaon High School Road by RCC Ch. 2850-3700m under Upazila Savar District Dhaka. Road ID no 326723028 B. Improvement of Mograkanda Poultry firm-Solaimarket via H/O. Ansar Ali road Ch. 00-625m under Upazila S |  | 3148 | GDP-3/D-19 | 1 | road | 36105 | 326723028 | 1.76 | 361 |  |  |  |  | GDP-3/D-19 | 0 | 0
9 |  |  | GDP-3, Greater Dhaka Rural Infrastructure Improvement Project-3 | GDP-3 | a Improvement of Kaisharchar-Nonder Khamar Kheaghat Road Kaisharchar pucca road via Domrakanda madrasha Nonder Khamar Ch. 00 to 1000m under Upazila Savar District Dhaka. Road ID no 326724270. Total salvage amount Tk. 348995.00 b Improvement of Chunarchar |  | 3149 | GDP-3/D-30 | 1 | road | 36105 | 326724270 | 1 | 361 |  |  |  |  | GDP-3/D-30 | 0 | 0
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Firingikanda Kabarsthan. Union: Bhakurta, Latitude: 23.7499, Longitude: 90.2606 |  | 3152 | GSIDP/DHK/DW-11 | 10 | others | 36105 |  |  | 361 | 2018-08-04 | M/S. Ruma Enterprise | 2018-06-06 |  | GSIDP/DHK/DW-11 | 100 | 1 | 2018-06-06 |  | Latitude: 23.7499, Longitude: 90.2606
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Aminbazar Kendrio Kabarsthan. Union: Aminbazar, Latitude: 23.7826, Longitude: 90.3284 |  | 3153 | GSIDP/DHK/DW-12 | 10 | others | 36105 |  |  | 361 | 2018-08-04 | M/S. Ruma Enterprise | 2018-06-06 |  | GSIDP/DHK/DW-12 | 100 | 1 | 2018-06-06 |  | Latitude: 23.7826, Longitude: 90.3284
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Jadurchar Play Ground. Union: Tetuljhora, Latitude: 23.7905, Longitude: 90.2803 |  | 3154 | GSIDP/DHK/DW-13 | 10 | others | 36105 |  |  | 361 | 2018-08-16 | M/S. Sumon Enterprise Prop: Md. Liakat Hossain | 2018-06-17 |  | GSIDP/DHK/DW-13 | 100 | 1 | 2018-06-17 |  | Latitude: 23.7905, Longitude: 90.2803
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Sree Sree Rammkrishno & Ponchaboti Mondir. Union: Savar Pourashava, Latitude: 23.8476, Longitude: 90.2484 |  | 3155 | GSIDP/DHK/DW-14 | 10 | others | 36105 |  |  | 361 | 2018-08-05 | M/S. Saba Enterprise | 2018-06-07 |  | GSIDP/DHK/DW-14 | 100 | 1 | 2018-06-07 |  | Latitude: 23.8476, Longitude: 90.2484
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Baitul Najat Talbag Kabarsthan Jame Mosque. Union: Savar Pourashava, Latitude: 23.8376, Longitude: 90.2581 |  | 3156 | GSIDP/DHK/DW-15 | 10 | others | 36105 |  |  | 361 | 2018-08-05 | M/S. Saba Enterprise | 2018-06-07 |  | GSIDP/DHK/DW-15 | 100 | 1 | 2018-06-07 |  | Latitude: 23.8376, Longitude: 90.2581
11 |  |  | EUCP, Extension of Upazila Complex Project (EUCP). (2nd Revised) | EUCP | Construction of Upazila Complex Extention Building & Hall Room |  | 3162 | PWA-UZC- Savar-99 | 4 | administrative building | 36105 |  |  | 361 | 2013-03-07 | M/S Urmi Enterprise | 2012-03-07 |  | PWA-UZC- Savar-99 | 100 | 1 | 2012-03-07 | Building Qty: 2
12 |  |  | LBC, Construction of Large Bridges on Upazila and Union Roads Project. | LBC | a) Const. of RCC Bridge on Balivadhra GC-Dhamshona UP-Simulia UP road at Ch. 4465m (ID No.: 326723025). |  | 3164 | PD CLBUURP, W-136 | 2 | bridge/culvert | 36105 |  | 66 | 361 | 2013-03-14 | Shikder Enterprise | 2011-09-08 |  | PD CLBUURP, W-136 | 100 | 1 | 2011-09-08
12 |  |  | LBC, Construction of Large Bridges on Upazila and Union Roads Project. | LBC | c) Remaining work for Const. of RCC Bridge on Balivadhra GC-Dhamshona UP-Simulia UP road at Ch. 4465m (ID No.: 326723025). |  | 3165 | PD CLBUURP, W-136A | 2 | bridge/culvert | 36105 |  |  | 361 |  | M/S.Sayed & Brothers |  |  | PD CLBUURP, W-136A | 0 | 0
12 |  |  | LBC, Construction of Large Bridges on Upazila and Union Roads Project. | LBC | Const. of PSC Girder Bridge on Munsurbag- Gazibari- Chandon Teki road of Simulia UP at ch.3250m. |  | 3166 | PD CLBUURP, W-305 | 2 | bridge/culvert | 36105 |  | 90 | 361 |  |  |  |  | PD CLBUURP, W-305 | 0 | 0
13 |  |  | IARP | IARP | Improvement of i) Approach road at Beraid HZ. Abul Khalek house to School (Ch. 00-345m) & ii) Toibpur Dewan Iddrish College to Shafina Poultry Firm Culvert approach (Ch. 0-455m) under Savar Upazila, District-Dhaka. (Estimate No. 46/11-12) |  | 3168 | IARP/DHK-08 | 1 | road | 36105 |  |  | 361 |  |  |  |  | IARP/DHK-08 | 0 | 0
14 |  |  | RIIP-2 | RIIP-2 | Improvement of Aricha Boliapur Bongaon UP (Konda Bazar)-Chakulia Bazar road, (Ch. 0+000Km to 4+881 Km), Upazila: Savar. |  | 3169 | W-DHAK-Savar-UNR-08-05 | 1 | road | 36105 |  | 4.88 | 361 | 2011-09-27 | M/S. Nipa Enterprise | 2009-01-14 |  | W-DHAK-Savar-UNR-08-05 | 100 | 1 | 2009-01-14 | Road- 4.881 km Bridge- .75m
14 |  |  | RIIP-2 | RIIP-2 | Improvement of Dhaka Aricha RHD at 22 Mile-Shimulia Road via nalam (ch. 2915-6000m) upazila Savar, Dist.- Dhaka |  | 3170 | W-DHAK-Savar-UZR-09-77(a) | 1 | road | 36105 |  | 3.09 | 361 | 2011-06-07 | Delco Engg. & Reduan Builders (JV) | 2010-06-07 |  | i) W-DHAK-Savar-UZR-09-77(a) | 40 | 0 | 2010-06-07
14 |  |  | RIIP-2 | RIIP-2 | Improvement of Dhaka Aricha RHD at 22 Mile-Shimulia Road via nalam (ch. 6000-7658m)connect vararia UPC(ch.00-1003m) upazila Savar, Dist.- Dhaka |  | 3171 | W-DHAK-Savar-UZR-09-77(b) | 1 | road | 36105 |  | 2.69 | 361 | 2011-06-29 | M/S. Geneva International & Badhan Traders (JV) | 2010-06-29 |  | ii) W-DHAK-Savar-UZR-09-77(b) | 60 | 0 | 2010-06-29
1 |  |  | City Region Development Project (1st revised) | CRDP | Impprovement of Road and Drain in Savar Pourashava |  | 3008 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-2 | 1 | road | 36105 |  | 6.69 | 361 | 2016-03-28 | M/S Jemin Corporation | 2015-03-29 |  | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-2 | 100 | 1 | 2015-03-29
2 |  |  | Construction of Upazilla Muktijoddha Complex(1st Revised) | CUMCP | Construction of Muktijoddha Complex Building in Shibalaya Upazila , Dist: Manikganj. |  | 3009 | UMC/MAN/SHI/ 15/C-237 | 4 | administrative building | 36606 |  |  | 366 | 2018-01-26 | M/S.Debesh Traders | 2016-07-26 |  | UMC/MAN/SHI/ 15/C-237 | 0 | 0 | 2016-07-26 | Land disput
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Shimulia (Afsar Chairman house more)-Bara Butuni bazar road by BC (Ch. 00-1000m) (ID No. 356784038) |  | 3058 | IRIDP/ Mnk/W-3 | 1 | road | 36606 | 356784038 | 1 | 366 | 2012-03-20 | M/S. Mona Traders | 2010-10-11 |  | IRIDP/ Mnk/W-3 | 100 | 1 | 2010-10-11 | Final
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Shimulia UP office (Darber sharif more) - Diarchar Sakrail bazar road by BC (Ch. 650-1650m) and same road for Construction of one No 1x4.30x3.60m RCC box culvert at ch., 1435m (ID No. 356783004) |  | 3059 | IRIDP/ Mnk/W-28 | 1 | road | 36606 | 356783004 | 1 | 366 | 2013-01-31 | M/S. Sarnamoni fish & Co. | 2011-03-21 |  | IRIDP/ Mnk/W-28 | 100 | 1 | 2011-03-21 | Final
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Dhaka-Aricha NHW (Moshuria)-Barotia UP office (Ghior) via Mouhali Bazar road (Ch. 670-1455m) (ID No.356784014) |  | 3060 | IRIDP/ Mnk/W-30 | 1 | road | 36606 | 356784014 | 0.79 | 366 | 2012-11-29 | M/S. Pervez Enterprise | 2011-05-31 |  | IRIDP/ Mnk/W-30 | 100 | 1 | 2011-05-31 | Final
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Shimulia-(Afsar Chairman’s house more)-Boro Butuni Bazar road (Ch. 1000-2500m) (ID No.356784038) |  | 3061 | IRIDP/ Mnk/W-27 | 1 | road | 36606 | 356784038 | 1.5 | 366 | 2013-06-10 | M/S. Rana Enterprise | 2011-03-21 |  | IRIDP/ Mnk/W-27 | 100 | 1 | 2011-03-21 | Final
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Shibalaya UP Office (Oxford Academy)-Teota UP Office via Jamduara bazar road at (Ch. 00-1000m) under Shibalaya Upazila, Dist: Manikgonj (ID No. 356783009) |  | 3062 | IRIDP/ Mnk/W-47 | 1 | road | 36606 | 356783009 | 1 | 366 | 2013-05-21 | M/S. Debsh Traders | 2012-08-08 |  | IRIDP/ Mnk/W-47 | 100 | 1 | 2012-08-08 | Final
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Dhaka-Aricha NHW (Moshuria)-Barotia UP office (Ghior) via Mouhali Bazar road by HBB (Ch. 1455-2330m) (ID No.356784014) |  | 3063 | IRIDP/ Mnk/W-32 | 1 | road | 36606 | 356784014 | 0.88 | 366 | 2013-02-28 | M/S. Hera Corporation | 2011-07-25 |  | IRIDP/ Mnk/W-32 | 100 | 1 | 2011-07-25 | Final
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Dhaka-Aricha NHW (Aricha ghat)-Nali GC road at (Ch. 3550-4288m & 5023-5160m) under Shibalaya Upazila, Dist: Manikgonj (ID No. 356782009) |  | 3064 | IRIDP/ Mnk/W-46 | 1 | road | 36606 | 356782009 | 0.88 | 366 | 2013-06-26 | M/S. M.A Quddus | 2012-04-22 |  | IRIDP/ Mnk/W-46 | 100 | 1 | 2012-04-22
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Improvement of Dashchira Halipad-Satter Master house via Shangbadik Motiur Rahman House & Munshi bari road (Ch. 00-1250m) (ID No.356784038) |  | 3065 | IRIDP/ Mnk/W-33 | 1 | road | 36606 | 356784038 | 1.25 | 366 | 2013-05-30 | M/S. Al-Amin Enterprise | 2011-07-25 |  | IRIDP/ Mnk/W-33 | 75 | 0 | 2011-07-25 | On going
3 |  |  | Important Rural Infrastructure Development Project on Priority Basis (IRIDP-II) | IRIDP | Tree plantation of Shimulia (Afsar chairman house more)-Boro Butuni road at ch. 00-2500m (ID No. 356784038) under Shibalaya Upazila, Dist: Manikgonj |  | 3066 | IRIDP/ Mnk/TP-57 | 1 | road | 36606 | 356784038 | 2.5 | 366 |  | L.C.S |  |  | IRIDP/ Mnk/TP-57 | 0 | 0 |  | Contract under prosses
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | (a)Improvement of Jaforganj GC (Dhushar)-Ghior GC via Nayabari bazar Bardhamankandi, Bhorrah bz & Thakurkandi GPS road from ch.1480-2556m (b) Construction of 01 no 1x2.00x2.00m culvert at ch 1765m on the same road. |  | 3070 | IRIDP-2/ Mnk/DW-37 | 1 | road | 36606 | 356784001 | 1.08 | 366 | 2017-08-18 | M/S. Al-Mamun Traders | 2016-04-26 |  | IRIDP-2/ Mnk/DW-37 | 35 | 0 | 2016-04-26 | on going
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | Improvement of Dhaka Aricha NHW (Falsatia)-Machain GC Via Sakrail Bazar Road from Ch.3115-4350m Under Shibalaya Upazila,Dist:Manikganj. |  | 3071 | IRIDP-2/ Mnk/DW-50 | 1 | road | 36606 | 356782010 | 1.24 | 366 | 2017-08-24 | M/S MM Bricks | 2016-10-16 |  | IRIDP-2/ Mnk/DW-50 | 20 | 0 | 2016-10-16 | On going
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | Improvement of Arua UP office -Machain GC Via Shaljana Road from Ch.00-1000m) Under Shibalaya Upazila,Dist:Manikganj. |  | 3072 | IRIDP-2/ Mnk/DW-51 | 1 | road | 36606 | 356783007 | 1 | 366 | 2017-08-28 | M/S Raka Enterprise, Manikganj | 2016-09-28 |  | IRIDP-2/ Mnk/DW-51 | 50 | 0 | 2016-09-28 | on going
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | (a)Improvement of Amdala Bazar-Tarail Bazar Bridge Via Maniknagar Road from Ch.2960-4160m Under Shibalaya Upazila,Dist:Manikganj. (b)Construction of 02 Nos 1x2.00x2.00m Culvert at Ch.3004 & 3334m on the same Road. (c)Construction of 01 Nos 1x2.50x2.00m Culvert at Ch.3600m on the same |  | 3073 | IRIDP-2/ Mnk/DW-57 | 1 | road | 36606 | 356784009 | 1.2 | 366 | 2017-10-03 | M/S Reba Construction Manikganj | 2017-01-03 |  | IRIDP-2/ Mnk/DW-57 | 30 | 0 | 2017-01-03 | on going
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | Improvement of Road from Ulail UP office (Rupsha) - Upazila H/Q (Tepra) road from ch. 00-900m Under Shibalaya Upazila, Dist:Manikganj. |  | 3074 | IRIDP-2/ Mnk/DW-58 | 1 | road | 36606 | 356783005 | 0.9 | 366 | 2017-08-05 | M/S. Israfil Traders | 2017-01-30 |  | IRIDP-2/ Mnk/DW-58 | 0 | 0 | 2017-01-30
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | Improvement of Road from Hazirbadha Botagash- Nobogram LGED Bridge via Natun Foridpur road from ch. 1650-2280m Under Shibalaya Upazila, Dist:Manikganj. |  | 3075 | IRIDP-2/ Mnk/DW-59 | 1 | road | 36606 | 356784019 | 0.63 | 366 | 2017-08-06 | M/S Hemal Traders, Garpara, Manikganj. | 2017-01-31 |  | IRIDP-2/ Mnk/DW-59 | 0 | 0 | 2017-01-31
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | Improvement of Road from Nilgram - Tawakhali via kodalia Primary School road from ch. 347-1100m Under Shibalaya Upazila, Dist:Manikganj. |  | 3076 | IRIDP-2/ Mnk/DW-60 | 1 | road | 36606 | 356784024 | 0.75 | 366 | 2017-08-06 | M/S Hemal Traders, Garpara, Manikganj. | 2017-01-31 |  | IRIDP-2/ Mnk/DW-60 | 0 | 0 | 2017-01-31
4 |  |  | Important Rural Infrastructure Development Project On Priority Basis. | IRIDP-2 | (a) Improvement of Dhaka-Aricha NHW (Khodratpara) Ekhlas Pir House to Nanno house Via Mr. mannan Chairman House Road from Ch.00-472m) Under Shibalaya Upazila,Dist:Manikganj. (b) Improvement of Khudra Tepra Ekhlas Pir SB House (Start From Mannan House) -Jalal House Ekhlas Pir House to Nanno house Via Mr. mannan Chairman House Road from Ch.250-750m) Under Shibalaya Upazila,Dist:Manikganj. |  | 3077 | IRIDP-2/ Mnk/DW-72 | 1 | road | 36606 | 356785094.3568 | 0.97 | 366 | 2018-01-16 | M/S. Twin Trade | 2017-05-17 |  | IRIDP-2/ Mnk/DW-72 | 0 | 0 | 2017-05-17
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | a) Teota UP Office-Jhafargonj GC (Poila) road |  | 3084 | RTIP-II/MAN/RPM-122 | 1 | road | 36606 |  | 5.71 | 366 | 2015-05-04 | Saleh and Brothers | 2014-03-12 |  | RTIP-II/MAN/RPM-122 | 100 | 1 | 2014-03-12 | Final
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | Mohadebpur-Zitka GC via Gongasagar Road. |  | 3085 | RTIP-II/MAN/RPM-222 | 1 | road | 36606 |  | 9.11 | 366 | 2016-08-25 | M/S. Niaz Traders | 2015-07-01 |  | RTIP-II/MAN/RPM-222 | 100 | 1 | 2015-07-01 | Final
5 |  |  | RTIP-2, Second Rural Transport Improvement Project | RTIP-2 | Uthali-Jaforgonj GC Road. |  | 3086 | RTIP-II/MAN/RPM-302 | 1 | road | 36606 |  | 7 | 366 | 2017-06-14 | M/S. ANIK TRADING CORPORATION | 2016-07-10 |  | RTIP-II/MAN/RPM-302 | 100 | 1 | 2016-07-10 | Final
6 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Construction of 54.00m Long RCC Girder Bridge on Baradia (Moynar gudara) Nayabari Road at Ch.70m Under Shibalaya Upazila,Dist:Manikganj.(ID No. 356784030) |  | 3091 | GDP-II/MAN/ Ghi/W(B)-58 | 1 | road | 36606 | 356784030 |  | 366 | 2017-08-30 | M/s. Debesh Traders | 2016-02-29 |  | GDP-II/MAN/ Ghi/W(B)-58 | 80 | 0 | 2016-02-29 | on going
6 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of Kaccol- Intajganj Via Jamunabad Road at Ch.1500 -1850m.Under Shibalaya Upazila, Dist: Manikganj.(ID No. 356784012) |  | 3092 | GDP-II/MAN/ Ghi/W(R)-74 | 1 | road | 36606 | 356784012 | 0.35 | 366 | 2017-07-14 | M/s.Al-Mamun Traders | 2016-03-14 |  | GDP-II/MAN/ Ghi/W(R)-74 | 75 | 0 | 2016-03-14
6 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishoreganj Districts | GDP-2 | Improvement of Road Starting from Bara Butuni Bazar - Kachidhara Battala via Basepara High School road at Ch.00 -869m.Under Shibalaya Upazila, Dist: Manikganj.(ID No. 356784035) |  | 3093 | GDP-II/MAN/ Ghi/W(R)-79 | 1 | road | 36606 | 356784035 | 0.87 | 366 | 2017-08-25 | M/s.Al-Mamun Traders | 2016-04-26 |  | GDP-II/MAN/ Ghi/W(R)-79 | 20 | 0 | 2016-04-26 | on going
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | MALUCHI School Additional Room |  | 3106 | PEDP-III/MNK/SHI/2011-12/W2.0551 | 3 | school building | 36606 |  |  | 366 | 2014-01-06 | M/S Rana Enterprise | 2013-01-13 |  | PEDP-III/MNK/SHI/2011-12/W2.0551 | 100 | 1 | 2013-01-13
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | KATTHALIYA School Additional Room |  | 3107 | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | 3 | school building | 36606 |  |  | 366 |  | M/S Sthapati Construction | 2014-06-25 |  | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | 0 | 0 | 2014-06-25
7 |  |  | Third Primary Education Development Program (PEDP-III) | PEDP-3 | BUTUNI School Major Maintenance |  | 3108 | PEDP-III/MNK/SHI/2011-12/W3.0333 | 3 | school building | 36606 |  |  | 366 | 2013-07-06 | M/S Rana Enterprise | 2013-01-13 |  | PEDP-III/MNK/SHI/2011-12/W3.0333 | 100 | 1 | 2013-01-13
9 |  |  | GDP-3, Greater Dhaka Rural Infrastructure Improvement Project-3 | GDP-3 | Improvement of Ulail UP Office (Rupsa)-Upazila H/Q (Tepra) Road from CH. 1270-2700 under Shibalaya Upazila, District Manikganj. Road ID No 3576783005 |  | 3150 | GDP3/MA -20 | 1 | road | 36606 | 3576783005 | 1.43 | 366 |  |  |  |  | GDP3/MA -20 | 0 | 0
9 |  |  | GDP-3, Greater Dhaka Rural Infrastructure Improvement Project-3 | GDP-3 | Rehabilitation of Shimulia Afsar Chairman House more - Boro Butuni Bazar Road Ch.00 - 2500m Under Shibalaya Upazila District Manikganj. Road ID No 356784038 |  | 3151 | GDP3/MA Reh-2 | 1 | road | 36606 | 356784038 | 2.5 | 366 | 2018-10-15 | M/s M. A. Quddus | 2018-05-16 |  | GDP3/MA Reh-2 | 100 | 1 | 2018-05-16
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of shibalaya central shasan ghat . Union: shibalaya, Latitude: 23.840258, Longitude: 89.799977 |  | 3157 | GSIDP/MNK/DW-8 | 10 | others | 36606 |  |  | 366 | 2018-11-11 | M/S. Meghna Builders | 2018-06-25 |  | GSIDP/MNK/DW-8 | 0 | 0 | 2018-06-25 |  | Latitude: 23.840258, Longitude: 89.799977
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Jhoriarbag graveyard. Union: shibalaya, Latitude: 23.808367, Longitude: 89.791533 |  | 3158 | GSIDP/MNK/DW-9 | 10 | others | 36606 |  |  | 366 | 2018-10-28 | M/S Tanvir Enterprise | 2018-06-10 |  | GSIDP/MNK/DW-9 | 100 | 1 | 2018-06-10 |  | Latitude: 23.808367, Longitude: 89.791533
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of East baulikanda sarbojonin kalimondir. Union: Arua, Latitude: 23.558321, Longitude: 89.653221 |  | 3159 | GSIDP/MNK/DW-10 | 10 | others | 36606 |  |  | 366 | 2018-11-11 | M/S. Meghna Builders | 2018-06-18 |  | GSIDP/MNK/DW-10 | 0 | 0 | 2018-06-18 |  | Latitude: 23.558321, Longitude: 89.653221
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Radhakantorpur Surbojanin Durga Mondir. Union: Utholy, Latitude: 23.8630, Longitude: 89.7936 |  | 3160 | GSIDP/MNK/DW-11 | 10 | others | 36606 |  |  | 366 | 2018-12-28 | MS. Tanvir Enterprise | 2018-09-06 |  | GSIDP/MNK/DW-11 | 10 | 0 | 2018-09-06 |  | Latitude: 23.8630, Longitude: 89.7936
10 |  |  | GSIDP, General Social Infrastructure Development Project | GSIDP | Improvement of Kesobpotty Jame Mosque. Union: Mohadebpur, Latitude: 23.8448, Longitude: 89.8473 |  | 3161 | GSIDP/MNK/SDW-12 | 10 | others | 36606 |  |  | 366 | 2019-01-05 | M/S. Simanta Enterprise | 2018-09-12 |  | GSIDP/MNK/SDW-12 | 0 | 0 | 2018-09-12 |  | Latitude: 23.8448, Longitude: 89.8473
11 |  |  | EUCP, Extension of Upazila Complex Project (EUCP). (2nd Revised) | EUCP | Construction of Upazila Complex Extention Building & Hall Room |  | 3163 | PWA-UZC- Shibalay-103 | 4 | administrative building | 36606 |  |  | 366 | 2016-09-15 | Starlite Services Limited | 2015-07-26 |  | PWA-UZC- Shibalay-103 | 100 | 1 | 2015-07-26 | Building Qty: 2
12 |  |  | LBC, Construction of Large Bridges on Upazila and Union Roads Project. | LBC | Const. of RCC Bridge on Dhaka-Aricha NHW (Shibrampur)-Machain GC via Rupsha road at Ch. 116150m (ID No.: 356782004). |  | 3167 | PD CLBUURP, W-170 | 1 | road | 36606 | 356782004 | 315 | 366 | 2013-09-30 | JV M/S nurul Islam and | 2011-02-07 |  | PD CLBUURP, W-170 | 100 | 1 | 2011-02-07

## Shivalay_Jalal
SL No. | Package No. | Package Name | Project Name | Schema_Type_id | Schema_Type_name | Lat-long | Road ID | Length of Road (Km) | Length of Bridge (M) | Building Qauntity (No) | Estimated Amount (Lac) | Name of Contractor | Contract Amount (Lac) | Date of Contract | Date of Commencement | Date of Completion | Physical Progress (%) | Financial Progress (Amt) | Financial Progress (%) | Date of Progress Update | Remarks
1 | PD CLBUURP, W-170 | Const. of RCC Bridge on Dhaka-Aricha NHW (Shibrampur)-Machain GC via Rupsha road at Ch. 116150m (ID No.: 356782004). | LBC | 1 | road |  | 356782004 | 315 |  |  | 326.05 | JV M/S nurul Islam and | 336.05 |  | 2011-02-07 | 2013-09-30 | 100
2 | UMC/MAN/SHI/ 15/C-237 | Construction of Muktijoddha Complex Building in Shibalaya Upazila , Dist: Manikganj. | CUMCP | 4 | administrative building |  |  |  |  | 0 | 217.71 | M/S.Debesh Traders | 180.69 | 2016-07-26 | 2016-07-26 | 2018-01-26 | 0 | 0 | 0 | 2017-07-05 | Land disput
3 | PWA-UZC- Shibalay-103 | Construction of Upazila Complex Extention Building & Hall Room | EUCP | 4 | administrative building | [5 empty] | 432.29 | Starlite Services Limited | 535.62 |  | 2015-07-26 | 2016-09-15 | 100 |  |  |  | Building Qty: 2
4 | GSIDP/MNK/DW-8 | Improvement of shibalaya central shasan ghat . Union: shibalaya, Latitude: 23.840258, Longitude: 89.799977 | GSIDP | 10 | others | Latitude: 23.840258, Longitude: 89.799977 |  |  |  |  | 6.5 | M/S. Meghna Builders | 6.18 |  | 2018-06-25 | 2018-11-11 | 0
5 | GSIDP/MNK/DW-9 | Improvement of Jhoriarbag graveyard. Union: shibalaya, Latitude: 23.808367, Longitude: 89.791533 | GSIDP | 10 | others | Latitude: 23.808367, Longitude: 89.791533 |  |  |  |  | 7 | M/S Tanvir Enterprise | 6.65 |  | 2018-06-10 | 2018-10-28 | 100
6 | GSIDP/MNK/DW-10 | Improvement of East baulikanda sarbojonin kalimondir. Union: Arua, Latitude: 23.558321, Longitude: 89.653221 | GSIDP | 10 | others | Latitude: 23.558321, Longitude: 89.653221 |  |  |  |  | 6.5 | M/S. Meghna Builders | 6.18 |  | 2018-06-18 | 2018-11-11 | 0
7 | GSIDP/MNK/DW-11 | Improvement of Radhakantorpur Surbojanin Durga Mondir. Union: Utholy, Latitude: 23.8630, Longitude: 89.7936 | GSIDP | 10 | others | Latitude: 23.8630, Longitude: 89.7936 |  |  |  |  | 10 | MS. Tanvir Enterprise | 9.5 |  | 2018-09-06 | 2018-12-28 | 10
8 | GSIDP/MNK/SDW-12 | Improvement of Kesobpotty Jame Mosque. Union: Mohadebpur, Latitude: 23.8448, Longitude: 89.8473 | GSIDP | 10 | others | Latitude: 23.8448, Longitude: 89.8473 |  |  |  |  | 10.92 | M/S. Simanta Enterprise | 10.38 |  | 2018-09-12 | 2019-01-05 | 0
9 | GDP3/MA -20 | Improvement of Ulail UP Office (Rupsa)-Upazila H/Q (Tepra) Road from CH. 1270-2700 under Shibalaya Upazila, District Manikganj. Road ID No 3576783005 | GDP-3 | 1 | road |  | 3576783005 | 1.43 |  |  | 114.71 |  | 0 |  |  |  | 0
10 | GDP3/MA Reh-2 | Rehabilitation of Shimulia Afsar Chairman House more - Boro Butuni Bazar Road Ch.00 - 2500m Under Shibalaya Upazila District Manikganj. Road ID No 356784038 | GDP-3 | 1 | road |  | 356784038 | 2.5 |  |  | 66.97 | M/s M. A. Quddus | 63.63 |  | 2018-05-16 | 2018-10-15 | 100
11 | IRIDP-2/ Mnk/DW-37 | (a)Improvement of Jaforganj GC (Dhushar)-Ghior GC via Nayabari bazar Bardhamankandi, Bhorrah bz & Thakurkandi GPS road from ch.1480-2556m (b) Construction of 01 no 1x2.00x2.00m culvert at ch 1765m on the same road. | IRIDP-2 | 1 | road |  | 356784001 | 1.08 | 2 |  | 4856137 | M/S. Al-Mamun Traders | 4882668.41 | 2016-04-26 | 2016-04-26 | 2017-08-18 | 35 | 1044000 |  | 2017-07-05 | on going
12 | IRIDP-2/ Mnk/DW-50 | Improvement of Dhaka Aricha NHW (Falsatia)-Machain GC Via Sakrail Bazar Road from Ch.3115-4350m Under Shibalaya Upazila,Dist:Manikganj. | IRIDP-2 | 1 | road |  | 356782010 | 1.24 |  | 0 | 7583506 | M/S MM Bricks | 6671418.09 | 2016-10-16 | 2016-10-16 | 2017-08-24 | 20 | 0 | 0 | 2017-07-05 | On going
13 | IRIDP-2/ Mnk/DW-51 | Improvement of Arua UP office -Machain GC Via Shaljana Road from Ch.00-1000m) Under Shibalaya Upazila,Dist:Manikganj. | IRIDP-2 | 1 | road |  | 356783007 | 1 |  | 0 | 7242225 | M/S Raka Enterprise, Manikganj | 6764257.11 | 2016-09-28 | 2016-09-28 | 2017-08-28 | 50 | 0 | 0 | 2017-07-05 | on going
14 | IRIDP-2/ Mnk/DW-57 | (a)Improvement of Amdala Bazar-Tarail Bazar Bridge Via Maniknagar Road from Ch.2960-4160m Under Shibalaya Upazila,Dist:Manikganj. (b)Construction of 02 Nos 1x2.00x2.00m Culvert at Ch.3004 & 3334m on the same Road. (c)Construction of 01 Nos 1x2.50x2.00m Culvert at Ch.3600m on the same | IRIDP-2 | 1 | road |  | 356784009 | 1.2 | 6.5 | 0 | 8800219 | M/S Reba Construction Manikganj | 7393005.52 | 2017-01-03 | 2017-01-03 | 2017-10-03 | 30 | 0 | 0 | 2017-07-05 | on going
15 | IRIDP-2/ Mnk/DW-58 | Improvement of Road from Ulail UP office (Rupsha) - Upazila H/Q (Tepra) road from ch. 00-900m Under Shibalaya Upazila, Dist:Manikganj. | IRIDP-2 | 1 | road |  | 356783005 | 0.9 |  | 0 | 5929537 | M/S. Israfil Traders | 5354354.85 | 2017-01-30 | 2017-01-30 | 2017-08-05 | 0 | 0 | 0 | 2017-07-05
16 | IRIDP-2/ Mnk/DW-59 | Improvement of Road from Hazirbadha Botagash- Nobogram LGED Bridge via Natun Foridpur road from ch. 1650-2280m Under Shibalaya Upazila, Dist:Manikganj. | IRIDP-2 | 1 | road |  | 356784019 | 0.63 |  | 0 | 4582357 | M/S Hemal Traders, Garpara, Manikganj. | 4168853.08 | 2017-01-31 | 2017-01-31 | 2017-08-06 | 0 | 0 | 0 | 2017-07-05
17 | IRIDP-2/ Mnk/DW-60 | Improvement of Road from Nilgram - Tawakhali via kodalia Primary School road from ch. 347-1100m Under Shibalaya Upazila, Dist:Manikganj. | IRIDP-2 | 1 | road |  | 356784024 | 0.75 |  | 0 | 4923591 | M/S Hemal Traders, Garpara, Manikganj. | 4484916.03 | 2017-01-31 | 2017-01-31 | 2017-08-06 | 0 | 0 | 0 | 2017-07-05
18 | IRIDP-2/ Mnk/DW-72 | (a) Improvement of Dhaka-Aricha NHW (Khodratpara) Ekhlas Pir House to Nanno house Via Mr. mannan Chairman House Road from Ch.00-472m) Under Shibalaya Upazila,Dist:Manikganj. (b) Improvement of Khudra Tepra Ekhlas Pir SB House (Start From Mannan House) -Jalal House Ekhlas Pir House to Nanno house Via Mr. mannan Chairman House Road from Ch.250-750m) Under Shibalaya Upazila,Dist:Manikganj. | IRIDP-2 | 1 | road |  | 356785094.3568 | 0.97 |  | 0 | 7016874 | M/S. Twin Trade | 6972331.7 | 2017-05-17 | 2017-05-17 | 2018-01-16 | 0 | 0 | 0 | 2017-07-05
19 | IRIDP/ Mnk/W-3 | Improvement of Shimulia (Afsar Chairman house more)-Bara Butuni bazar road by BC (Ch. 00-1000m) (ID No. 356784038) | IRIDP | 1 | road |  | 356784038 | 1 |  |  | 4808158 | M/S. Mona Traders | 4567750.1 |  | 2010-10-11 | 2012-03-20 | 100 |  |  |  | Final
20 | IRIDP/ Mnk/W-28 | Improvement of Shimulia UP office (Darber sharif more) - Diarchar Sakrail bazar road by BC (Ch. 650-1650m) and same road for Construction of one No 1x4.30x3.60m RCC box culvert at ch., 1435m (ID No. 356783004) | IRIDP | 1 | road |  | 356783004 | 1 |  |  | 5968262 | M/S. Sarnamoni fish & Co. | 5669848.9 |  | 2011-03-21 | 2013-01-31 | 100 |  |  |  | Final
21 | IRIDP/ Mnk/W-30 | Improvement of Dhaka-Aricha NHW (Moshuria)-Barotia UP office (Ghior) via Mouhali Bazar road (Ch. 670-1455m) (ID No.356784014) | IRIDP | 1 | road |  | 356784014 | 0.79 |  |  | 3737141 | M/S. Pervez Enterprise | 3550283.95 |  | 2011-05-31 | 2012-11-29 | 100 |  |  |  | Final
22 | IRIDP/ Mnk/W-27 | Improvement of Shimulia-(Afsar Chairman’s house more)-Boro Butuni Bazar road (Ch. 1000-2500m) (ID No.356784038) | IRIDP | 1 | road |  | 356784038 | 1.5 |  |  | 7422095 | M/S. Rana Enterprise | 7050990.25 |  | 2011-03-21 | 2013-06-10 | 100 |  |  |  | Final
23 | IRIDP/ Mnk/W-47 | Improvement of Shibalaya UP Office (Oxford Academy)-Teota UP Office via Jamduara bazar road at (Ch. 00-1000m) under Shibalaya Upazila, Dist: Manikgonj (ID No. 356783009) | IRIDP | 1 | road |  | 356783009 | 1 |  |  | 5072975 | M/S. Debsh Traders | 5783385.86 |  | 2012-08-08 | 2013-05-21 | 100 |  |  |  | Final
24 | IRIDP/ Mnk/W-32 | Improvement of Dhaka-Aricha NHW (Moshuria)-Barotia UP office (Ghior) via Mouhali Bazar road by HBB (Ch. 1455-2330m) (ID No.356784014) | IRIDP | 1 | road |  | 356784014 | 0.88 |  |  | 3759171 | M/S. Hera Corporation | 3571212.45 |  | 2011-07-25 | 2013-02-28 | 100 |  |  |  | Final
25 | IRIDP/ Mnk/W-46 | Improvement of Dhaka-Aricha NHW (Aricha ghat)-Nali GC road at (Ch. 3550-4288m & 5023-5160m) under Shibalaya Upazila, Dist: Manikgonj (ID No. 356782009) | IRIDP | 1 | road |  | 356782009 | 0.88 |  |  | 6424960 | M/S. M.A Quddus | 6739783.23 |  | 2012-04-22 | 2013-06-26 | 100
26 | IRIDP/ Mnk/W-33 | Improvement of Dashchira Halipad-Satter Master house via Shangbadik Motiur Rahman House & Munshi bari road (Ch. 00-1250m) (ID No.356784038) | IRIDP | 1 | road |  | 356784038 | 1.25 |  |  | 4599370 | M/S. Al-Amin Enterprise | 4599370 |  | 2011-07-25 | 2013-05-30 | 75 |  |  |  | On going
27 | IRIDP/ Mnk/TP-57 | Tree plantation of Shimulia (Afsar chairman house more)-Boro Butuni road at ch. 00-2500m (ID No. 356784038) under Shibalaya Upazila, Dist: Manikgonj | IRIDP | 1 | road |  | 356784038 | 2.5 |  |  | 275700 | L.C.S | 0 |  |  |  | 0 |  |  |  | Contract under prosses
28 | GDP-II/MAN/ Ghi/W(B)-58 | Construction of 54.00m Long RCC Girder Bridge on Baradia (Moynar gudara) Nayabari Road at Ch.70m Under Shibalaya Upazila,Dist:Manikganj.(ID No. 356784030) | GDP-2 | 1 | road |  | 356784030 |  | 54 |  | 213.36 | M/s. Debesh Traders | 181.96 | 2016-02-29 | 2016-02-29 | 2017-08-30 | 80 | 158.5 |  | 2017-07-05 | on going
29 | GDP-II/MAN/ Ghi/W(R)-74 | Improvement of Kaccol- Intajganj Via Jamunabad Road at Ch.1500 -1850m.Under Shibalaya Upazila, Dist: Manikganj.(ID No. 356784012) | GDP-2 | 1 | road |  | 356784012 | 0.35 |  |  | 28.99 | M/s.Al-Mamun Traders | 28.48 | 2016-03-14 | 2016-03-14 | 2017-07-14 | 75 | 14.08 |  | 2017-07-05
30 | GDP-II/MAN/ Ghi/W(R)-79 | Improvement of Road Starting from Bara Butuni Bazar - Kachidhara Battala via Basepara High School road at Ch.00 -869m.Under Shibalaya Upazila, Dist: Manikganj.(ID No. 356784035) | GDP-2 | 1 | road |  | 356784035 | 0.87 |  |  | 57.87 | M/s.Al-Mamun Traders | 55.84 | 2016-04-26 | 2016-04-26 | 2017-08-25 | 20 |  |  | 2017-07-05 | on going
31 | RTIP-II/MAN/RPM-122 | a) Teota UP Office-Jhafargonj GC (Poila) road | RTIP-2 | 1 | road |  |  | 5.71 |  |  | 114.39 | Saleh and Brothers | 316.43 |  | 2014-03-12 | 2015-05-04 | 100 |  |  |  | Final
32 | RTIP-II/MAN/RPM-222 | Mohadebpur-Zitka GC via Gongasagar Road. | RTIP-2 | 1 | road |  |  | 9.11 |  |  | 417.51 | M/S. Niaz Traders | 379.11 |  | 2015-07-01 | 2016-08-25 | 100 |  |  |  | Final
33 | RTIP-II/MAN/RPM-302 | Uthali-Jaforgonj GC Road. | RTIP-2 | 1 | road |  |  | 7 |  |  | 244.42 | M/S. ANIK TRADING CORPORATION | 199.07 |  | 2016-07-10 | 2017-06-14 | 100 |  |  |  | Final
34 | PEDP-III/MNK/SHI/2011-12/W2.0551 | MALUCHI School Additional Room | PEDP-3 | 3 | school building | [5 empty] | 2993000 | M/S Rana Enterprise | 7241004.94 |  | 2013-01-13 | 2014-01-06 | 100
35 | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | KATTHALIYA School Additional Room | PEDP-3 | 3 | school building | [5 empty] | 3546000 | M/S Sthapati Construction | 6045284.14 |  | 2014-06-25 |  | 0
36 | PEDP-III/MNK/SHI/2011-12/W3.0333 | BUTUNI School Major Maintenance | PEDP-3 | 3 | school building | [5 empty] | 149532 | M/S Rana Enterprise | 657966.51 |  | 2013-01-13 | 2013-07-06 | 100

## Sheet1
|  | CRDP | LBC
ID | Name | LBC | CUMCP
1 | road | EUCP | EUCP
2 | bridge/culvert | GSIDP | GSIDP
3 | school building | GDP-3 | GDP-3
4 | administrative building | IRIDP-2 | IRIDP-2
5 | growth center/market | IRIDP | IRIDP
6 | cyclone shelter | IARP | GDP-2
7 | rural waterways and ghats | GDP-2 | RTIP-2
8 | water control structure | RTIP-2 | PEDP-3
10 | others | PEDP-3
21 | cannel/pond | UNR-GDP
22 | embankment
42 | goods
43 | drain

## Savar
SL No. | Package No. | Package Name | Project Name | Upazila Name | Road ID | Length of Road (Km) | Length of Bridge (M) | Building Qauntity (No) | Estimated Amount (Lac) | Name of Contractor | Contract Amount (Lac) | Date of Contract | Date of Commencement | Date of Completion | Physical Progress (%) | Financial Progress (Amt) | Financial Progress (%) | Date of Progress Update | Remarks
1 | CRDP/LGED/Savar/ ICB/2013/ W-01 | (a) Dhaka - Aricha Highway Ashulia GC Road (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) ; (b) Dhaka - Aricha Highway Ashulia GC Road side Drain and Cross Culverts (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m); (c) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road (Ch. 0.00 - 5770m); (d) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road side Drain & Cross Culverts (Ch. 0.00 - 5770m) | CRDP | Savar |  | 10.67 |  |  | 0 |  | 29588854.56 |  |  |  | 0
2 | CRDP/LGED/ DHK/ NCB/2013/ W-02 | (a) Re-construction of Road (Nabinagar - Kaliakoir RHD at Sreepur - Kashimpur GC Road (Ch. 0- 1500m); (b) Kuturia - Bogabari Bazar Road (Ch.0- 4570m); (c) Jamgora Bazzar - Chitrachali -Kandail-Katgora Bazzar Road (Ch.0 --3615); (d) Jamgora Chowrasha Bhadail via Bhadail Primary School Road (Ch.0+000 - 2420, link 0+000 - 0+067); (e) Bhadail Chowrasta Madar Textile via Anobic Shakti Commission road. (Ch.0+00-1+280m); (f) Nabinagor-Kaliakoir RHD road-Tongi EPZ road via Birds Garments & Gajirchat Aliya Madrasha. (ch.0+350-1+620m); (g) Kumkumary-Sadhupara road. (ch.0+00-2+300m); and (h) Dhalpur-Katgora road. (ch.0+00-1+525m) | CRDP | Savar |  | 18.53 |  |  | 0 |  | 181626943.69 |  |  |  | 0
3 | CRDP/LGED/Savar/ ICB/2013/W-01 | (a) Dhaka - Aricha Highway Ashulia GC Road (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m) ; (b) Dhaka - Aricha Highway Ashulia GC Road side Drain and Cross Culverts (Anwar Jung Road) (Ch. 0+000 - 4235m & Ch. 6435 to 7100m); (c) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road (Ch. 0.00 - 5770m); (d) Dhaka Aricha Road (RHD) at 20 Mile - Jirabo Bazar Yearpur UP Road side Drain & Cross Culverts (Ch. 0.00 - 5770m) | CRDP | Savar |  |  |  |  | 298238000 | Mir Akhtar Hossain Ltd. | 363135661.59 |  |  | 2014-07-15 | 40
4 | CRDP/LGED/Savar/ NCB/2013/W-02 | (a) Re-construction of Road (Nabinagar - Kaliakoir RHD at Sreepur - Kashimpur GC Road (Ch. 0- 1500m); (b) Kuturia - Bogabari Bazar Road (Ch.0- 4570m); (c) Jamgora Bazzar - Chitrachali -Kandail-Katgora Bazzar Road (Ch.0 --3615); (d) Jamgora Chowrasha Bhadail via Bhadail Primary School Road (Ch.0+000 - 2420, link 0+000 - 0+067); (e) Bhadail Chowrasta Madar Textile via Anobic Shakti Commission road. (Ch.0+00-1+280m); (f) Nabinagor-Kaliakoir RHD road-Tongi EPZ road via Birds Garments & Gajirchat Aliya Madrasha. (ch.0+350-1+620m); (g) Kumkumary-Sadhupara road. (ch.0+00-2+300m); and (h) Dhalpur-Katgora road. (ch.0+00-1+525m) | CRDP | Savar |  | 18.53 |  |  | 152210000 | Project Builders Ltd. (PBL) | 181626943.69 |  |  | 2014-09-25 | 20
5 | CRDP/LGED/DHK/ ICB/2013/W-01 | Improvement of Road and Drain in Ashulia, Savar | CRDP | Savar |  | 17.73 |  |  | 2982.39 | Mir Akhtar Hossain Ltd. | 3680.54 |  | 2013-07-16 | 2014-08-24 | 100
6 | CRDP/LGED/DHK/ NCB/2013/W-02 | Improvement of Road and Drain in Ashulia, Savar | CRDP | Savar |  | 17.26 |  |  | 1552.2 | Project Builders Ltd. (PBL) | 1715.08 |  | 2013-09-26 | 2014-10-04 | 100
7 | CRDP/LGED/ Savar/NCB/2014/ W-01 | Impprovement of Road and Drain in Savar Pourashava | CRDP | Savar |  | 10.74 |  |  | 1155.11 | M/S. Md. Jamil Iqbal | 1590.94 |  | 2015-02-26 | 2016-03-09 | 100
8 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-01 | Impprovement of Road and Drain in Savar Pourashava | CRDP | Savar |  | 6.73 |  |  | 950.36 | TI-SB (Jv) | 1203.94 |  | 2015-03-22 | 2016-03-21 | 100
9 | CRDP/LGED/ Savar/NCB/2014/W-02, Lot-2 | Impprovement of Road and Drain in Savar Pourashava | CRDP | Savar |  | 6.69 |  |  | 805.1 | M/S Jemin Corporation | 906.88 |  | 2015-03-29 | 2016-03-28 | 100
10 | PD CLBUURP, W-136 | a) Const. of RCC Bridge on Balivadhra GC-Dhamshona UP-Simulia UP road at Ch. 4465m (ID No.: 326723025). | LBC | Savar |  | 66 |  |  | 82.17 | Shikder Enterprise | 82.17 |  | 2011-09-08 | 2013-03-14 | 100
11 | PD CLBUURP, W-136A | c) Remaining work for Const. of RCC Bridge on Balivadhra GC-Dhamshona UP-Simulia UP road at Ch. 4465m (ID No.: 326723025). | LBC | Savar |  |  |  |  | 151.45 | M/S.Sayed & Brothers | 0 |  |  |  | 0
12 | PD CLBUURP, W-305 | Const. of PSC Girder Bridge on Munsurbag- Gazibari- Chandon Teki road of Simulia UP at ch.3250m. | LBC | Savar |  | 90 |  |  | 0 |  | 0 |  |  |  | 0
13 | PWA-UZC- Savar-99 | Construction of Upazila Complex Extention Building & Hall Room | EUCP | Savar |  |  |  |  | 346.19 | M/S Urmi Enterprise | 360.87 |  | 2012-03-07 | 2013-03-07 | 100 |  |  |  | Building Qty: 2
14 | GSIDP/DHK/DW-11 | Improvement of Firingikanda Kabarsthan. Union: Bhakurta, Latitude: 23.7499, Longitude: 90.2606 | GSIDP | Savar |  |  |  |  | 4 | M/S. Ruma Enterprise | 3.8 |  | 2018-06-06 | 2018-08-04 | 100
15 | GSIDP/DHK/DW-12 | Improvement of Aminbazar Kendrio Kabarsthan. Union: Aminbazar, Latitude: 23.7826, Longitude: 90.3284 | GSIDP | Savar |  |  |  |  | 10 | M/S. Ruma Enterprise | 9.5 |  | 2018-06-06 | 2018-08-04 | 100
16 | GSIDP/DHK/DW-13 | Improvement of Jadurchar Play Ground. Union: Tetuljhora, Latitude: 23.7905, Longitude: 90.2803 | GSIDP | Savar |  |  |  |  | 4 | M/S. Sumon Enterprise Prop: Md. Liakat Hossain | 3.8 |  | 2018-06-17 | 2018-08-16 | 100
17 | GSIDP/DHK/DW-14 | Improvement of Sree Sree Rammkrishno & Ponchaboti Mondir. Union: Savar Pourashava, Latitude: 23.8476, Longitude: 90.2484 | GSIDP | Savar |  |  |  |  | 30 | M/S. Saba Enterprise | 28.5 |  | 2018-06-07 | 2018-08-05 | 100
18 | GSIDP/DHK/DW-15 | Improvement of Baitul Najat Talbag Kabarsthan Jame Mosque. Union: Savar Pourashava, Latitude: 23.8376, Longitude: 90.2581 | GSIDP | Savar |  |  |  |  | 20 | M/S. Saba Enterprise | 19 |  | 2018-06-07 | 2018-08-05 | 100
19 | GDP-3/D-19 | Improvement of Kobirpur BazarShimulia UP via Baidgaon High School Road by RCC Ch. 2850-3700m under Upazila Savar District Dhaka. Road ID no 326723028 B. Improvement of Mograkanda Poultry firm-Solaimarket via H/O. Ansar Ali road Ch. 00-625m under Upazila S | GDP-3 | Savar |  | 1.76 |  |  | 202.64 |  | 0 |  |  |  | 0
20 | GDP-3/D-30 | a Improvement of Kaisharchar-Nonder Khamar Kheaghat Road Kaisharchar pucca road via Domrakanda madrasha Nonder Khamar Ch. 00 to 1000m under Upazila Savar District Dhaka. Road ID no 326724270. Total salvage amount Tk. 348995.00 b Improvement of Chunarchar | GDP-3 | Savar |  | 1 |  |  | 128.86 |  | 0 |  |  |  | 0
21 | IRIDP-2/DHK/DW-13 | Improvement of Dendabor (PBS)-Corapir Mazar road from Ch. 00-2013m. | IRIDP-2 | Savar |  | 2.01 |  |  | 147.9 | M/S. M.B Traders, Prop: Md.Masudur Rahman Khan | 132.85 |  | 2016-03-23 | 2017-01-31 | 100
22 | IRIDP-2/DHK/DW-14 | a) Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road from Ch. 3179-4044m.b) Construction of 01 no 0.900mx1.000m culvert at ch.3537m on the same road. | IRIDP-2 | Savar |  | 0.87 |  |  | 63.57 | M/S. M.B Traders, Prop: Md.Masudur Rahman Khan | 56.23 |  | 2016-03-23 | 2016-09-26 | 100
23 | IRIDP-2/DHK/DW-15 | Improvement of Jahangir Nagar Bhashani Hall-Dakshin Shindhuria Road from Ch. 500-1500m. | IRIDP-2 | Savar |  | 1 |  |  | 57.3 | M/S. Shahjahan Traders Prop: Mr. Shawkat Hossain | 52.85 |  | 2016-03-16 | 2016-11-12 | 100
24 | IRIDP/Dhk/W-90 | Improvement of Fulbaria Bazar to Harannagar Bridge road (Ch. 00-1210m) Tetuljhora UP under Savar Upazila, District-Dhaka. (Estimate No. 209/10-11) ID No. 326723019 | IRIDP | Savar |  | 1.21 |  |  | 3988903 | M/S. Polas Construction | 4187922.75 |  | 2011-09-20 | 2011-04-26 | 100 |  |  |  | Final bill paid
25 | IRIDP-DHK/W-151 | Improvement of road from Hemayetpur Bus Stand-Joynabare Beparepara Bazar (Ch. 00-1440m) under Savar Upazila, District-Dhaka. ID No. 326724101 | IRIDP | Savar |  | 1.44 |  |  | 8135350 | M/S. Sumon Enterprise | 8538049.94 |  | 2013-07-07 | 2013-11-01 | 100
26 | IRIDP/Dhk/SW-116 | Improvement of Alipur Bridge-Firingikanda road by BC Ch. 00-1200m under Savar, District-Dhaka. (Estimate No. 51/11-12) | IRIDP | Savar |  | 1.2 |  |  | 5600261 | M/S. Jams Engineer's | 5600260.58 |  | 2012-05-14 | 2012-09-20 | 100
27 | IRIDP/Dhk/W-134 | Improvement of road & pipe drain on Swiss Tex Tile-Motin Bricks road (Ch. 00-700m) under Savar Upazila, District-Dhaka. (Estimate No. 86/11-12), ID No. 326724224 | IRIDP | Savar |  | 0.7 |  |  | 2714831 | M/S.Redowan Builders | 2878903.98 |  | 2012-06-25 | 2012-10-01 | 95
28 | IRIDP-DHK/W-221 | Improvement of road from Shampur Bazar-Horindhora Tenary more road (Ch. 00-475m) under Savar Upazila, District-Dhaka. ID No. 326724345 | IRIDP | Savar |  | 0.48 |  |  | 3117145 | M/S. Chonchal Builder's | 3173407.4 |  | 2013-07-21 | 2013-10-27 | 70
29 | IRIDP/Dhk/W-25 | Improvement of Chapra to Chapra Kheyaghat road at Vakorta UP Ch. 00-355m road under Savar Upazila, District-Dhaka. (Estimate No. 21/10-11),IRIDP/Dhk/W-25 | IRIDP | Savar |  | 0.36 |  |  | 1604814 | Boxer Enterprise | 1641372 |  | 2010-11-08 | 2011-02-14 | 100 |  |  |  | Work Order Cancel and bill paid with penalti
30 | IRIDP/Dhk/W-94 | Improvment of Kalmarchar-Shamlapur Hight School road Ch. 00-1200m under Vakurta UP, Savar, Dist-Dhaka. (Estimate No. 212/10-11), ID No. 326725232 | IRIDP | Savar |  | 1.2 |  |  | 4212391 | M/S. KhanTraders | 4760246.53 |  | 2011-12-28 | 2011-05-03 | 0
31 | IRIDP/Dhk/W-1 | Improvement of Anower Jong road (Narsari) to Helal Master's house road at ch. 00-870m) under Savar Upazila, District-Dhaka. (Estimate No.149/09-10), ID No. 326724264 | IRIDP | Savar |  | 0.87 |  |  | 3132632 | M/S. G. C Enterprise | 3132362 |  | 2010-09-20 | 2011-01-26 | 100 |  |  |  | Final bill paid
32 | IRIDP/Dhk/W-4 | Construction of Kondolbag Pukurpar to Sarker Market via Manikgonjpara & Gosbag (GPS) road at Ch. 1250-2550m under Savar Upazila, District-Dhaka. (Estimate No.152/09-10), ID No. 326724202 | IRIDP | Savar |  | 1.35 |  |  | 4811734 | M/S. Urmi Enterprise | 4811718.6 |  | 2010-09-14 | 2011-04-20 | 100 |  |  |  | Final bill paid
33 | IRIDP/Dhk/W-5 | Improvement of DEPZ-Vadial Chowrasta-Pobnarteck road (Ch.1000-1851m) under Savar Upazila, District-Dhaka. (Estimate No.153/09-10), ID No. 326724060 | IRIDP | Savar |  | 0.85 |  |  | 3872709 | M/S. Builders Aid | 3872361 |  | 2010-09-20 | 2011-03-25 | 100 |  |  |  | Final bill paid
34 | IRIDP/Dhk/W-6 | Improvement of Baron-Chitrashail-Manikgonj Para-Goshbag road (Ch.00-920m) under Savar Upazila, District-Dhaka. (Estimate No.154/09-10), ID No. 326724119 | IRIDP | Savar |  | 0.92 |  |  | 3718111 | M/S. Tahmina Traders | 3717719.33 |  | 2010-09-19 | 2011-03-30 | 100 |  |  |  | Final bill paid
35 | IRIDP/Dhk/W-9 | Development of Ali Azam Sarkar house-Nohingertek-Manikgaonjpara road (Norshinghapur-Nischintapur-Tayebpur road) road (Ch.750-1750m) under Savar Upazila, District-Dhaka. (Estimate No.157/09-10), ID No. 326724077 | IRIDP | Savar |  | 1 |  |  | 3701333 | M/S. Alam Traders | 3701304 |  | 2010-09-16 | 2011-03-30 | 100 |  |  |  | Final bill paid
36 | IRIDP/Dhk/W-33 | Improvement of Ashulia School & College to Tongi EPZ road via Bangobondu road at road under Savar Upazila, District-Dhaka. (Ch. 00-2060m) (Estimate No. 29/10-11) | IRIDP | Savar |  | 2.06 |  |  | 4928068 | M/S. Eva Enterprise | 4926635.43 |  | 2010-12-09 | 2011-04-07 | 100 |  |  |  | Final bill paid
37 | IRIDP/Dhk/W-34 | Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road under Savar Upazila, District-Dhaka. (Ch. 1234-1817m) (Estimate No. 30/10-11) | IRIDP | Savar |  | 0.58 |  |  | 3394531 | M/S. Hemany Enterprise | 3394306 |  | 2010-10-25 | 2011-03-03 | 100 |  |  |  | Final bill paid
38 | IRIDP/Dhk/W-124 | Improvement of Yearpur-Yearpur High School road Ch. 00-300m under Savar Upazila, District-Dhaka. (Estimate No. 60/11-12), ID No. 326725234 | IRIDP | Savar |  | 0.3 |  |  | 1338981 | Alpona Construction | 1338980.73 |  | 2012-04-12 | 2012-06-18 | 100 |  |  |  | Final bill paid
39 | IRIDP-DHK/W-172 | Improvement of Ashulia UP Office-Ashulia Hazera Khatun Madrasha road (Ch. 410-560m) under Savar Upazila, District-Dhaka. ID No. 326725111 | IRIDP | Savar |  | 0.15 |  |  | 528729 | M/S. Zia Enterprise | 555165.41 |  | 2013-04-23 | 2013-05-29 | 100 |  |  |  | Final bill paid
40 | IRIDP/Dhk/W-130 | Improvement of Polashbari Bazar-Bashbari via Gocharartek road (Ch. 650-1200m) under Savar Upazila,, District-Dhaka. (Estimate No. 75/11-12), ID No. 326724333 | IRIDP | Savar |  | 0.55 |  |  | 3025966 | M/S.Rima Tarders | 3025912.95 |  |  | 2013-01-25 | 100
41 | IRIDP-DHK/W-170 | Part-A) Improvement of road from Zamgora Chowrastha-Gazirchor High School road (Ch. 00-1010m) ID No. 326724153 & Part-(B) Maintenance of Gazirchot-Kandail road (Ch. 0-620m) under Savar Upazila, District-Dhaka. ID No. 326724235 | IRIDP | Savar |  | 1.63 |  |  | 6142302 | M/S. Nazma Enterprise | 6446341.1 |  | 2013-04-10 | 2013-07-16 | 100
42 | IRIDP-DHK/W-177 | Improvement of Dendabor (RHD) Madrasha-Polash Bari-Gocharateck road (Ch. 412-1785m) under Savar Upazila, District-Dhaka. ID No. 326724289 | IRIDP | Savar |  | 1.37 |  |  | 4377518 | M/S. Dewan Enterprise | 4683243 |  | 2013-04-21 | 2013-10-19 | 100
43 | IRIDP/Dhk/SW-108 | Improvement road from Gonokbari (Pacca road)-DEPZ road (ch. 00-498m) & Construction of 1x4.00x4.00m RCC Box Culvert (Ch. 455m) under Savar Upazila, District-Dhaka. (Estimate No. 04/11-12), ID No. 326724235 | IRIDP | Savar |  | 0.5 |  |  | 3869767 | M/S.Abdus Salam | 4847543.39 |  | 2012-06-26 | 2013-06-28 | 100
44 | IRIDP-DHK/W-167 | Improvement of road from Ashulia Polli Biddut to Office-Ashulia High School road (Ch. 00-400m) under Savar Upazila, District-Dhaka. ID No. 326725253 | IRIDP | Savar |  | 0.4 |  |  | 2084743 | Maz Bussiness Syn | 2175998 |  | 2013-05-19 | 2013-07-25 | 100 |  |  |  | Final bill paid
45 | IRIDP/Dhk/SW-85 | Development of C&B Ashulia road's Mozid Market-Roton Member;s house-Hikmot Alis house Dinestry Soweater's Ltd. (Akupara-Bongabandu road via Belma) under Savar Upazila, District-Dhaka. (Ch. 00-1500m) ID No. 326724175 (Estimate No. 205/10-11) | IRIDP | Savar |  | 1.5 |  |  | 6292980 | M/S. Unique Engineering | 6603281.88 |  | 2011-07-06 | 2011-07-13 | 70
46 | IRIDP/Dhk/W-59 | Improvement of road from H/O Salek Mohajon at Konda-H/O Javed Ali (Ch. 00-1200m) under Bongaon UP under Savar Upazila, District-Dhaka. (Estimate No. 119/2010-11) | IRIDP | Savar |  | 1.2 |  |  | 4062205 | M/S. Suchana Enterprise | 4061852 |  | 2011-02-02 | 2011-06-07 | 60 |  |  |  | W/O Canceled
47 | IRIDP/Dhk/W-7 | Development of Ashulia UP-Dolpur via Baro Rangamatia-Katgora road (Ch. 6260-7260m under Savar Upazila, District-Dhaka. (Estimate No.155/09-10), ID No. 3267223010 | IRIDP | Savar |  | 1 |  |  | 2711869 | M/S. Sony Enterprise | 2711524 |  | 2010-09-19 | 2011-03-25 | 60
48 | IRIDP/Dhk/W-8 | Improvement of road from Sreepur-Kashimpur road Hasan Member house-Hazi Rashid Shaheb house road (Ch. 00-575m) under Savar Upazila, District-Dhaka. (Estimate No.156/09-10), ID No. 326725112 | IRIDP | Savar |  | 0.58 |  |  | 2070484 | M/S. Bari Construction | 2070468 |  | 2010-09-21 | 2010-12-27 | 60
49 | IRIDP/Dhk/W-123 | Improvement of Yearpur H/O Jamat Ali-Lalpahar Buripara road Ch. 00-900m under Savar Upazila, District-Dhaka. (Estimate No. 59/11-12), ID No. 326724334 | IRIDP | Savar |  | 0.9 |  |  | 3998739 | M/S. Sajal Enterprise | 3998738.19 |  | 2012-04-12 | 2012-07-18 | 60
50 | IRIDP-DHK/W-164 | Improvement of Kandail Eidgah-Etakhola via Ghoshbag Rotary Girl's School road (Ghoshbag Rotary Girls School-Dewan filling Station) (Ch. 00-1240m) under Savar Upazila, District-Dhaka. ID No. 326724072 | IRIDP | Savar |  | 1.24 |  |  | 6485750 | M/S. Talukder Traders | 6485750.82 |  | 2013-05-19 | 2013-08-25 | 60
51 | IRIDP-DHK/W-174 | Improvement of Kohinor Mill to Pathalia-Rohimpur road (Ch. 400-1650m) under Savar Upazila, District-Dhaka. ID No. 326724115 | IRIDP | Savar |  | 1.25 |  |  | 9036586 | M/S. M.R Construction | 9486608.44 |  | 2013-05-21 | 2013-05-28 | 60
52 | IRIDP-DHK/W-175 | Improvement of Savar GC-CRP-Lalteck-Savar UP road (Ch.400-1650m) under Savar Upazila, District-Dhaka. ID No. 326723027 | IRIDP | Savar |  | 1.25 |  |  | 4316884 | Amanat Shah Electrict & Engr. | 4316883.95 |  | 2013-04-29 | 2013-05-06 | 60
53 | IRIDP/Dhk/W-86 | Development of Polashbari-Kaichabari-Bashbari road (Ch. 1.500-2.500Km) under Savar Upazila, District-Dhaka. ID No. 326724096 (Estimate No. 202/10-11) | IRIDP | Savar |  | 1 |  |  | 3920577 | M/S. Dewan Enterprise | 3918086.19 |  | 2011-08-08 | 2013-12-04 | 100 |  |  |  | Final bill paid
54 | IRIDP/DHK/W-132 | Improvement of Kaliakoir Kamlapur road Krishibid West Vew main Gate-Bagne Bare road (Ch. 00-750m) under Savar Upazila, District-Dhaka. (Estimate No. 84/11-12), ID No. 326725251 | IRIDP | Savar |  | 0.75 |  |  | 3351361 | Fina Superlub Co. | 3511234.36 |  | 2012-07-10 | 2013-08-29 | 100 |  |  |  | Final bill paid
55 | IRIDP-DHK/W-168 | Improvement of road from Choto Kaliakoir Pucca road-Komlapur road (Ch. 00-520m) under Savar Upazila, District-Dhaka. ID No. 326724350 | IRIDP | Savar |  | 0.52 |  |  | 2517908 | M/S. Nazma Enterprise | 2642540.89 |  | 2013-04-10 | 2013-06-16 | 100
56 | IRIDP-DHK/W-165 | (A) Improvement of Polashbari- Kaichabari-Bashbari road (Ch. 2500-3500m) & Link road & Ch.00-300m) (B) Same road 2715m, 2757m, 2788m & 3253m Ch. 0.600x0.600m 4 Drain Culvert under Savar Upazila, District-Dhaka. ID No. 326724096 | IRIDP | Savar |  | 1 |  |  | 6109634 | M/S. Talukder Traders | 6413893.82 |  | 2013-06-02 | 2014-01-15 | 100 |  |  |  | Final bill paid
57 | IRIDP-DHK/W-173 | Improvement of Gerua Bazar-Jamshing Bazar a road (Ch. 00-672m) under Savar Upazila, District-Dhaka. ID No. 326724190 | IRIDP | Savar |  | 0.67 |  |  | 4643047 | M/S. Hasib Enterprise | 5023703 |  | 2013-04-21 | 2013-07-27 | 60
58 | IRIDP/Dhk/W-3 | Part-A: Improvement of Dhakhin Gazirchot Sher Ali Market-Bottola road (Ch. 0-750m), Part-B: Construction of 4.50x3.50m RCC Box culvert road on Dhakhin Gazirchot Sher Ali Market-Bottola (Ch. 630m) road under Savar Upazila, District-Dhaka. (Estimate No.151/ | IRIDP | Savar |  | 0.75 |  |  | 3526729 | M/S. Deep Laid Enterprise | 3525625.5 |  | 2010-09-21 | 2011-01-27 | 50
59 | IRIDP/Dhk/W-82 | Construction of 90.00m RCC Girder Bridge over Kasoir Khal on Nutun Bondor Shimulia UP Office-Kasoir-Bagabari road at Ch. 0+610m under Savar Upazila, District-Dhaka.(Estimate No. 188/10-11) ID No. 326724204 | IRIDP | Savar |  |  |  |  | 17969697 | M/S. Humaira Enterprise | 18679500 |  | 2011-06-20 | 2012-06-26 | 45
60 | IRIDP/DHK/W-133 | Improvement of Ambagan-Islamnagar-Bottola-Gerua Bazar road (Ch. 00-972m) under Savar Upazila, District-Dhaka. (Estimate No. 85/11-12), ID No. 326724192 | IRIDP | Savar |  | 0.97 |  |  | 5022905 | M/S. Alam Traders | 5263697.19 |  | 2012-07-01 | 2014-04-23 | 60 |  |  |  | W/O Canceled and 242990/- pending paid
61 | IRIDP-DHK/W-171 | (A) Improvement of Nickrail-Chandpur-Vobanipur road (Ch. 00-1500m) (B) Same road 1100m Ch. 0.600x0.600m 1 Drain Culvert under Savar Upazila, District-Dhaka. ID No. 326724153 | IRIDP | Savar |  | 1.5 |  |  | 7989464 | M/S. S.S Construction | 7988665.48 |  | 2013-05-09 | 2013-09-15 | 60
62 | IRIDP/Dhk/W-2 | Improvement of Ashulia UP Office to Hajerakhatun Madrasha road at Ch. 00-410m under Savar Upazila, District-Dhaka. (Estimate No.150/09-10), ID No. 326725111 | IRIDP | Savar |  | 0.41 |  |  | 1392025 | M/S. Nabil International | 1389598.92 |  | 2010-09-29 | 2011-01-04 | 20
63 | IRIDP-DHK/W-169 | Improvement of road from Chakulia Pucca road (Gosh Bag) to Chakulia Deep Tubewell road (Ch. 00-500m) under Savar Upazila, District-Dhaka. ID No. 326724349 | IRIDP | Savar |  | 0.5 |  |  | 2042885 | M/S. Hasib Enterprise | 2145029.16 |  | 2013-04-21 | 2013-12-09 | 100
64 | IRIDP-DHK/W-166 | Improvement of road from Jamgora Simultoli-Sayed Masterbari-Jamgora Primary School road (Ch. 00-1000m) under Savar Upazila, District-Dhaka. ID No. 326725025 | IRIDP | Savar |  | 1 |  |  | 3874920 | M/S. Jakir Hossain | 4068665.64 |  | 2013-07-29 | 2014-03-13 | 100
65 | IRIDP-DHK/W-176 | Improvement of Toyebpur (Zirabo) Dewan Idrish College-Safina Poultry Firm Culvert Approach-Tayebpur Jame Mosque road) (Ch. 00-455m) under Savar Upazila, District-Dhaka. ID No. 326724247 | IRIDP | Savar |  | 0.46 |  |  | 2300995 | M/S. Biplop Enterprise | 2300994.61 |  | 2013-04-23 | 2013-06-28 | 0
66 | IRIDP-DHK/SW-221 | Improvement of road from Shampur Bazar-Horindhora Tenary more road (Ch. 00-475m) under Savar Upazila, District-Dhaka. ID No. 326724345 | IRIDP | Savar |  | 0.48 |  |  | 3117145 | M/S. Chonchal Builder's | 3173407.4 |  | 2013-07-21 | 2013-10-27 | 100 |  |  |  | Final bill paid
67 | IRIDP/Dhk/W-116 | Improvement of Alipur Bridge-Firingikanda road by BC Ch. 450-700m under Savar, District-Dhaka. (Estimate No. 51/11-12) ID No.326724272 | IRIDP | Savar |  | 1.2 |  |  | 5600261 | M/S. Jams Engineer's | 5600260.58 |  | 2012-05-14 | 2013-03-10 | 100 |  |  |  | Final bill paid
68 | IRIDP/Dhk/SW-134 | Improvement of road & pipe drain on Swiss Tex Tile-Motin Bricks road (Ch. 450-700m) under Savar Upazila, District-Dhaka. (Estimate No. 86/11-12), ID No. 326724224 | IRIDP | Savar |  | 0.25 |  |  | 2714831 | M/S.Redowan Builders | 2878903.98 |  | 2012-06-25 | 2012-10-01 | 95
69 | IRIDP/Dhk/SW-94 | Improvment of Kalmarchar-Shamlapur Hight School road Ch. 00-1200m under Vakurta UP, Savar, Dist-Dhaka. (Estimate No. 212/10-11), ID No. 326725232 | IRIDP | Savar |  | 1.2 |  |  | 4212391 | M/S. KhanTraders | 0 |  | 2011-12-28 | 2011-05-03 | 0 |  |  |  | W/O Canceled
70 | IRIDP/DHK/DW-241 | a)Improvement of Road from Hemayetpur Suwitch Textile to Motin Brick Field (Ch:00-445m) Road Code:326724224. b) Improvement of Road from Apurupa Textile Miles to Bagbari Via Kuddus Ali House. (CH:00-253.00m) Road Code:326725265 | IRIDP | Savar |  | 0.25 |  |  | 3494145 | M/S. Shafique & Brothers | 3460816.18 |  |  |  | 0
71 | IRIDP/DHK/DW-238 | Improvement of Bangabandhu Road to Katgora Bazar via Aragaon Road (Ch. 00-1110 m) under Savar Upazila, District-Dhaka. (Road ID No: 326724037) | IRIDP | Savar |  | 1.11 |  |  | 4599998 | M/S Shafiqual & Brothers | 5169742.69 |  | 2014-03-03 | 2014-10-01 | 60
72 | IARP/DHK-08 | Improvement of i) Approach road at Beraid HZ. Abul Khalek house to School (Ch. 00-345m) & ii) Toibpur Dewan Iddrish College to Shafina Poultry Firm Culvert approach (Ch. 0-455m) under Savar Upazila, District-Dhaka. (Estimate No. 46/11-12) | IARP | Savar |  |  |  |  | 3998980 |  | 3998980 |  |  |  | 0
73 | GDP-II/Dha/Sav/W(R)-05 | Improvement of Zirani-Shimulia Analbari-Nallapolla road Ch. 00-690m under Savar Upazila, District-Dhaka. (Estimate No. 22/11-12), ID No. 32672114, | GDP-2 | Savar |  | 0.69 |  |  | 3461248 | M/S Aunika International | 3288185 |  | 2012-01-22 | 2012-04-21 | 0
74 | GDP-II/Dha/sav/W(R)-11 | Improvement of Rajfulbaria Bus Stand-Rishipara via Fulbaria Bazar Road Ch. 00m- 650 m (ID No. 3267623005) under Saver Upazila Dist: Dhaka. | GDP-2 | Savar |  | 0.65 |  |  | 5186876 | M/S Emran Builders | 4927477 |  | 2012-03-01 | 2012-06-30 | 10
75 | GDP-II/DHA/Sav/W(R)-13 | Improvement of Aragaon Primary School-Doshaid School road Ch. 1400-2535m (ID No. -326724037) under Savar Upazila, District-Dhaka. (Estimate No. 53/11-12) | GDP-2 | Savar |  | 1.14 |  |  | 5532635 | M/S Futme Castle Constriction | 5528619 |  | 2012-04-03 | 2012-08-02 | 0
76 | GDP-II/DHA/Sav/W(R)-15 | A) Improvement of road from Gerua Bazar to Physics Department via Moulana Bhasani Hall & Bangabandhu Sheikh Mujibur Rahman Hall of Jahangir Nagar University Ch. 00-1020m (ID No. 326724003) & B) Improvement of Baroipara (Pacca road)-Olosara road Ch. 00-65m | GDP-2 | Savar |  |  |  |  | 7296902 |  | 0 |  |  |  | 0 |  |  |  | Tender sent to H/Q for approval
77 | W-DHAK-Savar-UNR-08-05 | Improvement of Aricha Boliapur Bongaon UP (Konda Bazar)-Chakulia Bazar road, (Ch. 0+000Km to 4+881 Km), Upazila: Savar. | RIIP-2 | Savar |  | 4.88 |  |  | 30395637 | M/S. Nipa Enterprise | 27106000 |  | 2009-01-14 | 2011-09-27 | 100 |  |  |  | Road- 4.881 km Bridge- .75m
78 | i) W-DHAK-Savar-UZR-09-77(a) | Improvement of Dhaka Aricha RHD at 22 Mile-Shimulia Road via nalam (ch. 2915-6000m) upazila Savar, Dist.- Dhaka | RIIP-2 | Savar |  | 3.09 |  |  | 22383684 | Delco Engg. & Reduan Builders (JV) | 22364000 |  | 2010-06-07 | 2011-06-07 | 40
79 | ii) W-DHAK-Savar-UZR-09-77(b) | Improvement of Dhaka Aricha RHD at 22 Mile-Shimulia Road via nalam (ch. 6000-7658m)connect vararia UPC(ch.00-1003m) upazila Savar, Dist.- Dhaka | RIIP-2 | Savar |  | 2.69 |  |  | 22432507 | M/S. Geneva International & Badhan Traders (JV) | 22137000 |  | 2010-06-29 | 2011-06-29 | 60
80 | RTIP-II/DHA/UNR-12 | c) Dhaka-Aricha RHD 20 Mile Army check post-Pathalaia UP (Ghugudia) Road | RTIP-2 | Savar |  | 3.55 |  |  | 313.9 |  | 0 |  | 2014-08-13 | 2017-02-20 | 100
81 | RTIP-II/DHA/RPM-106 | Ashulia UP Office-Rustumpur bazar road | RTIP-2 | Savar |  | 3.33 |  |  | 110.67 | M/S. Aunica International | 120.57 |  | 2014-03-19 | 2015-11-08 | 100 |  |  |  | Final
82 | RTIP-II/DHA/UNR-12-STR-2 | d) Construction of 2x4.00x5.50m RCC Box Culvert at Ch. 2+150km on Dhaka-Aricha RHD 20 Mile Army check post-Pathalaia UP (Ghugudia) Road | RTIP-2 | Savar |  | 8 |  |  | 48.19 |  | 0 |  | 2015-07-23 | 2017-05-16 | 100
83 | RTIP-II/DHA/RPM-199 | Zirani Bazar-Shimulia Bazar Road | RTIP-2 | Savar |  | 8.25 |  |  | 749.53 | AL_AMIN-KINGDOM-JVA | 786.29 |  | 2016-08-07 | 2019-02-28 | 80
84 | RTIP-II/DHA/RPM-346 | Bhakurta UP-Mugrakanda-Mohammad Pur. City protection embankment Rd. | RTIP-2 | Savar |  | 1.3 |  |  | 329.2 | Western Engineering (Pvt.) Ltd | 63.49 |  | 2017-03-20 | 2017-12-19 | 100 |  |  |  | Final. Force Majeure
85 | RTIP-II/DHA/RPM-392 | Savar Bazar Bus Stand-Birulia UP-Birulia bazar Rd | RTIP-2 | Savar |  | 2.68 |  |  | 214.37 | Topline | 192.75 |  | 2017-04-25 | 2018-06-30 | 100
86 | PEDP-III/DHK/SAV/2011-12/W1.0072 | sandip com. primary school School Reconstruction | PEDP-3 | Savar |  |  |  |  | 5140000 | M/s Emran Builders | 17948942 |  | 2012-09-07 | 2014-01-04 | 100
87 | PEDP-III/DHK/SAV/2012-13/W2.2128 | GAZIR CHAT School Additional Room | PEDP-3 | Savar |  |  |  |  | 6773000 | M/s Emran Builders | 10707330.69 |  | 2013-07-30 | 2014-08-05 | 100
88 | PEDP-III/DHK/SAV/2011-12/W2.0062 | PARAGRAM School Additional Room | PEDP-3 | Savar |  |  |  |  | 3388000 | M/S Udy Enterprise | 7311703 |  | 2012-06-09 | 2013-06-25 | 100
89 | PEDP-III/DHK/SAV/2011-12/W2.0538 | NUTAN BANDAR School Additional Room | PEDP-3 | Savar |  |  |  |  | 2993000 | M/s Boyanna Enterprise | 10244869 |  | 2012-07-05 | 2013-07-04 | 100
90 | PEDP-III/DHK/SAV/2011-12/W2.0539 | TETUL JHORA School Additional Room | PEDP-3 | Savar |  |  |  |  | 2993000 | M/s Nazma Enterprise | 6886750 |  | 2012-07-05 | 2013-07-04 | 100
91 | PEDP-III/DHK/SAV/2011-12/W2.1398 | SAIPARA School Additional Room | PEDP-3 | Savar |  |  |  |  | 2385000 | M/s Aziz Construction | 6638821.47 |  | 2012-09-30 | 2013-10-06 | 100
92 | PEDP-III/DHK/SAV/2011-12/W2.0540 | GOMAIL School Additional Room | PEDP-3 | Savar |  |  |  |  | 2993000 | M/s M.R Construction | 6973420 |  | 2012-07-05 | 2013-07-04 | 100
93 | PEDP-III/DHK/2012-13/W2.1842 | BARADESHI School Additional Room | PEDP-3 | Savar |  |  |  |  | 6072000 | M/s Kazi Traders | 7217580 |  | 2013-09-05 | 2014-06-11 | 100
94 | PEDP-III/DHK/SAV/2012-13/W2.1921 | CHAKAL GRAM School Additional Room | PEDP-3 | Savar |  |  |  |  | 5186000 | M/s Shahid & Co. | 6500487 |  | 2013-01-09 | 2013-10-15 | 25
95 | PEDP-III/DHK/SAV/2013-14/W2.2839 | kabirpur reg. primary school School Additional Room | PEDP-3 | Savar |  |  |  |  | 3955000 | M/s Alam traders | 3954848.97 |  | 2013-11-05 | 2014-07-10 | 85
96 | PEDP-III/DHK/SAV/2013-14/W3.0400 | kabirpur reg. primary school School Major Maintenance | PEDP-3 | Savar |  |  |  |  | 507708 | M/S Udoy Enterprise | 431557.91 |  | 2014-04-23 | 2014-11-09 | 100
97 | PEDP-III/DHK/SAV/2011-12/W3.0325 | KRINSHAPUR HASSIN School Major Maintenance | PEDP-3 | Savar |  |  |  |  | 179197 | M/s Mow Construction | 569829.6 |  | 2012-09-30 | 2013-04-06 | 100
98 | GDP-D-18 | Improvement of Savar UP (Dhaka-Aricha RHDD) Genda-Sadapur Bangoan road (Ch. 7315-7830m) under Savar Upazila, District-Dhaka. (Estimate No. 149/08-09), Package No. UNR-GDP-W-07/08-10 | UNR-GDP | Savar |  | 0.52 |  |  | 2487015 | The Bhuyan Engineers Ltd. | 2455339.14 |  | 2009-04-27 | 2009-07-21 | 100
99 | GDP-D-19 | Part-A) Improvement of Sreepur-Gohailbari via Shobondi & Dhamsona UP road (Ch. 5224-6570m) under Savar Upazial, District-Dhaka. (Estimate No. 150/08-09), Package No. UNR-GDP-W-08/08-09 | UNR-GDP | Savar |  | 1.35 |  |  | 5444120 | M/S. M.M Construction | 5423256 |  | 2009-03-12 | 2009-07-05 | 100
100 | GDP-D-26 | Improvement of Baipail BKSP Training Academy link road (Ch. 00-344m).under Savar Upazila, District-Dhaka.Package No.UNR-GDP-W-20/08-09 | UNR-GDP | Savar |  | 0.34 |  |  | 1500000 | M/S. M.R Enterprise | 1448856.26 |  | 2009-06-02 | 2009-09-04 | 100
101 | GDP-D-28 | Improvement of Hatubhanga road to Pathalia Housing Society road (Ch. 500-750m).under Savar Upazila, District-Dhaka. Package No. UNR-GDP-W-08/08-09 | UNR-GDP | Savar |  | 0.25 |  |  | 860469 | M/S. Kazoli Enterprise | 752137.5 |  | 2009-07-20 | 2009-10-14 | 100
102 | GDP-D-33 | Improvement of Boroipara RHD-Polly Biddut road (Ch. 981-1620m).under Savar Upazila, District-Dhaka.(Estimate No. 19/09-10) Package No. UNR-GDP-W-05/09-10 | UNR-GDP | Savar |  | 0.64 |  |  | 2908951 | M/S. Talukder Enterprise | 2447194.06 |  | 2010-01-20 | 2010-05-20 | 100
103 | GDP-D-37 | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch. 00-826m).under Savar Upazila, District-Dhaka.(Estimate No. 21/09-10), Package No. UNR-GDP-W-07/09-10 | UNR-GDP | Savar |  | 0.83 |  |  | 2845273 | M/S. Khondoker Enterprise | 2333123.25 |  | 2010-01-24 | 2010-05-24 | 100
104 | GDP-D-38 | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch. 825-1565m).under Savar Upazila, District-Dhaka.(Estimate No. 22/09-10), Package No. UNR-GDP-W-09/09-10 | UNR-GDP | Savar |  | 0.74 |  |  | 2861406 | M/S. T\Khondakar Enterprise | 3000184 |  | 2011-01-24 | 2011-05-02 | 65
105 | GDP-D-39 | Improvement of Poran Bazar BLRL (RHD) Ashulia UP road (Ch.1565-2219m).under Savar Upazila, District-Dhaka.(Estimate No. 23/09-10), Package No. UNR-GDP-W-10/09-10 | UNR-GDP | Savar |  | 0.65 |  |  | 2877730 | M/S. Khondoker Enterprise | 2330956.63 |  | 2010-01-24 | 2010-05-24 | 100
106 | GDP-D-59 | Improvement of Durgapur-Porbochala ch. 00-570m, 00-175m | UNR-GDP | Savar |  | 0.75 |  |  | 2300000 | M/S. Anando Construction | 2295500 |  | 2010-03-08 | 2012-04-22 | 100
107 | GDP-D-05 | Improvement of Dhaka-Aricha RHD to Genda Shadapur-Bongaon ch. 2100-3500m road. | UNR-GDP | Savar |  | 1.4 |  |  | 5612555 | M/S. Khan Enterprise | 5607999 |  | 2010-03-13 | 2010-07-13 | 100
108 | GDP-D-35 | Improvement of road from Mugrakanda Vakurta road Baily Bridge to Turag Super Market (Dewan house connecting road) road under Savar Upazila, (Ch. 00-210m) District-Dhaka. | UNR-GDP | Savar |  | 0.21 |  |  | 990000 | M/S. Integrated Solution Ltd. | 968990 |  | 2010-05-12 | 2010-09-12 | 70
109 | GDP-D-58 | a) Improvement of Tengori main road Shop of Rafiq-Tengori Mujibur & Ershad House road (Ch. 0-360m & 0-215m), b) Madhaya Konapara main road (Ch. 0-490m & 107m) under Savar Upazila, District-Dhaka. (Estimate No.94/09-10) | UNR-GDP | Savar |  | 1.17 |  |  | 4984005 | M/S. S.A Engineering | 5217839.68 |  | 2010-05-04 | 2010-09-04 | 100
110 | GDP-D-62 | Improvement of road from Zirani-Shimulia road Samon Ali Colony Konapara Jame Mosque road (Ch. 522-1044m) under Savar Upazila, District-Dhaka. | UNR-GDP | Savar |  | 0.52 |  |  | 2120145 | M/S. Siam Corporaton | 2014138 |  | 2010-05-02 | 2010-07-02 | 60
111 | GDP-D-74 | Improvement of Kalasuti Sultan house-Madrasha via H/O Haji Based road ch. 00-802m | UNR-GDP | Savar |  | 0.8 |  |  | 2890221 | M/S. M.S.A. Construction & Engineering | 2745710 |  | 2010-06-22 | 2010-09-22 | 100
112 | GDP-D-73 | Improvement of Kaltasuti Edrish Chowkider house-Noapara house of Jamal road at Shimulia UP (Ch. 00-587m) | UNR-GDP | Savar |  | 0.59 |  |  | 2359869 | Pial Construction | 2298876 |  | 2010-06-05 | 2010-09-05 | 100
113 | GDP-D-63 | Improvement of Tenguri Harun Factory to Kaltasuti Morichkata Shadhubari road (Ch. 00-545m) | UNR-GDP | Savar |  | 0.55 |  |  | 2415719 | M/S. Joy Construction | 2529022 |  | 2010-07-04 | 2010-09-04 | 50
114 | GDP-D-91 | Improvement of Sreepur Busstand Subondi Trimohoni road (Ch. 1150-2712m). | UNR-GDP | Savar |  | 1.56 |  |  | 3933360 | M/S. Hasan Traders | 3933125 |  | 2010-10-24 | 2011-01-24 | 60
115 | GDP-D-83 | Improvement of Gonakpara Govt. Primary School Joynal Dealar House road (Ch. 00-322m). | UNR-GDP | Savar |  | 0.32 |  |  | 1999390 | M/S. J&J Corporation | 1999331 |  | 2010-10-09 | 2011-01-09 | 60
116 | GDP-D-85 | Improvement of Hemayetpur Oporupa Textiles Mill to Bugbari Connecting road (Ch. 00-253m). | UNR-GDP | Savar |  | 0.25 |  |  | 934022 | M/S. Santa Enterprise | 971371 |  | 2010-08-07 | 2010-10-07 | 60
117 | GDP-D-86 | Improvement of a) Kaliakoir Nabinagaor road at Tengori Shop of Gias Uddin-Tengori Modina Colony road (Ch. 00-357m), b) Purbo Katlasuti house of Zahirul Islam-House of Nazir Hossain road Ch. 00-250m | UNR-GDP | Savar |  | 0.61 |  |  | 1756350 | Deep-Laid Enterprise | 1755561 |  | 2010-08-03 | 2010-10-09 | 70
118 | GDP-D-87 | Improvement of road from a) House of Khaleque-House of Azgar Ali at Tengori Ch. 00-210m b) House of Belayet Hossain-house of Abu Taher at Tan Konapara road Ch. 00-150m | UNR-GDP | Savar |  | 0.36 |  |  | 1243648 | M/S. Rekha Enterprise | 1243681 |  | 2010-08-08 | 2010-10-08 | 60
119 | GDP-D-76 | Improvement of Paragram Rustompur road Deun-Moinuddin Shop to Hazirat Ali House Ch. 00-568m | UNR-GDP | Savar |  | 0.57 |  |  | 2876186 | M/S. Momtaz Builder | 3007925 |  | 2010-07-19 | 2010-10-19 | 25
120 | GDP-D-111 | Improvement of Circular road of Savar Cantonment Savar, Dhaka. Ch. 00-10100m Dhaka.(Estimate No. 51/10-11) GDP-D-111 | UNR-GDP | Savar |  | 10.1 |  |  | 66129937 | Islam Trading Construction | 61732127 |  | 2010-12-12 | 2011-12-12 | 30
121 | GDP-D-100 | Improvement of Balivadra GC-Dhamsona UP-Shimulia UP road Ch. 1817-2328m under Savar Upazila, District-Dhaka. (Estimate No. 48/10-11 | UNR-GDP | Savar |  | 0.51 |  |  | 3499866 | M/S Haji Enterprize | 3499866 |  | 2011-01-01 | 2011-04-01 | 40
122 | GDP-D-104 | A) Improvement of Koltasuti Sabida Chala-Barol Kabarastan road Ch. 00-576m, B) Improvement of Koltasuti Sabida Chala-Dhalivari road Ch. 00-342m & c) Improvement of Tengori-Konapara Baidgaon road Ch. 00-837m under Savar Upazila, District-Dhaka. (Estimate N | UNR-GDP | Savar |  | 1.18 |  |  | 5499675 | M/S Bishal Enterprise | 5498935 |  | 2001-12-21 | 2011-04-21 | 60
123 | GDP-D-105 | A) Improvement road from Miar Rahman House-House of Sahufu at Kaltasuti (Road from House of Badsha-House of Halim at Kaltasuti (Ch. 00-145m & Ch. 00-145m) B) Tengori Akali House-Tengori Mujibur House road (Ch. 00-340m) under Savar Upazila, District-Dhaka | UNR-GDP | Savar |  | 0.63 |  |  | 4499190 | M/S. Zia Construction | 4499150 |  | 2011-02-02 | 2011-06-09 | 60
124 | GDP-D-106 | Improvement of Kuturia-Bogabari Bazar road Ashulia UP road (Ch.00-1700m) under Savar Upazila, Dist-Dhaka. (Estimate No.66/10-11) | UNR-GDP | Savar |  | 1.7 |  |  | 4999582 | M/S. Mollah Traders | 5244606 |  | 2011-02-05 | 2011-05-04 | 50
125 | GDP-D-116 | Part-A: Improvement of road from Sreepur-Subondi road near shop of Kojon Miah to house of Azim Uddin Member at Subondi (Ch. 00-1064m) & Part-B: Construction of 0.60m Span U-Drain at (Ch. 52m & 160m) on same road under Savar Upazila, District-Dhaka. (Estim | UNR-GDP | Savar |  | 1.06 |  |  | 4999895 | M/S Khazababa Center Point | 5243532 |  | 2011-03-20 | 2011-07-19 | 10
126 | GDP-D-138 | Part-A: Improvement of Purbo Kaltasuti Muslimteck (House of Surot Ali)-Mollarbag Mosque road (Ch. 00-1270m) & Part-B: Construction of 2.00m Span Box at (Ch. 692m) on the same road under Savar Upazila, District-Dhaka. (Estimate No. 122/10-11,Package No. UN | UNR-GDP | Savar |  | 1.27 |  |  | 5479829 | M/S. Hasan Traders | 5741174 |  | 2011-03-13 | 2011-07-12 | 65
127 | GDP-D-125 | Improvement of Rostumpur Shadhupara Chowrastha-Kagan Paragram Connecting via Paragram Koborstan road (Ch. 00-976m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 124/10-11 | UNR-GDP | Savar |  | 0.98 |  |  | 3985000 | M/S. Kashem Traders | 4176231 |  | 2011-02-17 | 2011-05-16 | 65
128 | GDP-D-126 | Improvement of Ronosthal-Myjhail-Pychail road (Ch. 00-1150m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 125/10-11 | UNR-GDP | Savar |  | 1.15 |  |  | 3984980 | M/S. Sadia Enterprise | 4180549 |  | 2011-03-28 | 2011-07-02 | 60
129 | GDP-D-127 | Improvement of Kuturia Dewan Bari Mosque-Khatghora High School road (Ch. 00-1038m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 126/10-11 | UNR-GDP | Savar |  | 1.04 |  |  | 3982505 | M/S. Palash Construction | 4168846 |  | 2011-03-01 | 2011-06-06 | 0
130 | GDP-D-112 | Improvement of Purbo Baidgaon (Pagla Bazar)-Purbo Baidgaon Govt. Primary School road (Ch.250-1000m) under Savar Upazila, Dist-Dhaka. (Estimate No.70/10-11) Package No. UNR-GDP-D-112 | UNR-GDP | Savar |  | 0.75 |  |  | 3479883 | M/S. Mollah Traders | 0 |  | 2011-02-05 | 2011-05-04 | 0
131 | GDP-D-113 | Improvement of Bariopara (RHD)-Polly Biddut road (Ch. 00-1134m) under Savar Upazila, Dist-Dhaka. (Estimate No.71/10-11) Package No. UNR-GDP-D-113 | UNR-GDP | Savar |  | 1.13 |  |  | 5979873 | M/S. Bishal Enterprise | 6276342 |  | 2011-02-23 | 2011-06-30 | 65
132 | GDP-D-114 | Improvement of road from Goalbari Machinepar Momin Bari-House of Ali (Ch.00-662m) under Savar Upazila, Dist-Dhaka. (Estimate No.72/10-11) Package No. UNR-GDP-D-114 | UNR-GDP | Savar |  | 0.66 |  |  | 2979985 | M/S Udhya Enterprize | 2979366 |  |  |  | 60
133 | GDP-D-141 | Improvement of road from Kondalbag Pukur Par to Sarkar Market via Bhuiyan Bari Jame Mosque road (Ch. 2550-3050m) under Upazila Savar Upazila, Dist-Dhaka. (Estimate No. 127/10-11) ,Package No. UNR-GDP-D-141 | UNR-GDP | Savar |  | 0.5 |  |  | 6070663 | M/S. Urmi Enterprise | 6373699 |  | 2011-03-09 | 2011-07-08 | 85
134 | GDP-D-142 | Part-A: Improvement of Nabinagar-Kaliakoair RHD (Savar Metal)-Sreepur Kaborsthan road (Ch. 00-962m) & Part-B: Construction of 500mm Span U-Drain at Ch. 650m same road under Savar Upazila, District-Dhaka. (Estimate No. 147/10-11), Package No. UNR-GDP-D-142 | UNR-GDP | Savar |  | 0.96 |  |  | 3989979 | M/S. Erfan Cons: | 3946640 |  | 2011-03-20 | 2011-07-23 | 65
135 | GDP-D-159 | Improvement of Nama Konapara Jalus House- Jolhash House Road . (Ch. 00-665m) | UNR-GDP | Savar |  | 0.67 |  |  | 2690055 | M/S. Miah Trader | 2674824 |  | 2011-04-11 | 2011-07-16 | 50
136 | GDP-D-161 | Part: A: Improvement of Road form of Satter Hazi (Pucca road) to House of Fazal at Purbo Kaltasuti Road (Ch. 00-350m), Part: B: Improvement of Purbo Kaltasuti Anwar House (BKSP Wall) to House of Kohinoor Road (Ch. 00-180m) | UNR-GDP | Savar |  | 0.35 |  |  | 2631150 | M/S. Miah Trader | 2615057 |  | 2011-04-17 | 2011-07-16 | 20

## Shivalay
SL No. | Package No. | Package Name | Project Name | Upazila Name | Road ID | Length of Road (Km) | Length of Bridge (M) | Building Qauntity (No) | Estimated Amount (Lac) | Name of Contractor | Contract Amount (Lac) | Date of Contract | Date of Commencement | Date of Completion | Physical Progress (%) | Financial Progress (Amt) | Financial Progress (%) | Date of Progress Update | Remarks
1 | PD CLBUURP, W-170 | Const. of RCC Bridge on Dhaka-Aricha NHW (Shibrampur)-Machain GC via Rupsha road at Ch. 116150m (ID No.: 356782004). | LBC | shivalaya |  | 315 |  |  | 326.05 | JV M/S nurul Islam and | 336.05 |  | 2011-02-07 | 2013-09-30 | 100
2 | UMC/MAN/SHI/ 15/C-237 | Construction of Muktijoddha Complex Building in Shibalaya Upazila , Dist: Manikganj. | CUMCP | shivalaya |  |  |  | 0 | 217.71 | M/S.Debesh Traders | 180.69 | 2016-07-26 | 2016-07-26 | 2018-01-26 | 0 | 0 | 0 | 2017-07-05 | Land disput
3 | PWA-UZC- Shibalay-103 | Construction of Upazila Complex Extention Building & Hall Room | EUCP | shivalaya |  |  |  |  | 432.29 | Starlite Services Limited | 535.62 |  | 2015-07-26 | 2016-09-15 | 100 |  |  |  | Building Qty: 2
4 | GSIDP/MNK/DW-8 | Improvement of shibalaya central shasan ghat . Union: shibalaya, Latitude: 23.840258, Longitude: 89.799977 | GSIDP | shivalaya |  |  |  |  | 6.5 | M/S. Meghna Builders | 6.18 |  | 2018-06-25 | 2018-11-11 | 0
5 | GSIDP/MNK/DW-9 | Improvement of Jhoriarbag graveyard. Union: shibalaya, Latitude: 23.808367, Longitude: 89.791533 | GSIDP | shivalaya |  |  |  |  | 7 | M/S Tanvir Enterprise | 6.65 |  | 2018-06-10 | 2018-10-28 | 100
6 | GSIDP/MNK/DW-10 | Improvement of East baulikanda sarbojonin kalimondir. Union: Arua, Latitude: 23.558321, Longitude: 89.653221 | GSIDP | shivalaya |  |  |  |  | 6.5 | M/S. Meghna Builders | 6.18 |  | 2018-06-18 | 2018-11-11 | 0
7 | GSIDP/MNK/DW-11 | Improvement of Radhakantorpur Surbojanin Durga Mondir. Union: Utholy, Latitude: 23.8630, Longitude: 89.7936 | GSIDP | shivalaya |  |  |  |  | 10 | MS. Tanvir Enterprise | 9.5 |  | 2018-09-06 | 2018-12-28 | 10
8 | GSIDP/MNK/SDW-12 | Improvement of Kesobpotty Jame Mosque. Union: Mohadebpur, Latitude: 23.8448, Longitude: 89.8473 | GSIDP | shivalaya |  |  |  |  | 10.92 | M/S. Simanta Enterprise | 10.38 |  | 2018-09-12 | 2019-01-05 | 0
9 | GDP3/MA -20 | Improvement of Ulail UP Office (Rupsa)-Upazila H/Q (Tepra) Road from CH. 1270-2700 under Shibalaya Upazila, District Manikganj. Road ID No 3576783005 | GDP-3 | shivalaya |  | 1.43 |  |  | 114.71 |  | 0 |  |  |  | 0
10 | GDP3/MA Reh-2 | Rehabilitation of Shimulia Afsar Chairman House more - Boro Butuni Bazar Road Ch.00 - 2500m Under Shibalaya Upazila District Manikganj. Road ID No 356784038 | GDP-3 | shivalaya |  | 2.5 |  |  | 66.97 | M/s M. A. Quddus | 63.63 |  | 2018-05-16 | 2018-10-15 | 100
11 | IRIDP-2/ Mnk/DW-37 | (a)Improvement of Jaforganj GC (Dhushar)-Ghior GC via Nayabari bazar Bardhamankandi, Bhorrah bz & Thakurkandi GPS road from ch.1480-2556m (b) Construction of 01 no 1x2.00x2.00m culvert at ch 1765m on the same road. | IRIDP-2 | shivalaya | 356784001 | 1.08 | 2 |  | 4856137 | M/S. Al-Mamun Traders | 4882668.41 | 2016-04-26 | 2016-04-26 | 2017-08-18 | 35 | 1044000 |  | 2017-07-05 | on going
12 | IRIDP-2/ Mnk/DW-50 | Improvement of Dhaka Aricha NHW (Falsatia)-Machain GC Via Sakrail Bazar Road from Ch.3115-4350m Under Shibalaya Upazila,Dist:Manikganj. | IRIDP-2 | shivalaya | 356782010 | 1.24 |  | 0 | 7583506 | M/S MM Bricks | 6671418.09 | 2016-10-16 | 2016-10-16 | 2017-08-24 | 20 | 0 | 0 | 2017-07-05 | On going
13 | IRIDP-2/ Mnk/DW-51 | Improvement of Arua UP office -Machain GC Via Shaljana Road from Ch.00-1000m) Under Shibalaya Upazila,Dist:Manikganj. | IRIDP-2 | shivalaya | 356783007 | 1 |  | 0 | 7242225 | M/S Raka Enterprise, Manikganj | 6764257.11 | 2016-09-28 | 2016-09-28 | 2017-08-28 | 50 | 0 | 0 | 2017-07-05 | on going
14 | IRIDP-2/ Mnk/DW-57 | (a)Improvement of Amdala Bazar-Tarail Bazar Bridge Via Maniknagar Road from Ch.2960-4160m Under Shibalaya Upazila,Dist:Manikganj. (b)Construction of 02 Nos 1x2.00x2.00m Culvert at Ch.3004 & 3334m on the same Road. (c)Construction of 01 Nos 1x2.50x2.00m Culvert at Ch.3600m on the same | IRIDP-2 | shivalaya | 356784009 | 1.2 | 6.5 | 0 | 8800219 | M/S Reba Construction Manikganj | 7393005.52 | 2017-01-03 | 2017-01-03 | 2017-10-03 | 30 | 0 | 0 | 2017-07-05 | on going
15 | IRIDP-2/ Mnk/DW-58 | Improvement of Road from Ulail UP office (Rupsha) - Upazila H/Q (Tepra) road from ch. 00-900m Under Shibalaya Upazila, Dist:Manikganj. | IRIDP-2 | shivalaya | 356783005 | 0.9 |  | 0 | 5929537 | M/S. Israfil Traders | 5354354.85 | 2017-01-30 | 2017-01-30 | 2017-08-05 | 0 | 0 | 0 | 2017-07-05
16 | IRIDP-2/ Mnk/DW-59 | Improvement of Road from Hazirbadha Botagash- Nobogram LGED Bridge via Natun Foridpur road from ch. 1650-2280m Under Shibalaya Upazila, Dist:Manikganj. | IRIDP-2 | shivalaya | 356784019 | 0.63 |  | 0 | 4582357 | M/S Hemal Traders, Garpara, Manikganj. | 4168853.08 | 2017-01-31 | 2017-01-31 | 2017-08-06 | 0 | 0 | 0 | 2017-07-05
17 | IRIDP-2/ Mnk/DW-60 | Improvement of Road from Nilgram - Tawakhali via kodalia Primary School road from ch. 347-1100m Under Shibalaya Upazila, Dist:Manikganj. | IRIDP-2 | shivalaya | 356784024 | 0.75 |  | 0 | 4923591 | M/S Hemal Traders, Garpara, Manikganj. | 4484916.03 | 2017-01-31 | 2017-01-31 | 2017-08-06 | 0 | 0 | 0 | 2017-07-05
18 | IRIDP-2/ Mnk/DW-72 | (a) Improvement of Dhaka-Aricha NHW (Khodratpara) Ekhlas Pir House to Nanno house Via Mr. mannan Chairman House Road from Ch.00-472m) Under Shibalaya Upazila,Dist:Manikganj. (b) Improvement of Khudra Tepra Ekhlas Pir SB House (Start From Mannan House) -Jalal House Ekhlas Pir House to Nanno house Via Mr. mannan Chairman House Road from Ch.250-750m) Under Shibalaya Upazila,Dist:Manikganj. | IRIDP-2 | shivalaya | 356785094.3568 | 0.97 |  | 0 | 7016874 | M/S. Twin Trade | 6972331.7 | 2017-05-17 | 2017-05-17 | 2018-01-16 | 0 | 0 | 0 | 2017-07-05
19 | IRIDP/ Mnk/W-3 | Improvement of Shimulia (Afsar Chairman house more)-Bara Butuni bazar road by BC (Ch. 00-1000m) (ID No. 356784038) | IRIDP | shivalaya |  | 1 |  |  | 4808158 | M/S. Mona Traders | 4567750.1 |  | 2010-10-11 | 2012-03-20 | 100 |  |  |  | Final
20 | IRIDP/ Mnk/W-28 | Improvement of Shimulia UP office (Darber sharif more) - Diarchar Sakrail bazar road by BC (Ch. 650-1650m) and same road for Construction of one No 1x4.30x3.60m RCC box culvert at ch., 1435m (ID No. 356783004) | IRIDP | shivalaya |  | 1 |  |  | 5968262 | M/S. Sarnamoni fish & Co. | 5669848.9 |  | 2011-03-21 | 2013-01-31 | 100 |  |  |  | Final
21 | IRIDP/ Mnk/W-30 | Improvement of Dhaka-Aricha NHW (Moshuria)-Barotia UP office (Ghior) via Mouhali Bazar road (Ch. 670-1455m) (ID No.356784014) | IRIDP | shivalaya |  | 0.79 |  |  | 3737141 | M/S. Pervez Enterprise | 3550283.95 |  | 2011-05-31 | 2012-11-29 | 100 |  |  |  | Final
22 | IRIDP/ Mnk/W-27 | Improvement of Shimulia-(Afsar Chairman’s house more)-Boro Butuni Bazar road (Ch. 1000-2500m) (ID No.356784038) | IRIDP | shivalaya |  | 1.5 |  |  | 7422095 | M/S. Rana Enterprise | 7050990.25 |  | 2011-03-21 | 2013-06-10 | 100 |  |  |  | Final
23 | IRIDP/ Mnk/W-47 | Improvement of Shibalaya UP Office (Oxford Academy)-Teota UP Office via Jamduara bazar road at (Ch. 00-1000m) under Shibalaya Upazila, Dist: Manikgonj (ID No. 356783009) | IRIDP | shivalaya |  | 1 |  |  | 5072975 | M/S. Debsh Traders | 5783385.86 |  | 2012-08-08 | 2013-05-21 | 100 |  |  |  | Final
24 | IRIDP/ Mnk/W-32 | Improvement of Dhaka-Aricha NHW (Moshuria)-Barotia UP office (Ghior) via Mouhali Bazar road by HBB (Ch. 1455-2330m) (ID No.356784014) | IRIDP | shivalaya |  | 0.88 |  |  | 3759171 | M/S. Hera Corporation | 3571212.45 |  | 2011-07-25 | 2013-02-28 | 100 |  |  |  | Final
25 | IRIDP/ Mnk/W-46 | Improvement of Dhaka-Aricha NHW (Aricha ghat)-Nali GC road at (Ch. 3550-4288m & 5023-5160m) under Shibalaya Upazila, Dist: Manikgonj (ID No. 356782009) | IRIDP | shivalaya |  | 0.88 |  |  | 6424960 | M/S. M.A Quddus | 6739783.23 |  | 2012-04-22 | 2013-06-26 | 100
26 | IRIDP/ Mnk/W-33 | Improvement of Dashchira Halipad-Satter Master house via Shangbadik Motiur Rahman House & Munshi bari road (Ch. 00-1250m) (ID No.356784038) | IRIDP | shivalaya |  | 1.25 |  |  | 4599370 | M/S. Al-Amin Enterprise | 4599370 |  | 2011-07-25 | 2013-05-30 | 75 |  |  |  | On going
27 | IRIDP/ Mnk/TP-57 | Tree plantation of Shimulia (Afsar chairman house more)-Boro Butuni road at ch. 00-2500m (ID No. 356784038) under Shibalaya Upazila, Dist: Manikgonj | IRIDP | shivalaya |  | 2.5 |  |  | 275700 | L.C.S | 0 |  |  |  | 0 |  |  |  | Contract under prosses
28 | GDP-II/MAN/ Ghi/W(B)-58 | Construction of 54.00m Long RCC Girder Bridge on Baradia (Moynar gudara) Nayabari Road at Ch.70m Under Shibalaya Upazila,Dist:Manikganj.(ID No. 356784030) | GDP-2 | shivalaya | 356784030 |  | 54 |  | 213.36 | M/s. Debesh Traders | 181.96 | 2016-02-29 | 2016-02-29 | 2017-08-30 | 80 | 158.5 |  | 2017-07-05 | on going
29 | GDP-II/MAN/ Ghi/W(R)-74 | Improvement of Kaccol- Intajganj Via Jamunabad Road at Ch.1500 -1850m.Under Shibalaya Upazila, Dist: Manikganj.(ID No. 356784012) | GDP-2 | shivalaya | 356784012 | 0.35 |  |  | 28.99 | M/s.Al-Mamun Traders | 28.48 | 2016-03-14 | 2016-03-14 | 2017-07-14 | 75 | 14.08 |  | 2017-07-05
30 | GDP-II/MAN/ Ghi/W(R)-79 | Improvement of Road Starting from Bara Butuni Bazar - Kachidhara Battala via Basepara High School road at Ch.00 -869m.Under Shibalaya Upazila, Dist: Manikganj.(ID No. 356784035) | GDP-2 | shivalaya | 356784035 | 0.87 |  |  | 57.87 | M/s.Al-Mamun Traders | 55.84 | 2016-04-26 | 2016-04-26 | 2017-08-25 | 20 |  |  | 2017-07-05 | on going
31 | RTIP-II/MAN/RPM-122 | a) Teota UP Office-Jhafargonj GC (Poila) road | RTIP-2 | shivalaya |  | 5.71 |  |  | 114.39 | Saleh and Brothers | 316.43 |  | 2014-03-12 | 2015-05-04 | 100 |  |  |  | Final
32 | RTIP-II/MAN/RPM-222 | Mohadebpur-Zitka GC via Gongasagar Road. | RTIP-2 | shivalaya |  | 9.11 |  |  | 417.51 | M/S. Niaz Traders | 379.11 |  | 2015-07-01 | 2016-08-25 | 100 |  |  |  | Final
33 | RTIP-II/MAN/RPM-302 | Uthali-Jaforgonj GC Road. | RTIP-2 | shivalaya |  | 7 |  |  | 244.42 | M/S. ANIK TRADING CORPORATION | 199.07 |  | 2016-07-10 | 2017-06-14 | 100 |  |  |  | Final
34 | PEDP-III/MNK/SHI/2011-12/W2.0551 | MALUCHI School Additional Room | PEDP-3 | shivalaya |  |  |  |  | 2993000 | M/S Rana Enterprise | 7241004.94 |  | 2013-01-13 | 2014-01-06 | 100
35 | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | KATTHALIYA School Additional Room | PEDP-3 | shivalaya |  |  |  |  | 3546000 | M/S Sthapati Construction | 6045284.14 |  | 2014-06-25 |  | 0
36 | PEDP-III/MNK/SHI/2011-12/W3.0333 | BUTUNI School Major Maintenance | PEDP-3 | shivalaya |  |  |  |  | 149532 | M/S Rana Enterprise | 657966.51 |  | 2013-01-13 | 2013-07-06 | 100

## Sheet2
Shivalay | Savar
LBC | CRDP
CUMCP | LBC
EUCP | EUCP
GSIDP | GSIDP
GDP-3 | GDP-3
IRIDP-2 | IRIDP-2
IRIDP | IRIDP
GDP-2 | IARP
RTIP-2 | GDP-2
PEDP-3 | RTIP-2
PEDP-3
UNR-GDP